## Sheet1
Joint UNDP/DPA Programme Management Response to Recommendations from External Review - DRAFT (January 2015)
Recommendation | Sub-Recommendation | Relevant Current Action | Proposed Action | Timeline | Required Activities | Funding Implications | Actor/ Unit Responsible | Status
1. Determine the Joint Programme's vision for conflict prevention | a. Draft JP's overall VISION and GOALS for conflict prevention, to include resource management strategy and JP's conflict prevention support to RCs besides PDA deployments. |  | In updating the ProDoc (2015-2017), articulate strategy that has broader focus than PDA deployments, highlighting opp for collab between UNDP and DPA across areas such as mediation/insider mediation, etc, and resource mobilization strategy developed. This should then be included in all public documents (annual report, etc) | Q1/2015 | Draft ProDoc to be reviewed/ cleared by Technical Committee. | N/A | Technical Committee | Completed (Q3/2015)
| b. Increase shared understanding within DPA and UNDP on Joint UNDP/DPA Programme | Information included in the induction programmes for DPA and UNDP HQ, as well as RCs and UNCT Heads of Agency | Regional consultations involving UNDP/RBx and DPA/RDiv to be held twice a year, one focused on PDA deployment and the other focused on other forms of JP engagement, providing forum to reflect on collaboration in region (beyond PDA deployments) and begin to shape strategy/collaboration on regional basis. | Q1 and Q2/2015 |  | N/A | UNDP/RBx; DPA/RDiv | Conducted twice per annum, with second iteration to be completed in September.
|  |  | SOPs on engagement with PDAs and collaboration through JP for [DPA AND UNDP] desk officers to be developed | Q2/2015 | SOPs for desk officers to be developed | N/A | JP Secretariat, Technical Committee | Currently being finalized.
|  |  | Share information regarding JP (and engagement with PBF) across UNDP/BPPS/GP, as resource for entire cluster | Q1/2015 | Arrange UNDP cluster-only brown bag lunch on Joint UNDP/DPA Programme (June 2015) | N/A | UNDP/BPPS, JP Secretariat | Complete
| c. strengthen theory of change of PDA deployments | justification for requesting PDA deployment should articulate rationale and theory of change, to be captured in justification/request template and PDA workplan submitted 3m after deployment. PDA to be seen as a tool (not the sole means) to advance UN's work on conflict prevention and peacebuilding, and the broader vision as articulated by the RC and UNCT (reflected in UNDAFs, CPDs, etc,) |  | Q1/2015 | Adapt introductory letters to PDAs; include discussion on workplan development during introductory calls; engage with RCs before and after PDA deployed to ensure agreement/consensus on how best to use PDA capacity; follow-up on workplan when conducting 3-month review; ensure workplan is shared with HQ and Regional counterparts; and then shared with Technical Committee to inform consideration of PDA extension. | N/A | Technical Committee, JP Secretariat | Complete.
| d. Strengthen other output areas of Joint Programme and, together with PBSO, identify additional areas of support |  | Technical Committee to agree on other areas of existing support/collaboration through Joint Programme (conflict analysis, short-term deployments, backstopping support, PDA training, support to RCs through Montreux, etc) and identify other opportunities for collaboration. To be reflected in new ProDoc. | Q1/2015 | JP to develop and implement, jointly with interested RCs, a work plan of JP conflict prevetion activities (e.g.conflict analysis) in support of UNCTs in countries where there is no PDA. |  | Technical Committee | Ongoing.
| e. Engage with DPKO, DPA, UNDP, SRSGs, DSRSGs to explore options for better linking political role of missions to programmatic capacities of UNCTs in mission settings, either through PDA deployment or other support |  | Technical Committee to identify countries where linkages between PKM/SPM and UNCT could be further strengthened; then engage with DPKO/DPA, SRSG and DSRSG/RC to identify ways and tools to forge a UN conflict prevention strategy for that country, and options for JP engagement. | Q1/Q2 2015 | Reach out to DPKO/HQ to discuss options for collaboration. | N/A | Technical Committee, DPKO | Not yet started.
|  |  | Options for JP support to UNCTs in mission settings should be explored on a case-by-case basis by DPA, UNDP, PBSO, and DPKO (if PKO) and exausted before recommending the deployment of a PDA. | ongoing |  | N/A | Technical Committee, DPKO | Not yet started.
2. Expand cooperation with PBSO and DOCO | a. Engagement with PBSO and DOCO | PBSO included in Technical and Steering Committee |  | Q1/2015 |  | N/A |  | Complete
|  | DPA and UNDP engagement in Task Team to facilitate information-exchange, shared analysis, and coordination, to inform considerations of JP engagement | More regular info-exchange with DOCO to have overview of UNDAF countries, HRA deployments and RCO capacities, to inform considerations of PDA deployments | Q1/2015 | JP Secretariat to be involved in Task Team discussions to share information regarding PDA deployments and other JP activities, as well as DOCO's periodic inter-agency discussions regarding capacity deployments | N/A | JP Secretariat, Technical Committee | Complete
3. Enhance prioritization and quality of support and resources provided to PDAs | a. Enhance prioritization of PDA deployments | Based on revised SOP criteria (Jan '15) | Engage with UNDP/RBx, DPA Rdivs, and PBSO to prioritize PDA deployments | Q1/2015 | February consultations | N/A | Technical Committee | Complete
| b. Review cost-sharing requirements |  | Define 'exit strategy' for PDA deployments in certain country contexts (with key milestones to be measured over time, including recruitment and training of national PDA, etc) | ongoing |  | N/A |  | Ongoing. To be initiated for countries identified through criticality assessment
| c.Enhance capacity to provide short-term deployments | PDA profile currently included in UNDP/ExpRes Roster, and used to identify candidates for short-term deployments | Engage with UNDP/RBx, UNDP/CRU, DPA/RDiv, DPA/PMD, and other agencies (as appropriate), including DPKO and DESA, to identify appropriate internal/external candidates for short-term PDA deployments, to be added to the UNDP/ExpRes Roster. | Q3/2015 |  | N/A |  | Ongoing.
|  |  | Have a public "call for applications" across the PDA-COP mailing list and other networks (including PBF and PBSO CoPs) calling for submission of profiles for PDA short-term roster | Q3/2015 | Engage with UNDP/RBx, UNDP/CRU, DPA/RDiv, DPA/PMD, and other agencies (as appropriate), including DPKO and DESA, to identify appropriate internal/external candidates for short-term PDA deployments, to be added to the UNDP/ExpRes Roster. | N/A |  | On track. Q4/2015
|  |  | Ensure resources earmarked within JP to cover at least six short-term deployments of up to four months, and more systematically advocate short-term deployments instead of full-time PDA deployments in certain country contexts. | ongoing |  | USD 200,000 p.a |  | Completed, reflected in new Programme Document
|  |  | Work closely with DPA/MSU to access expertise in Mediation Roster for short-term PDA deployments | Q2/2015 |  | as above |  | Ongoing
|  |  | Support pre-vetted UNDP and DPA staff undertake short-term assignments in support of PDA | ongoing |  | USD 100,000 p.a | DPA resources secured through XB. | Not yet started/ systematic
| d. Strengthen options for recourse for PDAs in instances where relationships with RC, UNCT is challenging. | 4m and 360 review process, as part of JP SOPs. | Have follow-up call with PDA and RC after completion of 4m review, to gauge nature of challenges not necessarily captured in 4m review (relationship with RC, UNCT agencies, etc). Would need to be at a suitably high level. | ongoing |  | N/A | JP Secretariat | Not yet started/ systematic
|  |  | In contexts where PDA function is not adequately supported by the UNCT, engage with relevant UNDP/RBx to initiate discussion with RC to clarify roles, expectations, and address any challenges that may limit the PDA's capacity to perform as initially envisaged. | ongoing |  | N/A | Technical Committee | Not yet started/ systematic
| e. Provide PDAs with programmatic and operational resources | PDAs provided with USD 50,000 to undertake conflict analysis for UNCT. Funds managed by RCO. | Provide USD 50,000 as standard package of support to all new PDA deployments, to cover both conflict analysis exercises as well as PDA operational costs. PDA and RC to report back to the Technical Committee on the utilization of funds provided to support the PDA deployment. | ongoing | Include additional USD 50,000 to PDA deployment costs | USD 50,000 per PDA deployment | Technical Committee | Offered to all new deployments, with criteria established
|  | Cost-sharing with PBSO in cases where PRF funding is provided, offers PDAs with avenue to inform and design programmatic responses to conflict prevention/ peacebuilding. | Pilot country settings with PDA's serving as head the Joint Steering Committee Secretariats. This would give them direct strategic control over important peacebuilding resources. They should have enough resources to make sure that this role doesn't take too much of their time. | ongoing |  |  | Technical Committee, PBSO | Complete
4. Maintain continuity between successive PDA deployments | a. Aim to have overlap period between successive PDA deployments, or ensure "lifeline" available between current and former PDA |  | Following 360 Review, and in conversations with Resident Coordinator, begin recruitment processes for successive PDA deployments three months prior to PDA departure. | ongoing |  | N/A | Technical Committee | Not yet started
| b. Ensure timely PDA deployments in contexts of mission transition/withdrawal |  | Regional consultations to identify pipeline priority countries, including those where missions are set to withdraw. | Q1/2015 |  | N/A | Technical Committee, UNDP/RBx and DPA/Rdivs | Complete
| c. Institutionalize PDA handover notes | All exiting PDAs required to complete handover note | Make use of UNDP's Oslo Governance Centre and support exiting PDAs to undertake a two-week end-of-assignment mission to Oslo to write and finalize handover notes, lessons learned, and engage with govt and civil society counterparts in reflection/discussion. |  |  | USD 100,000 p.a |  | on track
| d. Ensure joint missions take place within three months of PDA deployments to support the development of a UN conflict prevention strategy for the country, particularly when first time PDA deployment in particular country | Currently done on ad-hoc basis | Need to engage with UNDP/RBx and DPA/RDiv to a) secure resources for joint missions based on annual projections (up to 10 or 15 per year); b) engage with UNDP/RBx to align missions with other types of programmatic/country support provided |  |  | USD 150,000 p.a | UNDP/RBx; DPA/RDiv | ongoing
| e. Engagement with PBSO to ensure more coherent and sustainable support to UNCTs and national stakeholders on conflict prevention and peacebuilding | In appropriate countries, options for linking long-term PRF funding to medium to long-term PDA deployments, to inform DPA, UNDP, and PBSO strategies and engagement |  | ongoing |  | N/A | Technical Committee, PBSO | In context of AGE report, linking PDAs to IRF being explored
5. Increase opportunities and venues for RC and PDA peer-to-peer exchange | a. Maintain 'Montreux' series for Resident Coordinators | Montreux workshop held every two years (next in 2016) |  | Q2/2016 |  | N/A |  | on track
|  | Reflections series, published twice a year |  | Q2/2015 |  | N/A |  | Q1/2015
| b. PDA peer-to-peer exchange | Global PDA retreats held every two years |  | Q3/2015 |  | USD 300,000 |  | ongoing
|  | Regional retreats ad-hoc, with some regions more regular than others | [5 empty] | ongoing
|  |  | Bi-annual cross-regional retreats focused on particular thematic areas, not necessarily requiring global attendance but on key issues/emerging challenges facing select number of PDAs (organized crime, etc). Explore possibilities to trial joint workshops with PBF regional workshops. |  | Work with DPA and UNDP (at HQ and Regional levels) to identify cross-regional thematic issues on which to bring together smaller groups of PDAs to exchange experiences, good practices, etc. | USD 200,000 p.a | UNDP/BPPS, UNDP/RBx, DPA/RDiv | Not yet started
|  |  | Facilitate peer-to-peer exchange with Standby Team Mediators and establish mechanism of support by mediation standby-team to PDAs and RCs. | Q2/2015 | Include one or two SBT Members in Global PDA Retreats; undertake joint "lessons learned" in countries where SBT Member deployed and working with PDA | N/A | DPA resources secured through XB. | Not yet started
6. Increase substantive and technical support to PDAs | a. Clarify PDA reporting expectations | Ensure PDA reports are shared within region and sub-region, to ensure "common standard" and opportunities for regional collaboration are facilitated. | Apply to all regions | Q2/2015 |  | N/A |  | ongoing (though not uniform)
|  |  | Have UNDP and DPA Technical Committee representatives communicate importance of engaging with PDAs on reporting (with respective desks), possibly with message to come from Co-Chairs | Q1/2015 |  | N/A |  | Not yet started. Once guidelines for desk engagement are finalized, to be disseminated broadly.
| b. Improve engagement with PDAs following report submission | ad hoc teleconferences based on need/submitted quarterly reports | "Core groups": i) scanning of report by Programme Analyst (JP) and country focal points; ii) proposed engagement with technical expertise (DPA and UNDP and PBF, where applicable); iii) follow-up call plan planned within three weeks of submission. Relevant colleagues from DPA/MSU, EAD, UNDP/BPPS Technical Teams to be involved, as needed. Adjust PDA reporting guidance to include section where PDAs "check boxes" on the types of thematic/country support required following report submission, to in turn help identify appropriate capacities to be included in "core group" | Q1/2015 (ongoing) | To be discussed with Technical Committee. | N/A |  | ongoing (though not uniform)
|  |  | Map existing country-specific forum for countries where PDAs are deployed, and strengthen linkages with PDA's work and support provided by HQ. | Q2/2015 |  | N/A | Technical Committee | Not yet started
| c. Identify and address reasons behind gender disparity of PDA cadre | FBA commissioned study ongoing | Implementation of study recommendations to address gender inbalance |  |  | USD 50,000 (secured through FBA) |  | Proposed responses to be presented for Steering Committee endorsement (Q4/2015)
| d. Enhance support to, and development of, national PDAs |  | shadowing' missions to countries where international PDAs are deployed and local need has been identified by RC/UNCT |  |  | USD 50,000 p.a |  | ongoing
|  | Deployment of national UNV/PDAs |  | Q1/2015 |  | USD 75,000 p.a (USD 15,000 per national UNV) |  | ONGOING
|  | increase recruitment/training/ participation of national PDA cadre in PDA retreats |  | Q3/2105 |  | USD 75,000 p.a |  | ONGOING
7. Retain PDAs within the UN system | a. Career Development |  | Have PDAs considered in management track of UNDP, DPA, etc, (UNDP and DPA need to engage with respective HR focal points) | Q3/2015 | Establish working group of UNDP and DPA colleagues to discuss HR-related matters pertaining to PDAs, and identify ways of advancing discussions with OHRM and UNDP/HR. | N/A |  | Not yet started
| b. Mobility: lateral moves; PDAs as ‘internal candidates’; DPA and UNDP exchanges; HQ/field swaps | Engage with UNDP Senior Management/ RBx to facilitate lateral moves | DPA to have PDAs as ‘internal candidates’ (To be included in revised Partnership Note to be signed by UNDP Administrator and DPA USG, and taken forward within respective organizations) | Q3/2015 | As above | N/A |  | ongoing
8. Increase visibility, documentation and knowledge management | a. Better capture and communicate results achieved (and supported by) PDAs | Lessons learned/ success stories done on ad-hoc basis | Conduct "call" for PDA success stories and lessons learned on a regular basis (perhaps twice a year?), encouraging PDAs to draft (or work with CO, Regional, or HQ colleagues). To be published in semi-annual newsletter circulated amongst currently deployed PDAs, UNDP and DPA HQ, and donor counterparts. | Q2/2015 |  | N/A |  | Q4/2015 (once P2 position is filled)
|  | success stories to be included in 2014 Annual Report |  | Q1/2015 |  | N/A |  | Complete
9. Engage with donors to secure more predictable resources |  |  | Engage with current and prospective donors in reviewing draft JP review and management response | Q1/2015 |  | N/A |  | Complete
|  |  | DPA and UNDP high-level engagement with PRs of current and former donors to the JP | Q2/2015 |  | N/A |  | Complete