## Sheet1
PIMS 3796 Malaysia PA Financing Project Midterm Review
Management Response & Key Actions
| MTR Recommendation | Management Response | Key Action identified | Responsible Agent | Status (Not Initiatied/ Initiated/ Completed/ No Longer Applicable PLEASE UPDATE THE BELOW | Due Date (PLEASE UPDATE THE BELOW) | Comments | Update as of 29 March 2021
High Level Recs | 1. Implement Key Actions to Achieve Performance-Based Sustainable Financing Standards
| Key Action 1: Ensure budget considerations for PAs are included under the Malaysia Plan, every 5 years. | 1.1 Currently the National Conservation Trust Fund is being operated by the Ministry of Natural Resources and Environment (NRE) with an allocation of RM 10 million from the Government. The PA Financing Project helped NRE to develop the Operating Guidelines to operationalize the Fund, which include a set or criteria for project selection; approval and monitoring and evaluation. In January 2018; the Project has initiated with the engagement of a resource person to undertake study on developing “Strategic Plan and Resource Mobilization for National Conservation Trust Fund”. The study will provide options and strategic directions for strengthening the management and ensuring long term sustainability of the Fund. | 1. Undertake study on developing “Strategic Plan and Resource Mobilization for National Conservation Trust Fund | KATS, DWNP, MEA and PMU | on-going | 2018-12-31 | Recommendations to restructure NCTF have been submitted to KATS in September 2018. KATS acknowledged the need to restructure the NCTF and exploring the option of reviewing Section 10 of Treasury Regulations under which the Fund currently being operated. With the support of PA Financing Project “Resource Mobilization Strategy” being developed and wider level of stakeholders consultations are planned particularly with potential contributors into the Fund.
| Key Action 2: Revisit the fundamental issues of performance based financing | PA Financing Project collaborating with BioFin Project developing guidelines and criteria for budget proposals and allocation for conservation of biodiversity related programmes and projects under the Malaysian Five Year Plan. It is envisaged that these guidelines will be incorporated into the planning process of 12th Malaysia Plan; and elements of biodiversity conservation will be made part of criteria for budget allocation to the line ministries and agencies. | 2. Developing BioFin guidelines which is to be submitted to MEA by the end of 2018 | KATS & MEA | on-going | 2018-12-31 | Project is collaborating with BioFin activity, conducted a training session for state governments and agencies on financial planning for conservation in March 2018. Further training sessions are planned targeting specific training needs of participating states such as Johor and Perak. Meantime, findings and observations from BioFin Phase 1 activities will be advanced further for the consideration of decision makers in MEA and MOF; particularly to incorporate BioFin methodology/criteria for 12th Malaysia Plan projects.
| 2. Establish Action Plan on Protected Areas and Sustainable Finance | In January 2018, the Project initiated study on “The Economics of Economics and Biodiversity (TEEB)” for three target sites Taman Negara; Endau Rompin and Royal Belum. The study plans to develop evidence base for increased financial support and investment for the PAs by demonstrating its economics and non-economics contribution and values to the society. | 3. Study on “The Economics of Economics and Biodiversity (TEEB)” for three target sites Taman Negara; Endau Rompin and Royal Belum | KATS, MEA, DWNP, JNPC, PSPC | Initiated | 2020-04-01 | Two resource persons have been engaged in January 2018 to undertake study. In May 2018, the resource persons undertook extensive stakeholders’ consultation with participating states and implementing partners DWNP, JNPC and PSPC. The sessions helped to identify key areas for economic valuation for the 3 sites as well as targeted respondence (approximately 1300 for each site involving four categories) for the survey. Findings from the survey will provide fundamental inputs for the economic valuation for the 3 sites. PA Financing Project and UNDP are currently in the process of appointing a survey company and it is expected that the survey will start in June 2019. | The study of TEEB will be completed by June 2021 pending collection of data for 'Cost Conservation Surveys' from nine State Forestry Departments. Due to MCO restrictions, a planned workshop with the State Forestry Departments in December 2020 had to be postponed. Alternatively, inputs are being obtained via virtual calls with each of the State Forestry Departments
|  | Another study on “Sustainable Financing Plan” will be undertaken in 2018 targeting the three PA authorities: DWNP; JNPC and PSPC. This study will explore various market and non-market based financial mechanisms that could be adopted by the PA agencies for generating additional revenues at site and agency level. | 4. Study on “Sustainable Financing Plan” will be undertaken in 2018 targeting the three PA authorities: DWNP; JNPC and PSPC | KATS, DWNP, JNPC, PSPC & State Govts | Initiated | 2019-12-31 | PMU decided not to launch a separate study. Findings from Business Plans developed for DWNP, JNPC and PSPC and lessons from BioFin will be further evaluated and enhanced through series of training sessions for the agencies with the aim of strengthening conservation financial planning.
| 3. Strengthen Budget Planning and Budget Platform | Capacity building programme will be conducted for the Federal and State agencies. The BioFin methodology will be introduced, a structured method of developing financial planning for conservation of biodiversity. Whilst findings of TEEB provides economical argument for increased investment for conservation; the BioFin methodology will able to enhance the planning capacity for incorporating elements of conservation into development projects and programme. | 5. BioFin training workshops for federal & state planning units, to introduce the BioFin methodology | MEA, MOF, PA Agencies | Initiated | 2019-12-01 | Will be addressed together with actions planned for Recommendation No. 2.2.
|  | Another initiative is to explore the establishment of Business development unit in PA management unit. This recommendation was raised through the findings of Business Plans developed for the three PA agencies – stress the need of a dedicated unit focussing on financial planning for conservation. | 6. Establishing dedicated Business Development Units in the PA Managements | PA Agencies | Initiated | will be determiened by respective PA agencies and state governments | It is the States’ government’s discretion to decide on the process and when to establish the Unit. However, for both Perak and Johor the immediate priority is to strengthen capacity of existing for financial planning for conservation within the existing planning units.
| 4. Develop and Pilot-Test Sustainable Financing Mechanisms | Business Plans have been developed for the three PA agencies (DWNP; JNPC and PSPC) highlighting funding options and mechanisms that could be adopted and implemented at site and agency level. These options and mechanisms will be further scrutinized assessing the viability of implementation with the Agencies in accordance with legal mandate vested with them. In addition, the Sustainable Financing study also will able to provide some insights into this | (key action #4: Sustainable Financing Study) |  |  |  | Will be addressed together with recommendations 2 and 3.
| 5. Promote Institutional Strengthening at All Scales to Achieve Sustainable Finance Goals | IBD transformation plan to develop into a national training centre catering the capacity and skills development needs of PA agencies in the Country. The Project extends technical assistance to develop strategic actions particularly to strengthen IBD’s training portfolio. | 7. IBD restructuring plan developed | KATS, DWNP, JPA | Initiated | 2019-12-31 | In December 2018, a brainstorming session was organized to develop strategic framework for IBD transformation. The resource persons engaged from SPEEARS International applied ‘Contextualized Leadership Execution” method to gauge the leadership ability amongst DWNP officials to spearhead the IBD transformation. At the end of the Brainstorming session a framework outline for IBD transformation was produced through a comparative analysis with similar institutions around the world and major roles played by them in biodiversity conservation. The framework outline helps to identify areas and functions of IBD that could be further enhanced within the capacity and competency of DWNP. A workshop is scheduled from 2 till 4 May 2019 with the aim of presenting the framework outline to KATS; JPA and MOF; and to develop implementation plan.
|  | The six weeks training programme on “Effective Protected Area Management (EPAM)” will be strengthen further by acquiring professional accreditation for the programme. | 8. Professional accreditation for the Effective Protected Area Management (EPAM) training programme obtained | DWNP, JPA | Completed? | 2018-12-31 | DWNP is working with MQA and UiTM to obtain professional accreditation for EPAM by 2019.
|  | Financing Project collaborating with BioFin initiative to introduce methodologies for biodiversity conservation financial planning at all level: Federal; State and Agencies. In addition to specialised training sessions; this will be carried out through Sustainable Financing Study. | (key action #5: BioFin training workshops for federal & state planning units, to introduce the BioFin methodology) |  | Initiated |  | First training session is scheduled in March 2018. Target group all States Economic Planning Units and States Finance Offices.
| 6. Confirm That Government Actions Intended to Support and Strengthen Biodiversity Conservation, Actually Do So | The Government (NRE; DWNP and other key agencies will embark on National Policy on Biodiversity (NPBD) roadshow heightening the objectives; programmes and targets to be achieved with the State Governments. The Policy will provide the basis for financial planning for biodiversity conservation related program and projects. | 9. NPBD policy roadshow | MEA, MOF, KATS, DWNP, Federal & State agencies | Not initiated | 2021 (12MP) | To be planned for 12 MP period | As the NPBD 2016-2025 is currently under review and will be completed by end of 2021, KeTSA will be organizing the roadshows starting from 2022. New deadline for the completion of roadshows will be December 2025.
|  | PA Financing Project provides support to PA Agencies in-terms of revision of respective “Enactments” and study on sustainable financing. There is general consensus amongst PA agencies and State governments to strengthen and the governing structure (legal framework) and study the options and mechanisms for creating improved financing modes for biodiversity conservation programmes. | Technical support to reviews of state enactments relating to PA management | KATS, DWNP, Park Agencies | Initiated | 2019-12-31 | Project decided to withdraw support to Johor for JNPC Enactment review, as the proposed review was not in conformity with GEF/UNDP’s principles for technical assistance. A meeting was held in March 2019 with Pahang, Terengganu and Kelantan with regard to review/repeal of Taman Negara Enactment and produce a new Enactment. Project will help to develop a “concept paper” raising all the critical pre-conditional issues that must be addressed before proceeding with drafting a new enactment. The next course of actions will be decided by the respective States and agencies. Perak recently only submitted its request for PSPC Enactment review, however it is too late for Project to initiate and complete the process within the remaining project period. Attention will be given to develop SOP for enforcement (wildlife crime; poaching) as part of Management Plan strategies for RBSP.
|  | Developing strategic plan and resource mobilization strategies for NCTF. The study will elaborate on the various strategic options to transform the fund into and independently managed ensuring long term sustainability of funding sources; and mechanisms to address the financing gaps amongst the PA agencies. | Study on NCTF strategic plan & resource mobilization strategies | KATS, MEA, DWNP | Initiated | 2019-12-31 | The 1st draft of “Resource Mobilization Strategy” for NCTF will ne submitted to KATS in April 2019.
| 7. Promote Greater Community Engagement and Empowerment | Collaborating with PA agencies, developing mechanisms to engage the local communities for co-management in line with management plan of Endau Rompin (JNPC). With support of Project the local Community have formed a Cooperative which will help them to develop income generating opportunities as well as addressing land tenure issues faced by them. The Cooperative also can be used as a platform by the PA authority to engage the Community in an effective manner. | Engagement with local communities through cooperatives formed for developing income generating activities | UNDP, DWNP, PSPC, JNPC, MOTAC, JAKOA, PMU | Initiated | 2019-12-31 | A number of training and consultative sessions involving ERNP local communities were conducted. In addition, in December 2018 a dialogue between local communities from Krau Wildlife Reserve and government agencies was conducted.
|  | To prioritize the strategies and action plans elaborated in Management Plans for three Parks, related the co-management of the parks with the engagement of local communities. | involving local communities through engagement platforms established | DWNP, JNPC and PSPC | on-going | 2019-12-01 | Addressed by respective agencies. JNPC plans to organize a session with local communities on the management zone planning. Perak prioritized strengthening of enforcement and project will support developing SOP.
|  | To collaborate with IC – CFS with focused intervention for engaging local communities and CBOs. IC-CFS will built upon the capacity building platform developed for CBOs and local community; developing income generating opportunities at site levels. | utilising capacity building platform developed by IC-CFS project to engage local communities | PMU, DWNP, JNPC, PSPC, IC-CFS PMU | Initiated | 2019-12-31 | Due to IC- - CFS is undergoing restructuring, planned collaborative activities are put on hold.
| 8. Extend the Project Timeframe | The Department of Wildlife and National Parks (DWNP) as implementing partner of PA Financing Project will submit the request for extension of project timeframe. | Submission of project extension | DWNP and UNDP | Submitted | 2018-06-01 | Taking into account government procedural and decision -making process; extended project timeframe is necessitated to realize some of the Project’s outputs and results.
| 9. Continue High-Level Engagement For Greater Buy-In and More Effective Implementation of the Project | Processes have already been put in place to communicate the Project’s outputs and intended results to the decision makers particularly in Johor and Perak. This process will be continued by producing appropriate project communique assisting the PA authorities and State Government to adopt and implement Project’s outputs. This includes: Management Plans for PAs; review of legal framework and mechanisms for sustainable financing. The Project will provide additional support by assisting the PA agencies to prioritize strategies and action plans from the Management Plans for implementation. | Developing knowledge products such as PA Management Plans, legal framework reviews, and sustainable financing mechanism report, as well as action plans | PMU, DWNP, JNPC, PSPC, | Initiated | 2018-12-01 | All the 3 agencies DWNP, PSPC and JNPC have formally adopted their respective management plans. plans to table the Plan to PSPC’s board for adoption of Management Plan for Royal Belum.
Medium Level Recs | 10. Ensure That Indicators in the SRF are Specific, Measurable, Achievable, Relevant and Time-Bound (SMART) | PMU will undertake the review of SRF to determine the validity and applicability of the targets and indicators as set in the project document. | SRF review | PMU | Completed | 2018-12-31 | It was tabled at the NSC meeting on the 30th November 2017, and PMU incorporated inputs and comments from NSC into SRF.
| 11. Strengthen Communication and Coordination, and Leverage Collaboration Between the PA Financing Project and Related Initiatives | Collaborating with BioFin project, introducing the methodology for conservation financial planning to Federal and State Agencies. | Key action #5 | PMU | on-going |  | A training workshop on BioFin iwas conducted in March 2018, targeting State Government planning units.
|  | In collaboration with IC – CFS, joint initiatives focusing on local communities engagement in conservation; in addition capacity building and creating livelihood and income generating opportunities | Joint initiatives with IC-CFS to engage local communities | PMU & IC-CFS PMU | stalled | 2019 (pending IC-CFS restructuring) | Due to IC- - CFS is undergoing restructuring, planned collaborative activities are put on hold.
| 12. Establish More Effective Communications Platform Linking Up the States of Pahang, Terengganu and Kelantan in Taman Negara | DWNP will look into the possibilities of establishing “management committee” for Taman Negara comprising the 3 States, coordinating implementation of Management Plan and addressing related issues. Meantime, Taman Negara “Enactment” will be reviewed with the aim of streamlining the governing legal framework for Taman Negara between the 3 States. | Establishing management committee for Taman Negara & reviewof enactments between 3 states | KATS, DWNP | Initiated | 2018-12-31 | KATS and DWNP have initiated coordination meeting with the respective states. As a result agreement has been reached to review Taman Negara Enactment. In this regard, a meeting was held in March 2019 with Pahang, Terengganu and Kelantan with regard to review/repeal of Taman Negara Enactment and produce a new Enactment. Project will help to develop a “concept paper” raising all the critical pre-conditional issues that must be addressed before proceeding with drafting a new enactment. The next course of actions will be decided by the respective States and agencies.
| 13. Apply a “Theory of Change” Approach |  | within the jurisdiction of respective governments agencies |  | Not initiated |  | Project management will need to discuss considering the jurisdiction issue and GEF requirements