|  |  |  |
| --- | --- | --- |
| **UNDP Management Response Template** | | |
| Date: 29 September 2021 | | |
| Project BRA/12/G76 - HCFC Phase Out National Programme | | |
| Prepared by: Ana Paula Leal | Position: Project Manager | Unit/Bureau: UNDP Brazil |
| Cleared by: Juliana Wenceslau | Position: Strategic Planning Officer | Unit/Bureau: UNDP Brazil |
| Input into and update in ERC: 30 Sept 2021 | | Unit/Bureau: UNDP Brazil |

|  |
| --- |
| **Overall comments:** |

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Evaluation Recommendation or Issue 1:**  It is recommended for this type of project to estimate a longer time in the initiation phase, considering the need for awareness and dissemination of technical, administrative and financial knowledge to the stakeholders involved in order to prepare them for change. | | | | |
| **Management Response:**  It should be highlighted that all lessons learned, and cooperation established during the successful implementation of HPMP Stage I served as basis for the activities to be implemented during HPMP Stage II. In line with this recommendation, the Project BRA/16/G76 HCFC Phase Out National Programme – Stage II is under substantive review to postpone the deadline from 31 December, 2021 to 31 December, 2024. | | | | |
| **Key Action(s)** | **Time Frame** | **Responsible Unit(s)** | **Tracking** | |
| **Status** | **Comments** |
| Adopt measures to extend the deadline for the Project BRA/16/G76 execution up to December 2024. | May, 2021 | UNDP | On going | -- |