Management response template

**UNDP management response template**

**[Name of the Evaluation]** Date: 31 December 2021

Prepared by: Miao Weijie Position: Project Coordinator Unit/Bureau: Department of Climate Change, MEE

Cleared by: Sun Zhen Position: Deputy Director General Unit/Bureau: Department of Climate Change, MEE

Input into and update in ERC: Position: Unit/Bureau:

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Evaluation recommendation 1.**  **More specific plan on risk control and adaptive management** | | | | |
| **Management response: Agree. A more specific risk control and adaptive management plan has been developed in 4NC project design.** | | | | |
| **Key action(s)** | **Completion date** | **Responsible unit(s)** | **Tracking\*** | |
| **Comments** | **Status**  **(initiated, completed)** |
| 1.1 More specific risk control and adaptive management plan has been developed in 4NC project design | December, 2021 | *MEE,*  *UNDP CO* | N/A | Completed |

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Evaluation recommendation 2. –More inclusive stakeholder engagement plan**  **1).More stakeholders could be involved in the future NC project, for instance, the industrial associations could be involved in 1) project design; 2) substantial inventory development.**  **2).PSC members could be more inclusive, to involve more industrial partners (such as more industrial associations)**  **3).The PSC members could play more active role, not only in annual project planning and meeting, but also more project daily management decision-making activities.** | | | | |
| Management response: Agree. 4NC PSC will include more government departments, which is broader than before. The relevant industry associations will also be invited to participate in the 4NC, and provide suggestions for developing GHG inventories. 4NC PMO will cooperate with the PSC for the annual planning and carry out the daily management under the guide from PSC. | | | | |
| **Key action(s)** | **Completion date** | **Responsible unit(s)** | **Tracking** | |
| **Comments** | **Status (initiated, completed)** |
| 2.1 PSC include more stakeholder | December, 2021 | *MEE,*  *UNDP CO* | n/a | Completed |

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Evaluation recommendation 3.**  **Feasibility study to move the PMO to the outside of MEE** | | | | |
| **Management response**: Agree. 4NC PMO has been transferred to the Foreign Cooperation and Exchange Center (FECO) rather than the inner departments of MEE. FECO will provide sufficient professional and technical personnel for PMO and project management. | | | | |
| **Key action(s)** | **Completion date** | **Responsible unit(s)** | **Tracking** | |
| **Comments** | **Status (initiated, completed)** |
| 3.1 4NC PMO has been located in FECO rather than the inner departments of MEE | July, 2022 | *MEE,*  *UNDP CO* | n/a | Initiated |
| **Evaluation recommendation 4. Documentation, and Dissemination of Success Stories, as well as more knowledge sharing actions** | | | | |
| **Management response:** Agree. The important outcomes from 3NC project will be published and disseminated to share the China’s experience in developing GHG inventories as well as NC and BUR. 4NC project will further strengthen propaganda and exchange on China’s mitigation and adaptation measures as well as south-south cooperation on climate change through meeting, workshop, brochures, reports and international exchanges. | | | | |
| **Key action(s)** | **Completion date** | **Responsible unit(s)** | **Tracking** |  |
|  |  |  | **Comments** | **Status (initiated, completed)** |
| **4.1 The important outcome from 3NC has been publishing** | **The first quarter of 2022** | *MEE,*  *UNDP CO* | n/a | Initiated |
| **4.2 New propaganda plan has been designed in 4NC workplan.** | **December, 2021** | *MEE,*  *UNDP CO* | n/a | Completed |
| **Evaluation recommendation 5. Seek new South-South cooperation project under the coordination of UNDP**  **During the TE process, in consultation with MEE and NPD, it was found that there were extensive South-South cooperation activities on climate change are being conducted by MEE with other countries under the framework of BRI, and MEE is very interested in seeking opportunities to develop NC related cooperation under its BRI program, so, is suggested by TE, during the preparation of 4NC, the preparation team could hold special consultative meetings with MEE and UNDP reginal office to discuss the feasibilities of these kind of cooperation under 4NC** | | | | |
| **Management response:** Agree. We are willing to communicate with UNDP on the NC reports development under BRI, will discuss the possible time for meeting or workshop. | | | | |
| **Key action(s)** | **Completion date** | **Responsible unit(s)** | **Tracking** |  |
|  |  |  | **Comments** | **Status (initiated, completed)** |
| 5.1 Communicate with UNDP for the possible meeting time | The first quarter of 2022. | *MEE,*  *UNDP CO* | n/a | Initiated |

\* Status of implementation is tracked electronically in the ERC database.