Management response template

**UNDP management response template**

Date: 02/06/2022

Prepared by: James Angok Position: PMS, GEMS Project Unit/Bureau: South Sudan

Cleared by: Position: DRRP Unit/Bureau: South Sudan

Input into and update in ERC: Position: Unit/Bureau:

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Evaluation recommendation 1.**  Continuation with the GEMS Project focus and depth from a holistic and future looking perspective. | | | | |
| **Management response:**  **Agreed:**  UNDP South Sudan noted the recommendation and will continue to look for options for strategic capacity injection in political and economic governance institutions. | | | | |
| **Key action(s)** | **Completion date** | **Responsible unit(s)** | **Tracking\*** | |
| **Comments** | **Status**  **(Initiated, completed or no due date)** |
| Initiate talks with other donors and development partners to support project extension | December 2022 | RR/ and DRRP |  | Initiated |
| Incorporate GEMS project  lessons learned and results in the design of similar UNDP projects to reinforce the intervention for collective results | December 2023 | DRR-P/ Governance Advisor  DGSU Team Leader |  | Initiated |

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Evaluation recommendation 2.**  Mainstreaming transformative institutional capacity building in the next UN Cooperation Framework for Sustainable Development. | | | | |
| Management response:  **Agreed.**  UNDP will continue working with UN agencies and other partners to extend its leadership role in capacity building of government insinuations | | | | |
| **Key action(s)** | **Completion date** | **Responsible unit(s)** | **Tracking** | |
| **Comments** | **Status (initiated, completed or no due date)** |
| Advocate for and work with UN agencies, government, and other development partners to design a joint programme on capacity building, which will be mainstreamed in the next UNSDCF for South Sudan | December 2025 | RR/DRRP / Governance Advisor |  | Initiated |

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **Evaluation recommendation 3.**  **Rehabilitation of the National Public Service Training Centre.** | | | | | | |
| **Management response**: Agreed:  UNDP will advocate and look for other donors for supporting Rehabilitation of the National Public Service Training Centre | | | | | | |
| Advocate for and support the rehabilitation of the National Public Service Training Centre. | December 2025 | | **DGSU team leader** | |  | No due date |
| **Evaluation recommendation 4.**  **GoSS prioritizing capacity building in its national plan** | | | | | | |
| **Management response**:  **Agreed:**  UNDP South Sudan noted the recommendations and will support the government capacity building initiatives | | | | | | |
| Dialogue with UN agencies and other development partners to support the government capacity building initiatives. | | December 2025 | RR/  DRR-P/  Governance Advisor |  | | Initiated |

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Evaluation recommendation 5.**  **Developing adaptive management and exit strategy** | | | | |
| Management response:  **Agreed:**  UNDP will prepare clear implementation plan that emphasise on the smooth transition of the revised GEMS project | | | | |
| **Key action(s)** | **Completion date** | **Responsible unit(s)** | **Tracking** | |
| **Comments** | **Status (initiated, completed or no due date)** |
| Engaging the government and developing clear and informative implementation plan for the remaining period of the project | August 2022 | GEMS PM and DGSU team leader |  | Initiated |

\* Status of implementation is tracked electronically in the ERC database.