Management response template

**UNDP management response template**

Date: 07/06/2022

Prepared by: Solomon Yimam Position: M&E Specialist Unit/Bureau: South Sudan

Cleared by: Amit Arora Position: PMSU Team Leader Unit/Bureau: South Sudan

Input into and update in ERC: Position: Unit/Bureau:

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Evaluation recommendation 1.**  Ensure continued alignment of the Cooperation framework to national planning frameworks and strategies and pay special attention to emerging issues related to climate change, environment, gender, youth, and private sector | | | | |
| **Management response:**  **Agreed:**  To ensure national ownership and relevance of the UNSDCF, UNDP will contribute to and advocate for alignment of the Cooperation framework to national planning frameworks and strategies. | | | | |
| **Key action(s)** | **Completion date** | **Responsible unit(s)** | **Tracking\*** | |
| **Comments** | **Status**  **(Initiated, completed or no due date)** |
| UNDP will contribute to and advocate that the 2023-2025 UNSDCF design to be strongly linked to the R-NDS priority areas, SDGs | March 2023 | RR, DRRP, Results Group Leads and M&E Specialist |  | Initiated |

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Evaluation recommendation 2.**  Deepen the New Way of Working and strengthen coherence between UNCF and other key frameworks like PfRR, HRP, Mission Strategic vision, while extending collaboration to new donors on recovery and resilience building | | | | |
| Management response:  **Agreed:**  UNDP, as a co-chair of PfRR, will work and advocate for ensuring effective collaboration and coordination for better synergies and avoid duplication of efforts | | | | |
| **Key action(s)** | **Completion date** | **Responsible unit(s)** | **Tracking** | |
| **Comments** | **Status (initiated, completed or no due date)** |
| UNDP support common premises mapping and analysis of existing common services | December 2023 | OMT Co-chair, DRRP and M&E Specialist |  | Not Initiated |
| Evaluation recommendation 3  Strengthen and improve the M&E system including supporting the development of a national framework for monitoring and reporting on SDGs. | | | | |
| Management response:  Agreed:  Considering the challenges of collecting and consolidating data using the excel-based template that sometimes results in errors, it is important that UNDP will support the roll out to UNINFO platform for consistency, accuracy, and ease access to UNCF data | | | | |
| Key action(s) | Completion date | Responsible unit(s) | Tracking | |
| Comments | Status (initiated, completed or no due date) |
| Support the roll out of the online UNINFO for interactive planning, monitoring, and reporting | December 2022 | DRRP, M&E specialist and RG leads |  | Initiated |
| Support UNSDCT 2023-2025 M&E framework design | December 2022 | M&E Specialist |  | Initiated |
| **Evaluation recommendation 4**  Strengthen the alignment and coordination of the UNCF Results Groups, Sector Working Groups, humanitarian clusters to avoid duplication and ensure effective utilization of resources. | | | | |
| Management response:  **Agreed:**  Accepted: UNDP will support the emphasis for better coherence, coordination and synergies for greater impact will be given in the review of the governance structure of the new UNSDCF | | | | |
| **Key action(s)** | **Completion date** | **Responsible unit(s)** | **Tracking** | |
| **Comments** | **Status (initiated, completed or no due date)** |
| Support and facilitate UNSDCF Joint program design and implementation | December 2024 | RG leads, DRRP and M&E Specialist |  | Not Initiated |
| Facilitate and support Joint field visits of Result Groups for better coordination and collaboration | December 2024 | RGs leads, M&E Specialist |  | Not Initiated |