1. **Recommendation:**

**Continue proactively enhancing collaboration with national partners and donors. The level of awareness and engagement of partners in the peacebuilding project activities should be enhanced to practical solutions. Continue building the capacity of national partners along the project implementation. Build a strong foundation for the next phase of peacebuilding programming and intervention, as well as increase the level of local ownership over the achievements of the intervention.**

**Management Response:** Recommendation accepted. UNDP will continue strengthening partnership with national stakeholders particularly with the Youth Affairs Agency of Uzbekistan in peacebuilding and PVE interventions specifically within the new PVE-2 Regional Programme in Central Asia to achieve practical solutions in prevention and legal aid issues.

**Key Actions:**

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Key Action** | **Responsible** | **Due Date** | **Status** | **Comments** | **Documents** |
| 1. Building the capacity of national authorities to set up an inclusive system of early conflict warning and response, and strengthen the institutional frameworks for peacebuilding, conflict prevention and social cohesion through thematic capacity building interventions. The national partners, including Youth Affairs Agency of Uzbekistan will be equipped with necessary skills and mechanisms for participatory planning and service provision to prevent conflicts and violent extremism in the region within the PVE-2 Regional Programme in Central Asia. | Kamila Mukhamedkhanova, EGC leader | September 30, 2023 | At designing stage |  | Draft proposal of the PVE-2 Regional Programme in Centra Asia |

1. **Recommendation:**

**Continue investing in results that have the highest possible sustainability potential, such as expanding legal clinics and youth hubs to ensure institutional sustainability.**

**Management Response:** Recommendation accepted. UNDP will continue promoting and expanding legal clinics and youth hubs in rural areas to effectively facilitate the dialogue among communities and youth on peacebuilding, conflict management and PVE issues within the new PVE-2 Regional Programme in Central Asia.

**Key Actions:**

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Key Action** | **Responsible** | **Due Date** | **Status** | **Comments** | **Documents** |
| 1. Setting up public advisory groups, legal clinics and youth hubs in rural areas to provide legal, psychological and other support services to vulnerable youth including young women and ensure sustainable dialogue among local communities and youth at the center within the PVE-2 Regional Programme in Central Asia. | Kamila Mukhamedkhanova, EGC leader | August 30, 2023 | At designing stage |  | Draft proposal of the PVE-2 Regional Programme in Centra Asia |