## Somaliland
Administrative area | Project | Location | Implementing Partner | Type of contract | TPM Reporting Period | Issues Identified | Recommendation by TPM | Status | Action plan | Time | Responsible person | Current status
Somaliland | ROL | Hargeisa | HJC | LOA | Feb | provision of very limited beneficiries contact details | HJC to keep this records and be able to provide | Raised at PPU and will be taken to program team | To share with Project/Program team |  | Roble at area level and Bushra at country level | this has been reported to the project team at area level. Issue has been shared during visit in May. In addition monitoring visit is in plan of July which will clear more.
Somaliland | ROL | Hargeisa | University of Hargeisa | LOA | Feb | Discrepancy between the targeted and actual beneficiaries as find out by the TPM | Reconcilation and explanation needed | Raised at PPU | Shared with the program team and ask the partner |  | Roble | Case resolved. UoH has been monitored and they were mixing up two lists of previous beneficiaries and current LOA once the case has been sorted
Somaliland | Cross Cutting | Hargeisa | NAFIS | MCG | Feb | Non provision of the contact details of the beneficiries | NAFIS should provide the list | M&E meet with NAFIS and demanded the list | Updated list is being waited from NAFIS |  | Roble | Resolved. Nafis provided a contact list of 90 beneficiaries and the findings will be reported in the following report
Somaliland | ROL | Hargeisa | MOJ | LOA | Feb | MOJ has trained 50 justice staff but did not provide the list | MOJ should provide this list | Raised in PPU |  |  | Roble | Resolved. MoJ agreed to provided the list and it will be included in the following monitoring plan of this month July
Somaliland | ROL | Hargeisa | MOI | LOA | March | CCORD was not permitted to monitor community policing project | UNDP to make a meeting between CCORD and police head for getting the permision and assistance to carried out | appoinemet arranged | CCORD to carry out the monitoring | May | Roble to ensure | Resolved. The issue has been addressed together by program team and M&E the monitoring took place and it will come in July report
Somaliland | ROL | Hargeisa | MOJ | LOA | April | MOJ has claimed that an activity of supportng 6 legal aid centers which is indicated in their LOA are not to be implemented by MOJ | UNDP M&E to clear the issue with the MOJ and ROL team | appoinemet arranged | UNDP M&E to clear the issue with the MOJ and ROL team | June | Roble | Resolved. UNDP M&E had cleared this monitoring visit together with CCORD and the BTOR has been shared
Somaliland | ROL | Hargeisa | HGH | LOA | April | HGH is providing less verification in their activites | UNDP M&E to carry out a verification monitoring visit to the HGH | appoinemet arranged | UNDP M&E to carry out a verification monitoring visit to the HGH | June | Roble | Pending. This has been planned to take place in June but do you to absence of senior officer and Ramadan it was postponed to July
Somaliland | ROL | Hargeisa | MOI | LOA | March | CCORD was not permitted to monitor community policing project | UNDP to make a meeting between CCORD and police head for getting the permision and assistance to carried out | Issue resolved | CCORD to carry out the monitoring | May | Roble to ensure | This has been granted the monitoring of Community policing took place in June
Somaliland | ROL | Hargeisa | MOJ | LOA | April | MOJ has claimed that an activity of supportng 6 legal aid centers which is indicated in their LOA are not to be implemented by MOJ | UNDP M&E to clear the issue with the MOJ and ROL team | appoinemet arranged | UNDP M&E to clear the issue with the MOJ and ROL team | June | Roble | this has been cleared in moniroting by Roble and details are available at the BTOR
Somaliland | Environment | Hargeisa | MOERD | LOA | May | • The 10 solar systems that were supposed to be for women to use with water pumps ended up being installed in to provide electricity in Ina Sanweyne Secondary and Boarding School in Balidhig. • 8 solar panels installed in Inasanweyne Boarding Secondary school and two are missing without any explanation • The fodder seeds that were promised by the Ministry after their training have not been delivered yet the project ended • The project was to plant 5000 acacia trees in Qoryale, but due to what the people Qoyale intimate as politics, the location was changed to Hankidiile. • Only 4000 acacia trees were planted and the remaining 1000 trees have not yet been planted yet the project has ended | None | issue identified in Track sheet | 1. Solar system and trees location was chaned after community consultations. 2. Abdi Yusuf to follow up with the project partners on remaining issues and Roble to ensure follow up. | July | Abdi Yusuf | The Ministry has provided a detailed response and adequate justification for the changes made.
Somaliland | PREP | Hargeisa | MOERD | LOA | May | No evidence was provided to CCORD on the round table discussion on NRM | Follow up by CCORD and M&E on the issue | issue identified in Track sheet | Project to follow up | July | Project staff
Somaliland | PREP | Hargeisa | MOERD | LOA | May | CCORD was agreed to provide case studies from PREP support and it has not been captured in the report | To follow up with CCORD the provision of the case studies | Roble have discussed and shared this CCORD | Project to follow up | July | Project staff | CCORD provided some beneficiary testimony
Somaliland | GROL | Hargeisa | MOJ | LOA | May | CCORD identifies 50 staff training noted in the LOA was not carried out by the ministry | Meeting between CCORD, UNDP M&E and MOJ senior staff | Done | MOJ cleared the case | July | Roble | The issue has been addressed and the trainees were typo error in the LOA but not include in the Budget and other result frameworks
Somaliland | GROL | Hargeisa | HOR | LOA | Aug | The parliament offices are open but not functioning to the standard supposed and not creating solid linkage between citizens and MPs | Project team to address certain challenges include awareness and location of the offices | Roble shared with the Program team | follow Up | Oct | Program and M&E teams | Project has received the findings and working on it.
Somaliland | PREP | Hargeisa | HAVAYOCO | LOA | AUg | some of the infrustructures built for Togdher community under HAVOYOCO MCG are not working | The partner to take the responsibility of the defects and repair | the partner is shared with the defects | Follow up | oct | porgram team | Project is engaging on this with partner.
Somaliland | GROL | Hargeisa | HGH | LAO | July | the registerars in HGH reveal different than the reports, reports aim to just match the targets | revision of the targers and register improvements | reported | program team revised the targets for the coming LOAs | Done | Roble | Project is engaging on this with partner.

## Puntland
Administrative area | Project | Date | Implementing Partner | Type of contract | TPM Reporting Period | Issues Identified | Recommendation by TPM | Project Response | Status | Responsible Person
Garowe | ROL | 2016-02-01 | Police/ MOSD |  | 2016-02-16 | It was not possible to get the telephone contacts of the beneficiaries accessing services from the police station due to the sensitive nature of the matter. |  | House addresses are not commonly used by the society. Mostly service seekers are accompaned by a close relatives familiar in the area whose contacts are recorded. working with AGO,PHRD, PLAC to keep record for references and joint monitoring is in plan. | Pending. Recommended to establish anonymous call back centre for Legal Aid & police project beneficiaries recipients. UNDP PPU and ROL staff to work with TPM to develop SOP on interviewee confidentiality. UNDP and ROL staff to look at options for call back mechanisms. | Ali Farah in Puntland to ensure that the MoS shares list of beneficiaries; Ruth and Abdullahi to work on confidentiality issue of the interviewees with the TPM. PPU to facilitate.
Garowe | ROL | Feb | Police/ MOSD |  | 2016-02-16 | Also it was not possible to get contacts of the police officers that underwent the training, CCORD therefore requested for a meeting with police officers who participated in the Armo training 2015. |  | list of trainees is available in the office,TPM can find the list of the trainees if requested | Pending. UNDP staff to work with ROL partners to ensure that all trainees are well documented/ demographic Infor collected and traceable. | Ali Farah
Garowe | ROL | Feb | Police/ MOSD |  | 2016-02-16 | Though the training went well, time was too short to change the mentality of police officers who are also poorly remunerated (poor salaries). As well, the training equipment is inadequate. |  | establishing a mobile training unit is in plan. The unit will reach out to a number of stations and prodive on job training on policing and managing police station | Progress ongoing New LOA is being drafted. UNDP ROL staff to ensure that all trainings are designed and organized on a needs base with follow-up mechanisms for re-training are in place. | Ali Farah
Garowe | ROL | Feb | Police/ MOSD |  | 2016-02-16 | Recommendations by police officers. The following were key issue raised by the group as recommendation  Increases number and duration of trainings  Provision of adequate salaries  Providing modern equipments for the training |  | B. Salary is the prerogative of the State Government | Progress ongoing new LOA is being drafted. UNDP ROL staff to ensure that all trainings are designed and organized on a needs base with follow-up mechanisms for re-training are in place. A. Skills and educational background of the trainees help designing durable training plan. Secondly, properly graded and classified officers is essential as well . These characteristics are not adapted in police organisation. conclusion of the ongoing biometric registration will enable fair selection of trainees fitting nature and duration of training. . C. Equipment will be technically managed properly by selected and trained officers inasset management. | Ali Farah
Garowe | ROL | 2016-02-01 | ADR/ MOJRAR |  | 2016-02-16 |  The system of following up of inmates and detained persons is weak and has always resulted in prolonged and arbitrary detention of the inmates  Elders and Sheikhs need more capacity building on GBV and human rights standards.  MOJRAR DG mentioned that assets are given to private NGOs like PLAC and yet they public assets. These assets in some circumstances end up getting lost and cannot be accounted for  There is a high variance at the ADR house i.e. out of the 3000 cases received by elders only 1443 have been attended to which is less than half . The project staff interviewed attributed the high variance to the reduction of staff at the CDR houses and staff turn-over which needs to be addressed by UNDP and MOJRAR. |  There is a need to establish a database system whereby the information on inmates and detainees can be tracked.  There is a need for the establishment of asset management committee led by the ministry.  There is also the need to conduct a harmonization of the three legal systems in Puntland. |  | Progress. The prison database is developed by UNODC. This matter has been raised with the Minister MOJRAR and written information sent to them. PLAC is an ongoing partner of UNDP and the assets are being used. The ADR system is separate to that of the formal courts and this should be kept separate. The Rule of Law project has taken up the issue of harmonisation of the case management system with the Chief Justice of HJC and Minister MOJRAR to establish case management system. This will be followed up with the sharing of the case management TOR. | Hawo, Zafar, Doel
Garowe | ROL | 2015-11-01 | MOJRAR |  | 2015-11-01 |  According to ADR Elders in Bossaso, they have constructed one part of the compound of the house and need UNDP assistance to construct for them the other side of the compound in order to deter dumping of solid wastes around the house thus ensuring conductive environment of the house. |  |  | ROL staff to bring to the attention of the MOJRARA to ensure quality control standards and sanitation of the ARD centres. An email has been sent to the MOJRAR | Hawo,Doel
Garowe | ROL | 2015-11-01 | MOJRAR |  | 2015-11-01 | They told us that they have not received training recently and they need training on dispute resolution mechanisms. |  |  | Resolved. Trainings were held in 2015: (a)sharia and customary law; (b) functioning and mandate of formal and informal justice system (all the traditional elders , judges and prosecutors participated together) (c) legal awareness training for elders only. UNDP ROL staff to ensure that that there is a strategy and comprehensive training programme in place for all justice actors, and that they are part of the consultation in it's development. | Hawo
Garowe | ROL | 2015-11-01 | MOJRAR |  | 2015-11-01 |  In Bossaso the project officer, told us that UNDP suppliers brought incomplete furniture, up-to now they don’t utilize the cupboard and one executive chair since some essential parts are missing. In Garowe, they had brought one set of computer and another incomplete set of computer i.e, only CPU without the monitor. |  | The MOJ directly procured those items for CDR houses. | Pending. UNDP staff to undertake needs assessment of the ADR centre and follow-up on assets, financial resources allocated,to the centres. Also this needs assessment should be used to identify the funding provisions in LOA MOJRAR and UNDP extension from July to Dec 2016 | Hamdi to undertake needs assessment; Hawo to provide inputs to the LOA
Garowe | ROL | 2015-11-01 | MOJRAR |  | 2015-11-01 |  MoJRAR project management team told us that previous UNDP‘s ADR Project officer did not consult with ministry before bringing some of the operational equipment like  The facilities have few chairs; each facility had 20 chairs with the exception of Bossaso ADR House, which had only fifteen chairs. There is a shortage of chairs when settling more than two (2) cases especially family and inter-clan disputes. They also informed CCORD field team that they need one hundred (100) chairs. Although the ministry had bought 15 plastic chair for Garowe ADR house. |  |  | Pending. UNDP staff to undertake needs assessment of the ADR centre and follow-up on assets, financial resources allocated,to the centres. Also this needs assessment should be used to identify the funding provisions in LOA MOJRAR and UNDP extension from July to Dec 2016 | Hamdi to undertake needs assessment; Hawo to provide inputs to the LOA
Garowe | ROL | 2015-11-01 | MOJRAR |  | 2015-11-01 |  The funds allocated for refreshment is limited due to rate of inflation in Somalia which is high.  All the Facilities lack running water tap with exception of Garowe ADR House and this makes basic sanitation a problem since the toilet don’t have running water which could result in furniture, computers and printers. |  |  | Pending. UNDP staff to undertake needs assessment of the ADR centre and follow-up on assets, financial resources allocated,to the centres. Also this needs assessment should be used to identify the funding provisions in LOA MOJRAR and UNDP extension from July to Dec 2016 | Hamdi to undertake needs assessment; Hawo to provide inputs to the LOA
PUNTLAND | ROL | 2015-11-01 | MOJRAR |  | 2015-11-01 |  There was delay in the disbursement of funds which subsequently delayed the implementation of activities and MoJRAR do not have contingency fund in place to facilitate the implementation of activities like hiring of national consultant, holding consultation meeting/workshop. However, MoJRAR can still carry out other activities such as field monitoring and draft legal policy while waiting for the disbursement of fund. | Disbursing the fund at the right moment, will ensure proper planning, implementation and execution of project effectively |  | Resolved. There was HACT assessment, and there was anew payment modalities which HACT team recommended like direct payment which needs allot of processes before releasing the budget so that caused some delays in the past , but now the process in normal | Hamdi, Ruth, Ifrah
PUNTLAND | ROL | 2015-11-01 | MOJRAR |  | 2015-11-01 | DG told us that, for the last five months, the project staff does not receive their salaries resulting in low morale of the staff. The ministry submitted the narrative and financial report and approved other pending signatures at the moment | Disbursing the fund at the right moment, will ease the problem in the near future. | We aren't aware the staff who were waiting a salary for 5 months, once we receive their financial report and request we process it, the ROL project staff will need to seek more clarification. | Resolved | Hamdi, Ifrah, Ruth
PUNTLAND | ROL | 2015-11-01 | MOJRAR |  | 2015-11-01 | According to the DG, most of the office equipment that UNDP provided to MoJRAR at the inception of the ministry are all malfunctioning. The DG stated he uses his personal laptop. As well, the ministry does not have funds to hire IT officer in addition to allocating funds for the repair and maintenance of operational equipment like computers. | Support / Hire an Information Technology /IT security officer for the MoJRAR |  | Pending: some new assets have been requested. The issue will be resolved in the extension of LOA MOJRAR and UNDP: | Hawo to provide inputs into LOA
PUNTLAND | ROL | 2015-11-01 | MOJRAR |  |  | Since it is inception, the ministry staff had increased; the office space for our staff is getting smaller and smaller. Lack of office space made our work difficulty. | Partitioning the offices will create more space as well as ease the working condition of staffs |  | Resolved. This has been raised many times from MOJ management, but as per ROL project UNDP is not the leading agency for any construction. MOJRAR needs to raise this with UNOPS | Programme Secretariat
PUNTLAND | ROL | 2016-02-01 | MOJRAR |  | 2016-02-01 | The target was to reach 1800 citizens to receive legal aid or counseling, but only had reached 1146 beneficiaries. No explanations have been provided for the variance and UNDP is encouraged to follow UNDP should follow up. | To continue supporting the project since the University of Hargeisa does not have the capacity to continue funding the project activities. Increase staff morale by arranging capacity building training related to their work outside the country for them to gain practical experiences relating to their work. Improve and arrange coordination systems and networking for justice actors. UNDP to keep supporting and funding the Justice and Correction projects since it significantly benefits the communities members who do not have access to justice and cannot afford to hire lawyers UNDP to encourage partners to improve on record keeping and prepare beneficiary list with gender disaggregated data and confirm phone number for easy follow-ups. |  |  | Ali Farah
Garowe | ROL | 2015-12-01 | PSU -Legal Aid Clinic |  | 2015-12-01 | Paralegals and lawyer usually face challenges of transport during their weekly visits to several and different IDP Camps and Prisons. | Clinic rents vehicle for facilitation of the activities. |  | Resolved. UNDP is already supporting rented vehicle | Hamdi
Garowe | ROL | 2015-12-01 | PSU -Legal Aid Clinic |  | 2015-12-01 | Only one lawyer at Clinic: There are several cases in different levels of court. |  Clinical students and paralegals assist to prepare and draft the required documents.  There is need to hire another lawyer so as to reduce burden of case file |  | Resolved. UNDP with PSU has agreed with the partners that one lawyer is not enough, however due to the limitation of funding, this will have to be considered for future plans. | ROL project management
Garowe | ROL | 2015-12-01 | PSU -Legal Aid Clinic |  | 2015-12-01 |  Non- payment of judiciary staff hindered the speed of trials.  Poor case management in the court and in the police station.  Lack of qualified Criminal investigators |  We have shared this concern with clinical oversight and president of Nugal Regional court to take an appropriate action.  The need to train the police office on how to handle/draft case management.  There is need to train criminal investigators/detective |  | Progress ongoing: UNDP does not pay for judicial staff. Case management harmonised corodination through case management committee would be important and this discussion has been initiated with the HJC and MoJRAR. | Zafar
Garowe | ROL | 2015-12-01 | PSU -Legal Aid Clinic |  | 2015-12-01 |  Shortage of legal experts in the clinic. | We invite some legal experts to deliver guest lecture |  | Pending: UNDP and PSU to consider attaching pro bono lawyers to the law clinics | Hawo, Zafar
Garowe | ROL | 2015-12-01 | PSU -Legal Aid Clinic |  | 2015-12-01 | There was an Error in the budget line r head Legal Awareness Sessions: 5.1: | We have submitted the request to UNDP for amendments. |  | Resolved. UNDP Staff re-checked the budget in LOA NCE in June 2016 | Hawo, Ruth
Garowe | ROL | 2015-12-02 | PSU -Legal Aid Clinic |  | 2015-12-01 |  Support of scholarship and Internship program for 3 and 4 year law students was stopped | FOR PARTNER • Invite/hire technical advisor from the Diaspora, so that PSU legal aid clinic addresses the shortage of legal experts at the clinic and technical advisor from the Diaspora offer sustainable solution to this problem. • Continue to support the internship program for the 3&4th year students • PSU should provide fellowship program for the detective/private detective so that the issue of shortage of criminal investigators is fully addressed. • There is need to train the police officers/court registers on how to handle/draft case management so as to avoid poor case management and better documentation system.. • Joint performance evaluation with ministry of justice and UNDP will enable them to enhance accountability and transparency of the program they implement. FOR UNDP • Recruiting another lawyer especially a female lawyer. • Continuing support of internship program to increase the number of lawyers • Establishment of gender unit at Legal Aid Clinic. • Continuing of scholarship program for female and those who could not afford to pay the tuition fee especially girls from poor background • Capacity building for clinical staff on Human right, Criminal law, Rule of law, project management and financial and bbudgeting • Need for the expansion of legal Aid Clinic • Attaching expatriate legal educationist who has a civil law background to legal aid clinic and law faculty providing specialized legal trainings to law professors and students • Providing at least one vehicle for legal aid clinic to improve legal aid services and conduct legal awareness • Establishment of Human Rights Component • The need to train the police officer on how to handle/draft case management |  | Resolved. At the moment there is no support for new scholarships in 2015, but the project supporting continuance students whom already on board to see through they complete the programme. UNDP to integrate each recommendation into future programming, given availability of funding | Project management and Hawo; the recommendations are dependent on further funding
SOMALILAND | ROL | 2015-12-01 | Buroa Regional Hospital – Baahikoob Center |  |  | CCORD has only analysed reports and oral information | The project was successful according to the progress report made in sixth months, thus there is need to renew the project so that to enhanced with focus on women’s access to justice. |  |  | Ali Farah
SOMALILAND | ROL | 2015-12-01 | Buroa Regional Hospital – Baahikoob Center |  |  | CCORD was not able to interview target beneficiaries due to cultural and social issue barriers. | If there is voluntary beneficiary that can volunteer to provide information to the monitoring parts should be contacted in the future so that they can be contacted by the monitoring team. |  |  | Ali Farah
PUNTLAND | ROL | 2016-01-01 | HJC -GAROWE |  | Jan |  Lack of enforcement of the decisions taken by the courts  Involvement of civilian army  Lack of proper compensation to the law enforcement officers  Tribal conflicts  Poor charge execution  Lack of community policing  Inaccessibility of some villages |  Consistent salary payment to the police  Disbarment of the civilian army  Established court building in districts and police stations  Rehabilitation of the police station as a good building qualifies police in terms of education, trainings and dress. |  | Resolved. Payment of police salaries and constuction of police stations are now the tasks of the UNOPS under the JROLP | Programme Secretariat
PUNTLAND | ROL | 2016-01-01 | HJC -GAROWE |  | Jan | Beneficiary contact details not available | It is important UNDP follows up with HJC about the missing telephone contacts from the beneficiary list leading to a very low number that was interviewed. HJC should speed up implementation of the remaining 3 districts and identify villages that are accessible in order to provide training, technical assistance, and infrastructure to key justice institutions in those villages. As well, HJC should identify innovative ways of reaching out to the targeted number with the activities and awareness sessions as per the workplan so that the people targeted turn for the events. |  | Pending. Recommended to establish anonymous call back centre for Legal Aid & police project beneficiaries recipients. UNDP PPU and ROL staff to work with TPM to develop SOP on interviewee confidentiality. UNDP and ROL staff to look at options for call back mechanisms. | Ali Farah in Puntland to ensure that the MoS shares list of beneficiaries; Ruth and Abdullahi to work on confidentiality issue of the interviewees with the TPM. PPU to facilitate.
Garowe and Galkacyo | Gender | 2016-02-01 | African Women Foundation (FAWESOM) |  | Feb | Delay in the release of funds by UNDP |  |  | Final installment of funds disbursed | Kareema Hassan
Garowe and Galkacyo | Gender | 2016-02-01 | African Women Foundation (FAWESOM) |  | Feb | Lack of computer and poor communication services including internet | Purchase laptops |  | Still pending | Kareema Hassan
Garowe and Galkacyo | Gender | 2016-02-01 | African Women Foundation (FAWESOM) |  | Feb | Not enough funds for writing thesis and certificates | Provide funds for thesis and certificates i.e. 170usd |  | Still pending | Kareema Hassan
PUNTLAND | ROL | 2016-02-01 | Puntland Police |  | Feb | Though the training went well, time was too short to change the mentality of police officers | Increase the number and duration of trainings |  | Resolved. Along with the Mobile Training Unit, Internal and External oversight trainingis in planned for 2016. New LOA is being developed | Ali Farah
PUNTLAND | ROL | 2016-02-01 | Puntland Police |  | Feb | The training equipment is inadequate | Provide modern equipments for the training |  | Resolved. MOIS, EU, EUCAP-NESTOR are in discussion to finalise the shipment of equipment from Djbouti to Mogadishu and the distribution of these equipments are based on Heegan Plan | Project Management
Garowe and Nugal | ROL | 2016-02-01 | Ministry of Justice, religious and rehabilitation |  | Feb | The system of following up of inmates and detained persons is weak and has always resulted in prolonged and arbitrary detention of the inmates | There is a need to establish a database system whereby the information on inmates and detainees can be tracked. |  | Progress. The prison database is developed by UNODC. This matter has been raised with the Minister MOJRAR and written information sent to them. | Hawo, Zafar, Doel
Garowe and Nugal | ROL |  | Ministry of Justice, religious and rehabilitation |  | Feb | There is a high variance at the ADR house i.e. out of the 3000 cases received by elders only 1443 have been attended to which is less than half . The project staff interviewed attributed the high variance to the reduction of staff at the CDR houses and staff turn-over | This needs to be addressed by UNDP and MOJRAR. |  | Progress. The prison database is developed by UNODC. This matter has been raised with the Minister MOJRAR and written information sent to them. | Hawo, Zafar, Doel
Garowe and Nugal | ROL | 42401 | Ministry of Justice, religious and rehabilitation |  | Feb | MOJRAR DG mentioned that assets are given to private NGOs like PLAC and yet they public assets. These assets in some circumstances end up getting lost and cannot be accounted for | There is a need for the establishment of asset management committee led by the ministry |  | UNDP has their own Procurement procedures and we handed over this asset to the independent NGO called PLAC so there is nothing to do with the ministry, it is UNDP responsibility to Audit that NGO | Awil Abdinoor
Garowe and Nugal | ROL | 42401 | Ministry of Justice, religious and rehabilitation |  | Feb | Elders and sheikhs have limited knowlage and capacity related to GBV and human rights standards | Elders and Sheikhs need more capacity building on GBV and human rights standards |  | We included the GBV and human rights standards training for the next extension of their LOA starting form Sep-Dec-2016, so the elders will receive more capacity building | Awil Abdinoor
Garowe | SIP | 2016-03-16 | Ministry of Planning, Cooperation and International Relations |  | Mar | The recruitment process of the advisors to the ministry is undertaken jointly between UNDP and the ministry, unlike international consultant that is solely recruited by UNDP which caused delay in the process. | No recommendation from TPM | Recruitment was completed in April and the consultant commenced the work by May 13, 2016. | Resolved. | Musa Duale
Dangoroye, Qardho and Benderbayla | CCR | 2016-04-16 | Ministry of Wildlife and Tourism |  | Apr | The Ministry developed the climate change and drought | UNDP to approve the document | Climate Change and drought Management strategy have been drafted by the Ministry but the consultations workshop to validate the document has not been conducted by the Ministry . | Resolved. Next round of the LoA was planned to undertake this activity | Awil Abdinoor
Garowe | SIP | 2016-06-16 | Ministry of Women Development and Family Affairs |  | June - 2016 | Delays in the recruitment of consultants led to delays in the implementation of activities | UNDP to fast track on the recruitment of the Consultants so as to complete the implementation process

## South Central
Administrative area | Project | Location | Implementing Partner | Type of contract | TPM/PPU Reporting Period | Issues Identified | Recommendation by TPM/PPU | Status | Action plan | Time | Responsible person
FGS | RoL | Mogadishu | Association of Somali Women Lawyers | McG | June - July, 2015 | There fear factor in most of the beneficiaries called especially the legal Aid ones on grounds of security and suspicion that they are being followed up. most of ASWL beneficiaries were very suspicious to ask legal aid as they are affraiding to be followed-up. | No recommendation from TPM | to discuss with the proejct team
FGS/ISWA | Gender Project | Afgoi & Dolow | AAAWDO & HDC | McGs | Sept.2015 | The beneficiaries were satisfied with the project, however, would like more training and awareness campaigns on behavior change | More behaviorail change training should be provided tp CCEs beneficiaries in Afgoi and Dolow | to discuss with GEWE team
IJA | Local Economic Development | Luuq | CERID | McG | Sept.2015 | Beneficiaries had not been paid their wages despite have completed their work. The partner has not attempted to explain the circumstances of the delay hence creating disillusionment among the beneficiaries | Partner to should strengthen its monitoring mechanism to ensure issues are addressed as early as they emerge especially issues directly affecting the beneficiaries. | Beneficiaries had been paid their paid their wages | Direct payment to the beneficiaries | 2015-10-01 | LED Project Staff
IJA | Local Economic Development | Luuq | CERID | McG | Nov.2015 | Beneficiaries requested feeder roads rehabilitation, flood protection measures, provision of seeds that may include maize, sesame, and watermelon | No recommendation from TPM | to discuss with GEWE team
FGS | Clean-up Project | Mogadishu | BRADO (LNGO) | McG | Nov.2015 | The number of unanswered calls participated clean-up project was a concern for CCORD | Need to be addressed by UNDP | Pending
FGS | Justice and corrections | Mogadishu | The Attorney General | LoA | Dec.2015 | Not identified | NA
FGS | Justice and corrections | Mogadishu | The Supreme Court | LoA | Dec.2015 | Not identified | NA
FGS | Mogadishu Clean Up Project Hodan District (Short Term-Employment ) | Mogadishu | BRADO (LNGO) | McG | Dec.2015 | 199 out of 333 beneficiaries interviewed | The number of unanswered calls was a concern for CCORD and needs to be addressed by UNDP | Pending
GA | Alternative Livelihood to Piracy Phase 3 – Social Mobilization | Luuq | HOPEL | McG | Dec.2015 | Not identified | NA
FGS | Alternative Livelihood to Piracy Project | Mogadishu | Minstry of Labour | LoA | Dec.2015 | CCORD was not permitted to monitor this project by the ministry even after providing all the necessary documentation from UNDP | PREP team should facilitate the monitoring of Ministry of Labour by TPM | Pending
| Mogadishu Clean Up Project Yaaqashiid District District (Short Term-Employment ) | Mogadishu | BRADO (LNGO) | McG | 2016-01-01 | Not identified | NA
| Rule of Law - Justice and Correction | Mogadishu | The Supreme Court | LoA | 2016-01-01 | Graduate Interns Recruitment for Supreme Court - was supposed to interview 12 graduate interns’ candidates to be based at the supreme court. One Out of the 12 candidates was female and other 11 were male. However . the female candidate didn’t attend the interview. Therefore, there was need to re-advertise for graduate interns with special attention given to women candidates | Project team to follow-up | Pending
| Rule of Law - Justice and Correction | Mogadishu | The Office of Attorney General | LoA | 2016-01-16 | Not identified | NA
| Gender Project | Dolow and Belet-hawa | HDC | McG | 2016-01-16 | 5% of the male respondents from Dollow said they had some complaints about the CCE providers, while 8% of the female respondents from Dhollow said they had some complaints about the CCE providers. | Project to follow-up | Pending
JA | Local Economic Development | Luuq | CERID | McG | 2016-01-16 | Short term project. Pests control and deficient of nutrients for the farming productivity. Inaccessibility to the market. | Continuation of the support to the farmers living in Luuq. Provision of Integrated pest management and manure compost production training. rehabilitation of feeder roads before the harvesting of the crops in Luuq District in order to improve on transportation of the food products to the market. | Pending |  | 2016-02-01
Hiiran Region | Environment Project | Hawaadley village | GSA - Hawaadley | Contract | 2016-02-16 | • Community Conflict over water resources due to its scarcity • Poor construction of the existing canals • Common disaster affected environmental areas | • To rehabilitate Killi-adde canal which irrigates wide range of farms in Hawaadley • Drilling of one borehole and rehabilitation of 2 shallow wells • Request for total replacement of the sluice-gates (advised by the project engineer met with CCORD M&E) • Recommend culverts of the Killi -Adde canal to be rehabilitated to facilitate transport means • Re-construction of the Hawaadley village main road entrance which is totally destroyed | Pending |  | 2016-04-01 | PM
Lower Shabeele Region | Environment Project | Bula Ahmed Igow | GSA - BulaAhmed IGOW | Contract | 2016-02-16 | • Women fear the attack of the crocodile in the river while fetching drinking water from the river • Women usually plant vegetables and the canals are used as sources of water. And so without the canals to irrigate the farms they may not harvest. • The need for improving access to safe drinking water for households and therefore the need to for drilling of additional wells. • Inadequate river embarkment which affects the vegetable planted by women and subsequently affecting household income. | • Rehabilitate Nolol canal which is essential for irrigation and flood protection for the farming area. • GSA to sustain and consistently provide the capacity building training on the climate resilience to our vulnerable community; • Improve the river embankment to avoid river flooding | Pending |  | 2015-04-01 | PM
Lower Shabeele Region | Environment Project | Jawhar | GSA - Kafunji Village | Contract | 2016-02-01 | • Regular disaster water environment • Poor hygiene and water sanitation • Poor construction of canals | • Rehabilitate the canal assessed for Kafunji community reconstruct sluice-gates for protection of the floods into the Kafunji yards/farms • Rehabilitate or reconstruct culverts on the canal onto the main road of Jowhar which is important means for communication and transportation • Rehabilitate water catchment before rains come • Plan for capacity enhancement refresher course on the disaster management and climate resilience for Kafunji community. | Pending |  | 2016-04-01 | PM
ISWA and Jawhar Region | Environment Project | Jowhar & Afgoi | GSA - Bareer | Contract | 2016-02-01 | Only Two (Jowhar &Afgoye) districts have been Monitored. • The community has not fully responded to the causes of the floods; by maintaining sluice-gates • The River embankment to avoid river cracks or tears has been a challenge to achieve • Poor sanitation and hygiene in the community water village • Declining amount of water found in the shallow wells. • Increased conflict over water resources • Lack of clean water for drinking • Limited access to clean drinking water due to poor infiltration • Increased water prices • Increased water – related conflicts • Increased demand for borehole water | The remaining two districts(Balanbale and Guriel) will be monitored in month of March/201. • To increase the number capacity buildings trainings for community on climate resilience for adaptation • The canal rehabilitation - there is triangle of the canal where the community needs assistance in order to repair the sluice-gates; • In order to improve sanitation and hygiene practices in the village availability of water is essential and improve access to latrines • The need for river enbankment rehabilitation. • Baareey community requested for GSA to drill a borehole well for supplying clean drinking water to the village | Pending | To discuss with Environment proejct | 2016-04-01 | PM
FGS | GEWE | Mogadishu | AAWDO | MCG | 2016-02-01 | Sampling for beneficiaries of AAWDO project: • 5 beneficiary numbers were switched off, • 6 were wrong number provided by the beneficiaries. • 1 beneficiary contact information was incorrect numbers, | No recommendation from TPM | GEWE Project informed. | Strong follow-up by GEWE Project team | 2016-04-01 | Leila
FGS | Judicaiary and Correction (ROL) | Mogadishu | Suprteme Court | LoA | 2016-02-16 | There is no case so far that has been adjudicated in the mobile court and formally the regional court submits the cases to the supreme court. Mr Mursal stated that they are waiting for the regional court to submit the cases which in the coming two weeks around the end of February. vacant of 10 legal graduate interns. Out of ten(10) the supreme court has so far recruited five(5) and the remaining five(5) interns positions are being advertised this week through national TV and Radio Mogadishu. | CCORD will monitor this output regarding the 800 cases by march, 2016. CCORD will report the status of the remaining five legal intern graduates by march, 2016. | not updated | Judiciary Project to follow-up | 2016-04-01 | PM
GA | PREP | Balanbale & Guricel | General Services Agency (GSA) | Contract | March, 2016 | Training for the CBOs was undertaken to ensure community participation in design, implementation and monitoring of the activities but data, location of the training and number of beneficiaries should cleared. | Project to follow up | Pending | missing information is expected from CCORD to capture | May | Mohamed should enagge CCORD to capture those important information
FGS | GEWE Project | Mogadishu (Hodan and Hamarweyne) | AAWDO | McG | March, 2016 | Over the last 11 months, AAWDO has conducted 19 sessions but yet not cleared number of beneficiaries attaended Gender HIV sessions | Project to follow up | Pending | missing information is expected from CCORD to capture | May | Mohamed should enagge CCORD to capture those important infornation
GA | State Formation Project | Adaado | Ministry of Interior and Federal Affairs (MOIFA) | LoA | March, 2016 | Based upon the data given, it appears that the workshop did not increase the majority of participants’ understanding of approaches to effective internal and external communication and coordination. Thus, What are the resons that 92% of the participants did not significantly benefit from the communication and coordination workshop held in Adaado March 14-15 2016 . | Project to undertake regular post-workshop feedback and make recommendations to improve workshops. | Pending | Project team to respond | May | STEFS project
ISWA | State Formation Project | Merka | MoI | LoA | June, 2016 | • Lack of trust on the government evidenced by participant’s remarks • Limited participation of women leaders in the peace building and reconciliation activities • Lack of functional authority in Merka District • Limited number of police officers to maintain security in Merka District • Closure of markets because of insecurity caused by Militias | • It is important that government to win back the trust of the people through confidence building activities that will strengthen the capacity of the established committees in Merka District. • Government to increase women participation in peace building and reconciliation efforts • The government to implement functional local authority/administration in Merka District and support appointed local administration • The government to deploy 200 police from South-west State to maintain and support security and justice institutions such as of Police station, Merka Court, district prison • The government to continue with Militia disarmament, demobilization and their reintegration into the police force | Pending | Project team to respond | Sept | STEFS project
|  | Kismayo | Minstry of religious Affairs | LoA | June, 2016 | • By the time of monitoring, most of the activities had not been fully implemented • During the monitoring period, there was a handover process going on for the new Minister for Justice, Constitution and Religious Affairs and this delayed the monitoring for two days • Other challenges were to do with the Interns complaining of transport problems, delays in salaries and stipends, laptops for work in the field with Mobile Courts and general security issues | • CCORD anticipates monitoring MoJ again in September 2016 to verify if all the activities that are pending have been implemented • Salaries for the Interns should be released in good time to facilitate their movement and upkeep • UNDP to fast track on the procurement of the 3 vehicles, 11 computers and 7 Printers to support the performance of the judiciary and justice institutions of the MoJ-mandate in Jubbaland state | the implentation of the activities started | CCORD to carry out follow-up monitoring in Q3 | Sept | Project staff
ISWA | Judicaiary and Correction (ROL) | Baidao | Minstry of Justice | LoA | June, 2016 | • Lack of adequate office spaces at the Ministry of Justice • Delay in provision of technical advisors by UNDP to support priority units of the MoJ • Delay in salaries and stipends for the Interns • Delay in procurement of 3 vehicles, 11 Computers, 7 Printers and any other infrastructure in the LoA to support the performance of the judiciary and justice institutions of the MoJ-mandate in ISWA | • MoJ to seek support for more offices • UNDP to fast track on the hiring of the technical advisors • • Salaries and stipends to the Interns should be processed in goodin good time to facilitate their movement and upkeep • • UNDP in their agreement with MoJwith MoJ-ISWA should finalize thefinalize the procurement of 3of 3 vehicles, 11vehicles, 11 Computers, 7 Printers and any other infrastructure in the LoA to support the performance of the judiciary and justice institutions of the MoJ-mandate in ISWA | Project to respond | CCORD should carry out follow-up monitoring | Sept | Proejct Team
FGS | State Formation Project | Mogadishu | Boundary and Federalism Commission | LoA | May, 2016 | • Mandate of the BFC • Feedback mechanism to the community • BFC representation • Policy framework for demarcation of the boundaries • Social Media of the BFC • Cartographers experts for boundari | • BFC should continue engaging the public, federal state members, regional state authorities and all actors to be able to move their mandate further • BFC should develop content with feedback mechanism on their work that should be discussed through media channels- this will make the get views from the people • Form a taskforce consisting of federal state members, regional/district authorities, civil societies and the national government key relevant line ministries- spearheaded by MOIFA- (Modalities will be to ironed out in SOCSENSE meeting ASAP) • Engage the federal state authorities on any policy/framework on delimitation and demarcation process they have developed or laws therein • Develop an interactive website as soon as possible – This will engage the public through discussion and act as feedback mechanism through the BFC portal • Commence social media movement through the secretariat in discussing the matters of federalism and boundaries for the Diaspora and far-flung communities- Internet is available throughout Somalia • Commence immediately collating all Somalia Maps- work with former military cartographers and engage donor communities to assist in the process | Project to respond | BFC | June, July, August | BFC
FGC | SIP | Mogadishu | A | LoA | April, 2016 | • Financial challenge • The second main challenge facing the Aid Coordination Unit is related to the second expected output of the project (Facilitation of engagement of regions in Compact implementation), which has seen cancellations and delays of meetings due to security problems and political instability • Possibility of staff turnover - The SIP project supports the core government ministries with salaries for local Advisors on short term basis of about three to six months. In an environment like Somalia where qualified human resources are scarce, the staff members have the potential to be absorbed by other institutions | The CD-SIP support is expected to continue until the end of 2017. However, the budget allocations within the CD-SIP project are insufficient to continue financing the ACU in its present form. While some re-allocation and reconfiguring of duties within ACU and the MOPIC may help to reduce costs, additional resource mobilization will be required to ensure full functionality of the Aid Coordination Unit. | Pending | Project to update | May | CD - SIP Project Team
FGS | SIP | Mogadishu | MoPIC | LoA | April, 2016 | • The ICT department of MoPIC, despite the interventions that have been supported by UNDP is still faced by a myriad of challenges that include poor communication flow within the departments, inadequate space to operate from for Technical Advisors, transportation issues, inadequate ICT equipment, and insecurity • The department of International Cooperation cited lack of information flow within the department and other departments within the Ministry as slowing implementation of programs | • There is need to continue providing training and modern equipment to the ICT department staff so as to improve their capacity to deliver services Creation of office for the Advisors A functional Communication policy and procedures should be put in place within the department in order to strengthen correspondence and information flow There is also an urgent need to create office spaces for the Technical Advisors as well an increase in budget to finance operation for the department. On job training for the staff should be continuous including interdepartmental coordination on the use of ICT to improve on efficiency • There is need for more support to build the institutional capacities of the working groups in order for them to prepare and draft functional documents of the department. • Coordination of M&E activities should be improved through the establishment and proper management of a dedicated website. • Structured follow-up on aid pledges and aid delivery commitments made in the compact as part of an agreed code of conduct • Need to strengthen cooperation between MoPIC, other Government institutions and agencies involved in the delivery and implementation of the compact, including the regional administrations. | Pending | Project to update | Sept | Project staff & MoPIC
JA | Parlaiment Support Project | Kismayo | Jubbaland Parlaiment | LoA | August | • Due to lack of knowledge, skills and experience of the committees’ role and therefore, the challenges is to remain open to achieve unintended outcomes. • Recognized the Standing Committees can work at different levels which may, but do not necessarily reinforce each other. • Recognized the Standing Committees can work at different levels which may, but do not necessarily reinforce each other. • Recognized the Standing Committees can work at different levels which may, but do not necessarily reinforce each other. • Recognized the Standing Committees can work at different levels which may, but do not necessarily reinforce each other. • There is great concern on what ‘space’, ‘political space’ or ‘democratic space’ might for the youth at different levels, from the micro to the national level • The need to understand better how to the parliament works at different levels of their beneficiaries and in different arenas was not worked effectively as the parliament do not share sessions decisions with the beneficiaries as they mentioned that they do not understand the work of different standing committees. • Recognized the Standing Committees can work at different levels which may, but do not necessarily reinforce each other. | • At all levels, the MPs of Jubbaland state neither have the capacity of law drafting and 99% of the MPs nor have legal education background, hence we would recommend to establish and enhance a partnership between the Parliament of the other states and the international law firms, several civil society organizations, and the private sector in through developing and launching mechanisms of interaction, consultation and dialogue. • The parliament of Jubbaland is a new born and they have an absolute need of capacity trainings of Law Drafting, Laws Submission, Laws Approval Procedures, Law Amendment, Law Review, Laws Proposal, Law Discussions in the Sessions, etc. In addition, the parliament need with speedy achievement on the capacity building of leadership, chairing, advocacy, accountability, budget planning, oversight, monitoring, evaluation, gender response in peace building and reconciliation, standards of human rights and information and transparency to the society to improve the Jubbaland Parliament performance to be in line with the best international democratic practices both at the legislative mechanisms level and the methods/tools of exercising the oversight function of the parliamentary • UNDP Parliament Project, to support speed up of the implementation of the current LOAs as the remaining periods is so limited and lots of work need to be done. • There is need of UNDP parliament project to strengthen its presence in Jubaland to support and coordinate the implementation of activities | To be done | To be included in next phase of project