## M&E Plan
| GOAL: | By June of 2019, UN Peace Building Programme has contributed to sustaining Peace on Bougainville through maintainence of an enabling environment within and between the Government of Papua New Guinea and the Autonomous Government of Bougainvile for joint decision-making to progress implementation of the BPA, strengthening horizontal and vertical communication channels to increase the public and elite population of Bougainville and abroad, their knowledge and thereby understanding of the progress of the Bougainville Peace Agreement, and through this understanding, their awareness and coorperation in meeting the provisions of the BPA resulting in weapons disposal and at least 50% of the total population of Bougainville being well-informed of the consequences of their vote to be cast in a generally perceived safe and secure referendum.
Evaluation | Monitoring | [13 empty] | Evaluation
Broad Evaluation Questions | What do we want to know? | How will we know it? | Performance Marker |  | Where will we get the data? |  | How will we get the data? |  | When will data be captured, analysed and reported? |  |  | Who will capture, analyse and report the data? |  |  | Estimated Cost | Who will be involved | How will it be reported?
| Monitoring Question | Indicator | Baseline | Target | Primary Data Source | Secondary Data Source | Method of Primary Data Collection | Method of Secondary Data Collection | Frequency of: |  |  | Responsible for:
| Outcome 1 | Outcome Indicator 1.a:
| Enhanced political dialogue between the two Governments and the two Parliaments ensures decisions around BPA implementation and referendum are progressed jointly | Number of joint communiques on BPA or referendum process issued by the two governments | 1 | 4 | Official joint Govt press releases / Signed official documents | Project Progress Monitoring Reports | Media and Partner Communications monitoring / Liasion with NCOBA | Project Routine Monitoring and Review (Project Staff Progress Reports and Project Quarterly Data Quality Audits) / Liaison with GoPNG and ABG officials | data collection |  | Quarterly | data collection |  | M&E Officer & PMT |  | JSC / RUNOS with support of PBF Secretariat | Mid-term Evaluation Report / Endline Evaluation Report
[9 empty] | analysis |  | Six monthly | analysis |  | M&E Officer & PMT
[9 empty] | reporting |  | Six monthly | reporting |  | M&E Officer & PMT
[9 empty] | performance assessment | Internal | Annual | performance assessment | Internal | JSC / RUNOS with support of PBF Secretariat
[10 empty] | External | Mid-term and End-term |  | External
Outcome Indicator 1.b:
|  | Evidence of joint decisions by two Government on referendum questions, voter eligibility and appointment of chair for the BRC | Referendum questions, voter eligibility and BRC chair not agreed | Referendum questions, voter eligibility and BRC chair agreed | JSB Resolutions / Official Govt Gazzettes / Official Press Releases / Copy of Ballot Paper | Project Progress Monitoring Reports | Media and Partner Communications monitoring /Liaioson with NCOBA | Project Routine Monitoring and Review (Project Staff Progress Reports and Project Quarterly Data Quality Audits) / Liaison with GoPNG and ABG officials | data collection |  | Quarterly | data collection |  | M&E Officer & PMT |  | JSC / RUNOS with support of PBF Secretariat | Mid-term Evaluation Report / Endline Evaluation Report
[9 empty] | analysis |  | Six monthly | analysis |  | M&E Officer & PMT
[9 empty] | reporting |  | Six monthly | reporting |  | M&E Officer & PMT
[9 empty] | performance assessment | Internal | Annual | performance assessment | Internal | JSC / RUNOS with support of PBF Secretariat
[10 empty] | External | Mid-term and End-term |  | External
Outcome Indicator 1.c:
|  | Level of partnership between the national parliament and BHOR on the BPA and referendum supported by joint statements | Draft MoU for cooperation and collaboration exists | MoU for cooperation and Collaboration in place, signed and implemented | Official joint Govt press releases / Signed official government documents | Project Progress Monitoring Reports | Media and Partner Communications monitoring | Project Routine Monitoring and Review (Project Staff Progress Reports and Project Quarterly Data Quality Audits) / Liaison with NCOBA | data collection |  | Quarterly | data collection |  | M&E Officer & PMT |  | JSC / RUNOS with support of PBF Secretariat | Mid-term Evaluation Report / Endline Evaluation Report
[9 empty] | analysis |  | Six monthly | analysis |  | M&E Officer & PMT
[9 empty] | reporting |  | Six monthly | reporting |  | M&E Officer & PMT
[9 empty] | performance assessment | Internal | Annual | performance assessment | Internal | JSC / RUNOS with support of PBF Secretariat
[10 empty] | External | Mid-term and End-term |  | External
| Output 1.1 | Output Indicator 1.1.1
| JSB meets regularly and its resolutions are implemented jointly by the two governments | Frequency of JSB meetings and joint resolutions on the BRC and arrangements for the referendum | 1 | 4 | JSB signed meeting minutes / Official joint Govt press releases / Signed official documents | Media / Project Progress Monitoring Reports | Media monitoring / Liaison with NCOBA / UN Liaison Officer's Reports | Project Routine Monitoring and Review (Project Staff Progress Reports and Project Quarterly Data Quality Audits) / Liaison with NCOBA | data collection |  | Monthly | data collection |  | Implementing Staff |  | JSC / RUNOS with support of PBF Secretariat | Mid-term Evaluation Report / Endline Evaluation Report
[9 empty] | analysis |  | Quarterly | analysis |  | M&E Officer & PMT
[9 empty] | reporting |  | Six monthly | reporting |  | M&E Officer & PMT
[9 empty] | performance assessment | Internal | Annual | performance assessment | Internal | JSC / RUNOS with support of PBF Secretariat
[10 empty] | External | Mid-term and End-term |  | External
Output Indicator 1.1.2
|  | Proportion of joint JSB resolutions implemented by both GoPNG and ABG | 10% | 40% | Official joint Govt press releases / Signed official documents | Official joint Govt press releases / Signed official documents | Media monitoring / Liaison with NCOBA / UN Liaison Officer's Reports | Media monitoring / Liaison with NCOBA / UN Liaison Officer's Reports | data collection |  | Monthly | data collection |  | Implementing Staff |  | JSC / RUNOS with support of PBF Secretariat | Mid-term Evaluation Report / Endline Evaluation Report
[9 empty] | analysis |  | Quarterly | analysis |  | M&E Officer & PMT
[9 empty] | reporting |  | Six monthly | reporting |  | M&E Officer & PMT
[9 empty] | performance assessment | Internal | Annual | performance assessment | Internal | JSC / RUNOS with support of PBF Secretariat
[10 empty] | External | Mid-term and End-term |  | External
Output Indicator 1.1.3
|  | Number of women leaders participating in JSB meetings | 1 | 4 | Official joint Govt press releases / Signed official documents | Official joint Govt press releases / Signed official documents | Media monitoring / Liaison with NCOBA / UN Liaison Officer's Reports | Media monitoring / Liaison with NCOBA / UN Liaison Officer's Reports | data collection |  | Monthly | data collection |  | Implementing Staff |  | JSC / RUNOS with support of PBF Secretariat | Mid-term Evaluation Report / Endline Evaluation Report
[9 empty] | analysis |  | Quarterly | analysis |  | M&E Officer & PMT
[9 empty] | reporting |  | Six monthly | reporting |  | M&E Officer & PMT
[9 empty] | performance assessment | Internal | Annual | performance assessment | Internal | JSC / RUNOS with support of PBF Secretariat
[10 empty] | External | Mid-term and End-term |  | External
| Output 1.2 | Output Indicator 1.2.1
| The two parliaments make joint decisions on the BPA and referendum processes, including on post-referendum | Parliamentary Partnership Agreement signed between the National Parliament and the BHOR for cooperation and collaboration | 0 | 1 | Official joint Govt press releases / Signed official documents | Project Progress Monitoring Reports | Media monitoring / Liaison with NCOBA / UN Liaison Officer's Reports |  | data collection |  | Monthly | data collection |  | Implementing Staff |  | JSC / RUNOS with support of PBF Secretariat | Mid-term Evaluation Report / Endline Evaluation Report
[9 empty] | analysis |  | Quarterly | analysis |  | M&E Officer & PMT
[9 empty] | reporting |  | Six monthly | reporting |  | M&E Officer & PMT
[9 empty] | performance assessment | Internal | Annual | performance assessment | Internal | JSC / RUNOS with support of PBF Secretariat
[10 empty] | External | Mid-term and End-term |  | External
Output Indicator 1.2.2
|  | Number of public statements made by the speakers in support of a strengthened parliamentary partnership | 0 | 4 | Official joint Govt press releases / Signed official documents | Official joint Govt press releases / Signed official documents | Media monitoring / Liaison with NCOBA / UN Liaison Officer's Reports | Media monitoring / Liaison with NCOBA / UN Liaison Officer's Reports | data collection |  | Monthly | data collection |  | Implementing Staff |  | JSC / RUNOS with support of PBF Secretariat | Mid-term Evaluation Report / Endline Evaluation Report
[9 empty] | analysis |  | Quarterly | analysis |  | M&E Officer & PMT
[9 empty] | reporting |  | Six monthly | reporting |  | M&E Officer & PMT
[9 empty] | performance assessment | Internal | Annual | performance assessment | Internal | JSC / RUNOS with support of PBF Secretariat
[10 empty] | External | Mid-term and End-term |  | External
Output Indicator 1.2.3
|  | Number of mission reports tabled in national parliament following bipartisan committee missions | 0 | 1 | Official joint Govt press releases / Signed official documents | Official joint Govt press releases / Signed official documents | Media monitoring / Liaison with NCOBA / UN Liaison Officer's Reports | Media monitoring / Liaison with NCOBA / UN Liaison Officer's Reports | data collection |  | Monthly | data collection |  | Implementing Staff |  | JSC / RUNOS with support of PBF Secretariat | Mid-term Evaluation Report / Endline Evaluation Report
[9 empty] | analysis |  | Quarterly | analysis |  | M&E Officer & PMT
[9 empty] | reporting |  | Six monthly | reporting |  | M&E Officer & PMT
[9 empty] | performance assessment | Internal | Annual | performance assessment | Internal | JSC / RUNOS with support of PBF Secretariat
[10 empty] | External | Mid-term and End-term |  | External
Output Indicator 1.2.4
|  | Number of dialogues with the population on key political issues is enhanced through the Peace Implementation Forum, convening in each region. | 0 | 6 | Official joint Govt press releases / Signed official documents | Official joint Govt press releases / Signed official documents | Media monitoring / Liaison with NCOBA / UN Liaison Officer's Reports | Media monitoring / Liaison with NCOBA / UN Liaison Officer's Reports | data collection |  | Monthly | data collection |  | Implementing Staff |  | JSC / RUNOS with support of PBF Secretariat | Mid-term Evaluation Report / Endline Evaluation Report
[9 empty] | analysis |  | Quarterly | analysis |  | M&E Officer & PMT
[9 empty] | reporting |  | Six monthly | reporting |  | M&E Officer & PMT
[9 empty] | performance assessment | Internal | Annual | performance assessment | Internal | JSC / RUNOS with support of PBF Secretariat
[10 empty] | External | Mid-term and End-term |  | External
| Output 1.3 | Output Indicator 1.3.1
| Key government institutions with responsibilities for BPA implementation and coordination between the two governments are enabled to implement their functions effectively | NCOBA establishes a permanent presence in the AROB to facilitate the implementation of the BPA | 0 | NCOBA establishes an office in the AROB | Official joint Govt press releases / Signed official documents | Official joint Govt press releases / Signed official documents | Media monitoring / Liaison with NCOBA / UN Liaison Officer's Reports | Media monitoring / Liaison with NCOBA / UN Liaison Officer's Reports | data collection |  | Monthly | data collection |  | Implementing Staff |  | JSC / RUNOS with support of PBF Secretariat | Mid-term Evaluation Report / Endline Evaluation Report
[9 empty] | analysis |  | Quarterly | analysis |  | M&E Officer & PMT
[9 empty] | reporting |  | Six monthly | reporting |  | M&E Officer & PMT
[9 empty] | performance assessment | Internal | Annual | performance assessment | Internal | JSC / RUNOS with support of PBF Secretariat
[10 empty] | External | Mid-term and End-term |  | External
Output Indicator 1.3.2
|  | Number of annual meetings held between the two Chief Secretaries | 2 | 4 | Official joint Govt press releases / Signed official documents | Official joint Govt press releases / Signed official documents | Media monitoring / Liaison with NCOBA / UN Liaison Officer's Reports | Media monitoring / Liaison with NCOBA / UN Liaison Officer's Reports | data collection |  | Monthly | data collection |  | Implementing Staff |  | JSC / RUNOS with support of PBF Secretariat | Mid-term Evaluation Report / Endline Evaluation Report
[9 empty] | analysis |  | Quarterly | analysis |  | M&E Officer & PMT
[9 empty] | reporting |  | Six monthly | reporting |  | M&E Officer & PMT
[9 empty] | performance assessment | Internal | Annual | performance assessment | Internal | JSC / RUNOS with support of PBF Secretariat
[10 empty] | External | Mid-term and End-term |  | External
| Outcome 2 | Outcome Indicator 2.a:
| Increased dialogue and awareness on the BPA, referendum and post-referendum issues ensuring that both the population in and outside of Bougainville is informed, and is and feels, included in the process | Increase in the proportion of women and youth with a sufficient understanding of the referendum | 26% | 15% increase | Six monthly Public and Elite Perception survey findings / Mid-term Evaluation Report | Project Progress Monitoring Reports | Six monthly Public Perception Survey / Six monthly Elite Perception Survey / Mid-term Evaluation | Project Routine Monitoring (Communications Consultant's Reports, Staff Progress Monitoring Reports and Project Quarterly Data Quality Audits) | data collection |  | Six monthly | data collection |  | M&E Officer & PMT |  | JSC / RUNOS with support of PBF Secretariat | Mid-term Evaluation Report / Endline Evaluation Report
[9 empty] | analysis |  | Six monthly | analysis |  | M&E Officer & PMT
[9 empty] | reporting |  | Six monthly | reporting |  | M&E Officer & PMT
[9 empty] | performance assessment | Internal | Annual | performance assessment | Internal | JSC / RUNOS with support of PBF Secretariat
[10 empty] | External | Mid-term and End-term |  | External
Outcome Indicator 2.b:
|  | Improved understanding of BPA and its pillars by the wider Bougainville population | 27% | 23% increase | Six monthly Public and Elite Perception survey findings / Mid-term Evaluation Report | Project Progress Monitoring Reports | Six monthly Public Perception Survey / Six monthly Elite Perception Survey / Mid-term Evaluation | Project Routine Monitoring (Communications Consultant's Reports, Staff Progress Monitoring Reports and Project Quarterly Data Quality Audits) | data collection |  | Six monthly | data collection |  | M&E Officer & PMT |  | JSC / RUNOS with support of PBF Secretariat | Mid-term Evaluation Report / Endline Evaluation Report
[9 empty] | analysis |  | Six monthly | analysis |  | M&E Officer & PMT
[9 empty] | reporting |  | Six monthly | reporting |  | M&E Officer & PMT
[9 empty] | performance assessment | Internal | Annual | performance assessment | Internal | JSC / RUNOS with support of PBF Secretariat
[10 empty] | External | Mid-term and End-term |  | External
| Output 2.1 | Output Indicator 2.1.1
| Both governments agree on joint messages on the BPA, including referendum, and facilitate their dissemination. | Bi-monthly meetings convened by both governments through the BRC Transitional Committee to discuss key messages and their dissemination | 1 meeting convened through the BRC transitional committee | All Key messages agreed by the BRC | Official joint Govt press releases / Signed official documents | Official joint Govt press releases / Signed official documents | Media monitoring / Liaison with NCOBA / UN Liaison Officer's Reports | Media monitoring / Liaison with NCOBA / UN Liaison Officer's Reports | data collection |  | Monthly | data collection |  | Implementing Staff |  | JSC / RUNOS with support of PBF Secretariat | Mid-term Evaluation Report / Endline Evaluation Report
[9 empty] | analysis |  | Quarterly | analysis |  | M&E Officer & PMT
[9 empty] | reporting |  | Six monthly | reporting |  | M&E Officer & PMT
[9 empty] | performance assessment | Internal | Annual | performance assessment | Internal | JSC / RUNOS with support of PBF Secretariat
[10 empty] | External | Mid-term and End-term |  | External
| Output 2.2 | Output Indicator 2.2.1
| Innovative and community led dialogues about a peaceful future for Bougainville | Number of awareness sessions conducted by the Department of Community Government at the district level | 0 | 13 | Official joint Govt press releases / Signed official documents | Official joint Govt press releases / Signed official documents | Media monitoring / Liaison with NCOBA / UN Liaison Officer's Reports | Media monitoring / Liaison with NCOBA / UN Liaison Officer's Reports | data collection |  | Monthly | data collection |  | Implementing Staff |  | JSC / RUNOS with support of PBF Secretariat | Mid-term Evaluation Report / Endline Evaluation Report
[9 empty] | analysis |  | Quarterly | analysis |  | M&E Officer & PMT
[9 empty] | reporting |  | Six monthly | reporting |  | M&E Officer & PMT
[9 empty] | performance assessment | Internal | Annual | performance assessment | Internal | JSC / RUNOS with support of PBF Secretariat
[10 empty] | External | Mid-term and End-term |  | External
Output Indicator 2.2.2
|  | Number of radio dramas on the BPA produced and aired across Bougainville and Papua New Guinea | 0 | 10 | Official joint Govt press releases / Signed official documents | Official joint Govt press releases / Signed official documents | Media monitoring / Liaison with NCOBA / UN Liaison Officer's Reports | Media monitoring / Liaison with NCOBA / UN Liaison Officer's Reports | data collection |  | Monthly | data collection |  | Implementing Staff |  | JSC / RUNOS with support of PBF Secretariat | Mid-term Evaluation Report / Endline Evaluation Report
[9 empty] | analysis |  | Quarterly | analysis |  | M&E Officer & PMT
[9 empty] | reporting |  | Six monthly | reporting |  | M&E Officer & PMT
[9 empty] | performance assessment | Internal | Annual | performance assessment | Internal | JSC / RUNOS with support of PBF Secretariat
[10 empty] | External | Mid-term and End-term |  | External
Output Indicator 2.2.3
|  | Number of BPA and referendum awareness sessions staged outside of Bougainville | 0 | 3 | Official joint Govt press releases / Signed official documents | Official joint Govt press releases / Signed official documents | Media monitoring / Liaison with NCOBA / UN Liaison Officer's Reports | Media monitoring / Liaison with NCOBA / UN Liaison Officer's Reports | data collection |  | Monthly | data collection |  | Implementing Staff |  | JSC / RUNOS with support of PBF Secretariat | Mid-term Evaluation Report / Endline Evaluation Report
[9 empty] | analysis |  | Quarterly | analysis |  | M&E Officer & PMT
[9 empty] | reporting |  | Six monthly | reporting |  | M&E Officer & PMT
[9 empty] | performance assessment | Internal | Annual | performance assessment | Internal | JSC / RUNOS with support of PBF Secretariat
[10 empty] | External | Mid-term and End-term |  | External
| Output 2.3 | Output Indicator 2.3.1
| BPA dialogue and referendum awareness raising increases within Papua New Guinea. | Number of jointly approved messages disseminated via SMS through mobile phones across AROB | 0 | 10 | Copy of SMS Blast messages | Copy of SMS Blast messages | Media monitoring | Media monitoring | data collection |  | Monthly | data collection |  | Implementing Staff |  | JSC / RUNOS with support of PBF Secretariat | Mid-term Evaluation Report / Endline Evaluation Report
[9 empty] | analysis |  | Quarterly | analysis |  | M&E Officer & PMT
[9 empty] | reporting |  | Six monthly | reporting |  | M&E Officer & PMT
[9 empty] | performance assessment | Internal | Annual | performance assessment | Internal | JSC / RUNOS with support of PBF Secretariat
[10 empty] | External | Mid-term and End-term |  | External
Output Indicator 2.3.2
|  | Media practitioners have an increased awareness and knowledge of the BPA and referendum process | 0 | 2 trainings with trainees demonstrating improvement in knowledge on BPA and referendum issues | Official joint Govt press releases / Signed official documents | Official joint Govt press releases / Signed official documents | Media monitoring / Liaison with NCOBA / UN Liaison Officer's Reports | Media monitoring / Liaison with NCOBA / UN Liaison Officer's Reports | data collection |  | Monthly | data collection |  | Implementing Staff |  | JSC / RUNOS with support of PBF Secretariat | Mid-term Evaluation Report / Endline Evaluation Report
[9 empty] | analysis |  | Quarterly | analysis |  | M&E Officer & PMT
[9 empty] | reporting |  | Six monthly | reporting |  | M&E Officer & PMT
[9 empty] | performance assessment | Internal | Annual | performance assessment | Internal | JSC / RUNOS with support of PBF Secretariat
[10 empty] | External | Mid-term and End-term |  | External
Output Indicator 2.3.3
|  | Increased awareness by PNG population in the effective implementation of the BPA through regular forums | 0 | 8 forums conducted with participants demonstrating increase in knowledge on BPA implementation | Official joint Govt press releases / Signed official documents | Official joint Govt press releases / Signed official documents | Media monitoring / Liaison with NCOBA / UN Liaison Officer's Reports | Media monitoring / Liaison with NCOBA / UN Liaison Officer's Reports | data collection |  | Monthly | data collection |  | Implementing Staff |  | JSC / RUNOS with support of PBF Secretariat | Mid-term Evaluation Report / Endline Evaluation Report
[9 empty] | analysis |  | Quarterly | analysis |  | M&E Officer & PMT
[9 empty] | reporting |  | Six monthly | reporting |  | M&E Officer & PMT
[9 empty] | performance assessment | Internal | Annual | performance assessment | Internal | JSC / RUNOS with support of PBF Secretariat
[10 empty] | External | Mid-term and End-term |  | External
| Outcome 3 | Outcome Indicator 3.a:
| Weapons disposal is progressed as per the BPA through a joint ABG-GoPNG process whilst supporting factional unification and solutions to security concerns of outlier communities | Weapons disposal process completed and a safe and secure environment provided for conduct of the Bougainville referendum | Few weapons collected through the referendum ready concept of parliament | Weapons collected from all 33 constituencies of Bougainville | Community Weapons Disposal Status Reports / Official joint govt & factions press releases / Mid-term Evaluation Report | Project Progress Monitoring Reports | Constituency Referendum Ready Declarations Tracking / Media monitoring / Elite and Public Perception Survey / Mid-term Evaluation | Desk Review of all Status Reports / Desk Review of Constituency Referendum Ready Declarations / Project Routine Monitoring (Weapons Disposal Expert's Reports, Staff Progress Monitoring Reports) | data collection |  | Quarterly | data collection |  | M&E Officer & PMT |  | JSC / RUNOS with support of PBF Secretariat | Mid-term Evaluation Report / Endline Evaluation Report
[9 empty] | analysis |  | Six monthly | analysis |  | M&E Officer & PMT
[9 empty] | reporting |  | Six monthly | reporting |  | M&E Officer & PMT
[9 empty] | performance assessment | Internal | Annual | performance assessment | Internal | JSC / RUNOS with support of PBF Secretariat
[10 empty] | External | Mid-term and End-term |  | External
Outcome Indicator 3.b:
|  | Outlier factions accepting and cooperating in the weapons disposal process | 3 outlier factions are still not part of the peace process and did not sign the BPA | 3 remaining outlier factions participating in the weapons disposal process | Constituency Referendum Ready Declaration / Official joint Govt and factions press releases / Signed official documents / Mid-term Evaluation Report | Project Progress Monitoring Reports | Constituency Referendum Ready Declarations Tracking / Media monitoring / Mid-term Evaluation | Desk Review of Constituency Referendum Ready Declarations / Project Routine Monitoring (Weapons Disposal Expert Reports, Staff Progress Monitoring Reports) | data collection |  | Quarterly | data collection |  | M&E Officer & PMT |  | JSC / RUNOS with support of PBF Secretariat | Mid-term Evaluation Report / Endline Evaluation Report
[9 empty] | analysis |  | Six monthly | analysis |  | M&E Officer & PMT
[9 empty] | reporting |  | Six monthly | reporting |  | M&E Officer & PMT
[9 empty] | performance assessment | Internal | Annual | performance assessment | Internal | JSC / RUNOS with support of PBF Secretariat
[10 empty] | External | Mid-term and End-term |  | External
Outcome Indicator 3.c:
|  | All communities around the last factions become part of the weapons disposal process and benefitting from reintegration | No community-based approach has been undertaken to collect weapons from communities in Bougainville | A community approach implemented to collect weapons in Bougainville led by the ABG | Constituency Referendum Ready Declarations / Official joint Govt and factions press releases / Mid-term Evaluation Report | Project Progress Monitoring Reports | Constituency Referendum Ready Declarations Tracking / Mid-term Evaluation / Media monitoring | Desk Review of Constituency Referendum Ready Declarations / Project Routine Monitoring (Weapons Disposal Expert Reports, Staff Progress Monitoring Reports) | data collection |  | Quarterly | data collection |  | M&E Officer & PMT |  | JSC / RUNOS with support of PBF Secretariat | Mid-term Evaluation Report / Endline Evaluation Report
[9 empty] | analysis |  | Six monthly | analysis |  | M&E Officer & PMT
[9 empty] | reporting |  | Six monthly | reporting |  | M&E Officer & PMT
[9 empty] | performance assessment | Internal | Annual | performance assessment | Internal | JSC / RUNOS with support of PBF Secretariat
[10 empty] | External | Mid-term and End-term |  | External
| Output 3.1 | Output Indicator 3.1.1
| In partnership with DPAI, implementation of the recommendations of the weapons disposal report by the UN, including support to the set up and operation of a Joint Secretariat; identification of remaining weapons and monitoring of collection | The two governments agree through a JSB resolution on the political conditions for the successful collection of weapons | 0 | 1 | Official joint Govt press releases / Signed official documents | Official joint Govt press releases / Signed official documents | Media monitoring / Liaison with NCOBA / UN Liaison Officer's Reports | Media monitoring / Liaison with NCOBA / UN Liaison Officer's Reports | data collection |  | Monthly | data collection |  | Implementing Staff |  | JSC / RUNOS with support of PBF Secretariat | Mid-term Evaluation Report / Endline Evaluation Report
[9 empty] | analysis |  | Quarterly | analysis |  | M&E Officer & PMT
[9 empty] | reporting |  | Six monthly | reporting |  | M&E Officer & PMT
[9 empty] | performance assessment | Internal | Annual | performance assessment | Internal | JSC / RUNOS with support of PBF Secretariat
[10 empty] | External | Mid-term and End-term |  | External
Output Indicator 3.1.2
|  | Level of knowledge gained by CSOs, CBOs, Community Governments, women, youth and churches on weapons disposal as a key pillar of the BPA and of arms collection processes | 43% | 58% | Official joint Govt press releases / Signed official documents | Official joint Govt press releases / Signed official documents | Media monitoring / Liaison with NCOBA / UN Liaison Officer's Reports | Media monitoring / Liaison with NCOBA / UN Liaison Officer's Reports | data collection |  | Monthly | data collection |  | Implementing Staff |  | JSC / RUNOS with support of PBF Secretariat | Mid-term Evaluation Report / Endline Evaluation Report
[9 empty] | analysis |  | Quarterly | analysis |  | M&E Officer & PMT
[9 empty] | reporting |  | Six monthly | reporting |  | M&E Officer & PMT
[9 empty] | performance assessment | Internal | Annual | performance assessment | Internal | JSC / RUNOS with support of PBF Secretariat
[10 empty] | External | Mid-term and End-term |  | External
Output Indicator 3.1.3
|  | Number of Arms collection centres established and number of weapons collected and recorded | No official record of weapons collection centres or weapons collected in targeted communities in Bougainville | Weapons collection centres established in all 33 constituencies with weapons collected recorded and destroyed | Official joint Govt press releases / Signed official documents | Official joint Govt press releases / Signed official documents | Media monitoring / Liaison with NCOBA / UN Liaison Officer's Reports | Media monitoring / Liaison with NCOBA / UN Liaison Officer's Reports | data collection |  | Monthly | data collection |  | Implementing Staff |  | JSC / RUNOS with support of PBF Secretariat | Mid-term Evaluation Report / Endline Evaluation Report
[9 empty] | analysis |  | Quarterly | analysis |  | M&E Officer & PMT
[9 empty] | reporting |  | Six monthly | reporting |  | M&E Officer & PMT
[9 empty] | performance assessment | Internal | Annual | performance assessment | Internal | JSC / RUNOS with support of PBF Secretariat
[10 empty] | External | Mid-term and End-term |  | External
Output Indicator 3.1.4
|  | Number of EOD teams trained and deployable to undertake EOD activities pre and post-referendum | 0 EOD local capacity on Bougainville | 1 local EOD team trained and operational | Official joint Govt press releases / Signed official documents | Official joint Govt press releases / Signed official documents | Media monitoring / Liaison with NCOBA / UN Liaison Officer's Reports | Media monitoring / Liaison with NCOBA / UN Liaison Officer's Reports | data collection |  | Monthly | data collection |  | Implementing Staff |  | JSC / RUNOS with support of PBF Secretariat | Mid-term Evaluation Report / Endline Evaluation Report
[9 empty] | analysis |  | Quarterly | analysis |  | M&E Officer & PMT
[9 empty] | reporting |  | Six monthly | reporting |  | M&E Officer & PMT
[9 empty] | performance assessment | Internal | Annual | performance assessment | Internal | JSC / RUNOS with support of PBF Secretariat
[10 empty] | External | Mid-term and End-term |  | External
| Output 3.2 | Output Indicator 3.2.1
| Support to the factional unification in Bougainville, including bringing the remaining outliers on board with the BPA and helping to implement and monitor the MOUs between the factions and the ABG | All outlier factions sign and implement an MoU/MoA or declaration of intent to participate in the implementation of the peace process | Three factions do not recognise the ABG and are not part of the peace process | All factions recognize and work with ABG to actively participate in the implementation of the peace process | Official joint Govt press releases / Signed official documents | Official joint Govt press releases / Signed official documents | Media monitoring / Liaison with NCOBA / UN Liaison Officer's Reports | Media monitoring / Liaison with NCOBA / UN Liaison Officer's Reports | data collection |  | Monthly | data collection |  | Implementing Staff |  | JSC / RUNOS with support of PBF Secretariat | Mid-term Evaluation Report / Endline Evaluation Report
[9 empty] | analysis |  | Quarterly | analysis |  | M&E Officer & PMT
[9 empty] | reporting |  | Six monthly | reporting |  | M&E Officer & PMT
[9 empty] | performance assessment | Internal | Annual | performance assessment | Internal | JSC / RUNOS with support of PBF Secretariat
[10 empty] | External | Mid-term and End-term |  | External
Output Indicator 3.2.2
|  | Women and Youth Participate in weapons disposal efforts disaggregated by age and sex | Very few women and youth participate in weapons disposal discourse in Bougainville | 50% of those involved in the weapons disposal process are women and youth | Official joint Govt press releases / Signed official documents | Official joint Govt press releases / Signed official documents | Media monitoring / Liaison with NCOBA / UN Liaison Officer's Reports | Media monitoring / Liaison with NCOBA / UN Liaison Officer's Reports | data collection |  | Monthly | data collection |  | Implementing Staff |  | JSC / RUNOS with support of PBF Secretariat | Mid-term Evaluation Report / Endline Evaluation Report
[9 empty] | analysis |  | Quarterly | analysis |  | M&E Officer & PMT
[9 empty] | reporting |  | Six monthly | reporting |  | M&E Officer & PMT
[9 empty] | performance assessment | Internal | Annual | performance assessment | Internal | JSC / RUNOS with support of PBF Secretariat
[10 empty] | External | Mid-term and End-term |  | External
Output Indicator 3.2.3
|  | Successful reconciliations between former fighting factions in Bougainville and with the PNG Government | Very few reconciliations among factions and government have been successful | All reconciliations completed between former fighting factions and the government | Official joint Govt press releases / Signed official documents | Official joint Govt press releases / Signed official documents | Media monitoring / Liaison with NCOBA / UN Liaison Officer's Reports | Media monitoring / Liaison with NCOBA / UN Liaison Officer's Reports | data collection |  | Monthly | data collection |  | Implementing Staff |  | JSC / RUNOS with support of PBF Secretariat | Mid-term Evaluation Report / Endline Evaluation Report
[9 empty] | analysis |  | Quarterly | analysis |  | M&E Officer & PMT
[9 empty] | reporting |  | Six monthly | reporting |  | M&E Officer & PMT
[9 empty] | performance assessment | Internal | Annual | performance assessment | Internal | JSC / RUNOS with support of PBF Secretariat
[10 empty] | External | Mid-term and End-term |  | External
| Output 3.3 | Output Indicator 3.3.1
| Targeted support to ex-combatants and affected communities with community-based reinsertion activities in war affected communities and linked to the weapons disposal process, which may include support with community conversations, referral to trauma services, community development for improved social cohesion, support to war wounded | Number of community reinsertion programmes targeting localities with outlying factions | Unknown | At least 80 per cent of former combatants of the factions outside of the BPA benefit from community reinsertion programmes | Official joint Govt press releases / Signed official documents | Official joint Govt press releases / Signed official documents | Media monitoring / Liaison with NCOBA / UN Liaison Officer's Reports | Media monitoring / Liaison with NCOBA / UN Liaison Officer's Reports | data collection |  | Monthly | data collection |  | Implementing Staff |  | JSC / RUNOS with support of PBF Secretariat | Mid-term Evaluation Report / Endline Evaluation Report
[9 empty] | analysis |  | Quarterly | analysis |  | M&E Officer & PMT
[9 empty] | reporting |  | Six monthly | reporting |  | M&E Officer & PMT
[9 empty] | performance assessment | Internal | Annual | performance assessment | Internal | JSC / RUNOS with support of PBF Secretariat
[10 empty] | External | Mid-term and End-term |  | External
Output Indicator 3.3.2
|  | Number of targeted community-based reinsertion programmes for engagement on weapons disposal carried out | 0 | 10 communities benefitting from community-based reinsertion assistance report improved perceptions of security and the adaptation of former combatants to civilian life | Official joint Govt press releases / Signed official documents | Official joint Govt press releases / Signed official documents | Media monitoring / Liaison with NCOBA / UN Liaison Officer's Reports | Media monitoring / Liaison with NCOBA / UN Liaison Officer's Reports | data collection |  | Monthly | data collection |  | Implementing Staff |  | JSC / RUNOS with support of PBF Secretariat | Mid-term Evaluation Report / Endline Evaluation Report
[9 empty] | analysis |  | Quarterly | analysis |  | M&E Officer & PMT
[9 empty] | reporting |  | Six monthly | reporting |  | M&E Officer & PMT
[9 empty] | performance assessment | Internal | Annual | performance assessment | Internal | JSC / RUNOS with support of PBF Secretariat
[10 empty] | External | Mid-term and End-term |  | External
Note on C1: Shaddie Tapo: Guiding Principle (Shaddie's note)

## GanttChartPro (hidden)
Gantt Chart Template Pro
Gantt Chart Template Pro is similar to this free version, but
it is more feature-packed. It also comes with other bonus content.
Learn About Gantt Chart Template Pro
https://www.vertex42.com/ExcelTemplates/excel-gantt-chart.html
The following link is a blog post that talks specifically about the
Pro version for Excel Online.
Gantt Chart Template Pro for Excel Online
Benefits and Features of Gantt Chart Template Pro
Simple Color-Coding
The Pro version includes a column for specifying the color of bars in the chart. For example,
you could change the color based on urgency or task lead.
Daily, Weekly, or Monthly View
The Pro version includes a drop-down next to the Display Week that lets you choose to display
the columns in the chart area as days, weeks, or months.
Use Work Days as an Input
By default, the Pro version is set up to have you enter Work Days instead of Calendar Days.
The expanded set of template rows provides more options for defining the Start date, End date,
and Duration of tasks. Define a task based on …
- Start date and End date
- Start date and Work days
- Start date and Calendar days
Easily Create Task Dependencies
Though you can still use your own formulas for creating task dependencies, the Pro version
includes template rows that calculate the Start date based on the WBS number that you enter
in the Predecessor column.
Exclude Holidays from Work Days
List holidays and other specific non-working days that you want to exclude from work days.
September Progress Reports
Email Reminder on End of Month Report due date
Review and provide feedback on reports
Call for finalisation of monthly reports
Receipt of finalised monthly reports for entry and archives
October Progress Reports
Email Reminder on End of Month Report due date
Review and provide feedback on reports
Call for finalisation of monthly reports
Receipt of finalised monthly reports for entry and archives
November Progress Reports
Email Reminder on End of Month Report due date
Review and provide feedback on reports
Call for finalisation of monthly reports
Receipt of finalised monthly reports for entry and archives
Progress on track
Progress off track
Completed
Not yet due to start
Preparation of M&E products for training and participants assessment as well as training contents
Preparation of M&E products for training and participants assessment as well as training contents
September Visual Updates of GYPI and PBF 2 Updates
| October Visual Updates of GYPI and PBF 2 Updates |  | 2018-10-22 | 5
| November Visual Updates of GYPI and PBF 2 Updates |  | 2018-11-26 | 5
| December/January Visual Updates of GYPI and PBF 2 Updates |  | 2019-01-28 | 5