## Sheet1
Dynamic Futures Programme
Communications Plan – January – December 2019
# | Key Event - Activity - Deliverables | Target Audience | Key Messages | Documentation | Desired Result / com output | Medium | Frequency | Due date | Delivery Date | Status | No of Units
1 | Project activities
1 | World Youth Skills Day | Donor, Mass Media, Local and International Community | Highlights Fakhoora scholar’s skilling development | Captions of Fakhoora scholar’s community service interventions in Gaza | 30 photos, Reports reflect high engagement with the Campaign, | Fakhoora Website, Donor, Newspaper | one-time | 15.07.2019 | 15.07.2019 | Completed
2 | International Youth Day | Donor, Mass Media, Local and International Community | Highlights Fakhoora scholar’s community service to reflect their role youth leaders in Gaza | Captions of Fakhoora scholar’s community service interventions in Gaza | 30 photos, Reports reflect high engagement with the Campaign, | Fakhoora Website, Donor, Newspaper | one-time | 12.08.2019 | 12.08.2019 | Completed
3 | International Day for the Eradication of Poverty | Donor, Mass Media, Local and International Community | Reflect on the situation of Gazans under siege, contributing to ideas to enhance and empower people | Captions of Fakhoora scholar’s community service interventions in Gaza | 30 photos, Reports reflect high engagement with the Campaign, | Fakhoora Website, Donor, Newspaper | one-time | 17.10.2018 | 17.10.2018 | Planned
2 | Key Events
WBS 1110: Domestic Undergraduate Scholarships
4 | Graduation Ceremony for 120 Scholars | Donor, Mass Media, Local Community, Representatives of Universities | increase the visibility of Dynamic Future programme among the public public and enhances community ownership of the programme, | Press release, Photography, 2 minutes, Documentary, 1 Minute time-lapse Documentary, Al Fakhoora Dynamic Futures Page Story, and UNDP Website Story. | Documentary, 70 photos, Press Release, time-lapse Documentary, published Stories, Fakhoora progress report | UNDP Website, Fakhoora.org | one-time | 19.02.2019 | 19.02.2019 | Completed
5 | Graduation Ceremony for 85 Scholars | Donor, Mass Media, Local Community, Representatives of Universities | increase the visibility of Dynamic Future programme among the public public and enhances community ownership of the programme, | Press release, Photography, 2 minutes, Documentary, Al Fakhoora Dynamic Futures Page Story, and UNDP Website Story. | Documentary, 70 photos, Press Release, time-lapse Documentary, published Stories, Fakhoora progress report | UNDP Website, Fakhoora.org | one-time | 18.12.2019 | 18.12.2019 | Planned
WBS 1120: Technical Assistance for Quality Education
6. | Higher Education in Palestine | Donor, UNDP, Local Partners | Knowledge Product to be share with different stockholders | Press release, Research | Press Release, Fakhoora progress report, Distibuation in the | UNDP Website, Fakhoora.org | one-time | December | December | Planned
WBS 1210 – 1250 : Student Affairs
7 | Ramdan Iftar for | Donor, Local Community, | Show a case of One DF Community of scholars who interact and interchange experiences. | Press Statement | 70 photos and Captions | UNDP Website, Fakhoora.org | one-time | 07.05.2019 | 07.05.2019 | Completed
|  |  |  | Photography | Fakhoora progress report
Success story
8 | Al Fakhoora Sports Carnival | Donor, Local Community, | Show a case of studetns skills and promot the Programme in Gaza and byond | Press release, Photography | 70 photos and Captions | UNDP Website, Fakhoora.org | one-time | July | July | Completed
Fakhoora progress report
9 | Lunching of English Training for 300 Students | Donor, Local Community, Local Partners | Highlighting an important activity within the context of student capacity building and the partnerships building with key organizations. | Press Statement | 10 photos, | UNDP Website, Fakhoora.org | one-time | February | December | In progress
|  |  |  | Photography | Fakhoora progress report
10 | Lunching of ICDL Training for 97 Students | Donor, Mass Media, Local Community, | Highlighting an important activity within the context of student capacity building and the partnerships building with key organizations. | Press Statement | 10 photos, | UNDP Website, Fakhoora.org | one-time | March | April | Completed
|  |  |  | Photography | Fakhoora progress report
Success story
WBS 1140: Technical Assistance for Student Services
11 | Academic Counselling Toolkit | Donor, UNDP, Local Partners | Knowledge Sharing Document that reflect the QE Strategy | Toolkit | Fakhoora progress report | UNDP Website, Fakhoora.org | one-time | December | December | Planned
12 | Wellbeing and Resilience Toolkit | Donor, UNDP, Local Partners | Knowledge Sharing Document that reflect the QE Strategy | Toolkit | Fakhoora progress report | UNDP Website, Fakhoora.org | one-time | December | December | Planned
WBS 2110 – 2160 : Leadership Development
13 | Inspire Conference | Donor, Mass Media, Local Community, | Show case of student's capacities and skills through the actualization of their tranings | Press release, Photography, 2 minutes Documentary and Promo, Al Fakhoora Dynamic Futures Page Story, and UNDP Website Story. | Press Release, 70 photos,, Fakhoora progress report | UNDP Website, Fakhoora.org | one-time | 31.01.2019 | 31.01.2019 | Completed
14 | Leadership Development Programme, Foundation Training for 28 students | Donor, Mass Media, Local Community, | Highlighting the continuity of the Leadership building programme and show case of student activities | Photography and Short Video | 70 photos,, Fakhoora progress report | UNDP Website, Fakhoora.org | one-time | February | February | Completed
15 | Launching Art of dialogue and Facilitation Training Programme for at least 42 scholars | Donor, Mass Media, Local Community, | Highlighting the continuity of the Leadership building programme and show case of student activities | Captions of Fakhoora scholar’s voices and feedback | 70 photos, Fakhoora progress report and Short Vedio | Fakhoora Website, Donor, | one-time | July | August | Completed
16 | Selction Camp for the third level of Leadership Development | Donor, Mass Media, Local Community, | Highlighting the approach of the Leadership Development programme | Captions of Fakhoora scholar’s voices and feedback | 70 photos, Short Vedio | Fakhoora Website, Donor, | one-time | August | August | Completed
17 | Starting Third Level of Training Development | Donor, Mass Media, Local Community, | Highlighting the new developments of the Leadership Model | Press release, Photography, 2 minutes Documentary and Promo, Al Fakhoora Dynamic Futures Page Story, and UNDP Website Story. | 70 photos, Documentary Press Release, published Stories, Fakhoora progress report | Fakhoora Website, Donor, | one-time | September | November | Planned
18 | Kicking off the Students Clubs | Donor, Mass Media, Local Community, | Highlighting the students creativity and innovation and capacity | Captions of Fakhoora scholar’s voices and feedback | 70 photos, Documentary Press Statement, published Stories, Fakhoora progress report | Fakhoora Website, Donor, | one-time | September | TBC | Planned
WBS 2161: Technical Assistance for Leadership Development
19 | Publication of Leadership Development Component Design | Donor, UNDP, Local Partners | Knowledge Sharing Document that reflect the QE Strategy | Book | Fakhoora progress report | UNDP Website, Fakhoora.org | one-time | December | December | Planned
WBS 2210 – 2253 : Economic Empowerment
20 | Triggering Second Round of Internship Programme | Donor, Mass Media, Local and International Community | Highlight the Internship Intervention as an effective modality to support students access the Market | Photography, Al Fakhoora Dynamic Futures Page, 7 Stories, UNDP Website Story, | 70 photos, Fakhoora progress report, Press Statement | Fakhoora Website, Donor, Newspaper | one-time | April | August | Completed
21 | Triggering Third Round of Internship Programme | Donor, Mass Media, Local and International Community | Highlight the Internship Intervention as an effective modality to support students access the Market | Photography, Al Fakhoora Dynamic Futures Page, Story, UNDP Website Story, | 70 photos, Fakhoora progress report , Press Statement | Fakhoora Website, Donor, Newspaper | one-time | September | TBD | Planned
22 | Career Day | Donor, Mass Media, Local and International Community | Show Fakhoora Students Capacities and skills and engage them with market actors | Photography, Al Fakhoora Dynamic Futures Page, Story, UNDP Website Story, | 70 photos, Fakhoora progress report , Press Statement | Fakhoora Website, Donor, Newspaper | one-time | 25.03.2019 | 25.03.2019 | Completed
23 | Career Day | Donor, Mass Media, Local and International Community | Show Fakhoora Students Capacities and skills and engage them with market actors | Photography, Al Fakhoora Dynamic Futures Page, Story, UNDP Website Story, | 70 photos, Fakhoora progress report , Press Statement | Fakhoora Website, Donor, Newspaper | one-time | September | TBC | Planned
24 | Lunching Internship Website | Donor, Mass Media, Local and International Community | Connect Al Fakhoora Alumni with the Market and connect the market with Alumni capacities and stories. | Photography, Al Fakhoora Dynamic Futures Page, Story, UNDP Website Story, | Fakhoora progress report , Press Statement | Fakhoora Website, Donor, Newspaper | one-time | October | TBC | Planned
25 | Inspirational Talks | Donor, Mass Media, Local and International Community | Inspire students of successful models in selected field | Photography, Al Fakhoora Dynamic Futures Page, Story, UNDP Website Story, | 70 photos, Fakhoora progress report | Fakhoora Website, Donor, Newspaper | one-time | 01.08.2019 | 01.08.2019 | Completed
26 | Launching E-work Project | Donor, Mass Media, Local and International Community | Highlight the e-work Intervention as an effective modality to support students access the global Market | Press Statement, Photography, 2 minutes Documentary and Promo, Al Fakhoora Dynamic Futures Page Story, and UNDP Website Story. | Fakhoora progress report , Press Statement | Fakhoora Website, Donor, Newspaper | one-time | September | TBC | Planned
WBS 2254: Technical Assistance for Economic Empowerment
27 | Publication of Economic Empowerment Component Design | Donor, UNDP, Local Partners | Knowledge Sharing Document that reflect the QE Strategy | Book |  | UNDP Website, Fakhoora.org | one-time | December | TBD | Planned
3 | Deliverables
28 | Success stories (human interest / impact oriented) | Media | Reflect success of the Programme and reflect on programme achievement. | Interviews | 24 success stories | UNDP website | two per month | First week for each month | January - December | In progress | 24
|  | Donors |  | Photos |  | Donor website
|  | Government |  | Progress reports |  | Social media
|  | UNDP |  |  |  | Annual reports
29 | Inspire Conference | Media, Donor, UNDP | Reflect Leadership Art of Faciliation and Dialogue act | Documenntary and Promos | 1 Documenntary | Website, Social Media | one time | January | February | Completed | 1
30 | Profile Documentaries | Media, Donor, UNDP | reflect Students engagment with the activities | Promos | 5 Profile Vedios | Website, Social Media | one time | March | December | In progress, 3 Completed | 5
31 | Thank You Book – Messages from Student’s and their families that highlights the impact of DF on their lives. | Media, Donor, UNDP | Showing the impact of DF on students lives | Book | A Book to be produced both Online and hard copy with Portraits of about 100 DF student’s families that reflects the impact of the programme in their lives. | Website, Social Media | one time | March | March | Completed | 100
32 | Diary | Media, Donor, UNDP | increase the visibility of Dynamic Future programme among the public | Diary | 1000 Agendas to be distributed to the students and the local community | Website, Social Media | one time | March | March | Completed | 1000
33 | Office Calendar | Media, Donor, UNDP | increase the visibility of Dynamic Future programme among the public | Calendar | 1000 Agendas to be distributed to the students and the local community | Website, Social Media | one time | March | March | Completed | 2000
34 | Brochure | Media, Donor, UNDP | increase the visibility of Dynamic Future programme among the public | Brochure | 500 Brochure to be distributed to the stakeholders. | Website, Social Media | one time | October | TBD | In progress | 500
35 | Press Statements | Media | Reflect success of the Programme and reflect on programme achievement. | Interviews | 3 Press Statements | UNDP website | Occasionally | TBD | January - December | In progress | 3
|  | Donors |  | Photos |  | Donor website
|  | Government |  | Progress reports |  | Social media
|  | UNDP |  |  |  | Magazines
36 | Press Release | Media | Reflect success of the Programme and reflect on programme achievement. | Photos | 5 Press Releases | UNDP website | Based on the Programme key events | Based on the events schedule | January - December | In progress, 3 Completed | 5
|  | Donors |  | Progress reports |  | Donor website
|  | Government |  |  |  | Social media
|  | UNDP |  |  |  | Magazines
|  | Students in Qatar |  |  |  | Reports
37 | Al Fakhoora Journey – Triggering 4 years Documentary | Media | Reach out and reflect on programme achievement. | Documentary | One 4 years Documentary that will highlight the journey of 2 students through the 4/5 years of their study. | UNDP website | One Time | April | TBD | In progress | 1
|  | Donors |  | Progress reports |  | Donor website
| Stage ONE | Government |  |  |  | Social media
UNDP
38 | We Shift Documentary | Media | Showing the impact of DF on students lives | Documentary | This is a Documatry to show three stories of Al Fakhoora Alumni and how the Programme changed their lives | UNDP website | One Time | April | April | Completed | 1
|  | Donors |  | Progress reports |  | Donor website
|  | Government |  |  |  | Social media
UNDP
39 | Developing Infographics for DF, for the different component of the programme | Media | Visualizing the programme components | Photos | 6 Infographics that tell the journey of students through the programme | UNDP website | One Time | October | TBD | In progress | 10
|  | Donors |  | Progress reports |  | Donor website
|  | Government |  |  |  | Social media
UNDP
40 | 5th Graduation documentary | Media | Reach out to the local and International Community and show case of Al Fakhoora Model of Success | Photos | One (2-3 minutes) Documentary | UNDP website | One Time | February | February | Completed | 1
|  | Donors |  | Progress reports |  | Donor website
|  | Government, and UNDP |  |  |  | Social media
41 | 6th Graduation documentary | Media | Reach out to the local and International Community and show case of Al Fakhoora Model of Success | Photos | One (2-3 minutes) Documentary | UNDP website | One Time | October | 15.10.2019 | Planned | 1
|  | Donors |  | Progress reports |  | Donor website
|  | Government, and UNDP |  | Documentary |  | Social media
42 | Starts DF Students platform | Donor, Mass Media, Local and International Community including universities, | Reflect DF news, achievements of different components of Dynamic Futures by highlighting student’s initiatives, voices. | Dynamic platform that will be feeded from the above content – which also will be communication channel with the public | To be updated by middle of each month | Email and using stories in PAPP website and Fakhoora.org | one time | December | TBC | Planned | 1
43 | Professional photography | Donors | Human faces behind | Progress reports | Updated image bank, documenting progress | UNDP and donor websites | As needed | January | December | In progress
|  | Media | resilience | Beneficiary listings |  | Social media
|  | UNDP |  | Interviews |  | Exhibitions
Publications
44 | Banners and Rollups | Media | Reach out and reflect on programme achievement. | Photos | Visibility Materials to be used for different activities of the programme | UNDP website | One Time | January | December | In progress
|  | Donors |  | Progress reports |  | Donor website
|  | Government |  |  |  | Social media
|  | UNDP |  |  |  | Magazines
reports
45 | Internship Documentary and Two promos | Media | Reach out and reflect on the Internship Process achievement. |  | Visibility Materials to be used for different activities of the programme | UNDP website | One Time | May | May | Completed | 1
|  | Donors |  | Documentary |  | Donor website
|  | Government |  |  |  | Social media
UNDP