**UNDP Management Response Template**

**TERMINAL EVALUATION REPORT**

**GCCA+ Global Climate Change Alliance Suriname adaptation project** Date: 24 July 2020

Prepared by: Haidy Malone Position: Project Manager GCCA+ project Unit/Bureau: Environment and Natural Resources

Cleared by: Bryan Drakenstein Position: Head of Unit Unit/Bureau: Environment and Natural Resources

Management Programme

Approved by: Margaret Jones Williams Position: Deputy Resident Representative Unit/Bureau: Country office Suriname


Input into and update in ERC: Ruben Martoredjo Position: Programme Associate Unit/Bureau: Social Development/M&E Focal Point

**Overall comments:** Recommendations are intended for planned second Phase of the GCCA+ project. Climate Change has to be managed through a pluri- and cross sectoral approach due to its complexity. Services to manage and implement CC activities and projects are scarse; Climate activities in Suriname involve different ministries and local authorities. Good stakeholder engagement and continuous communication with government partners is also a key for a successful implementation; Regular inter-departmental discussion at policy and technical level could result improved coordination of national CC Adaptation initiatives.

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Evaluation Recommendation or Issue 1:**  Project design GCCA+ phase 2 |  |  |  |  |
| **Management Response:** |  |  |  |  |
| **Key Action(s)**  **. Start the design of phase 2 as soon as possible in order to prevent difficulties and**  **potential delays due to the next year elections and potential changes in the government**  **objectives and structure;**  **· Set targets coherent with timeframe and local conditions;**  **· Define clear roles and responsibilities among government and implementing partners;**  **· Allocate resources for maintenance of instrumental equipment;**  **. Gender mainstreaming needs to be clearly embedded from project design onward;**  **· Include more gender indicators for the outputs in the Logical Framework;**  **· Provide support to ensure the implementation of the IWRM, including establishment of**  **national water authority;**  **· Private sector should be more involved in the implementation of phase 2;**  **· Foresee protection from vandalism for instruments;**  **· Allocate resources for translation in Dutch but also in local languages for villages.** | **Time Frame**  **30 March 2021** | **Responsible Unit(s)**  Environment and Natural Resource Management Programme | **Tracking\*** | |
| **Status**  **Design of phase 2 completed** | **Comments**  **June 30, 2020** |
|  |  |  |  |  |
| **Evaluation Recommendation or Issue 2:**  **Project management and implementation GCCA+ phase 2** |  |  |  |  |
| **Management Response:** |  |  |  |  |
| **Key Action(s)**  **. Future projects need to be closely monitored by all parties involved (implementing and executing partners, project governance bodies) in order to establish if they are meeting with expected outputs and products;**  **· Take into account the difficulty to find local skilled experts, as well as international ones,**  **on Climate Change issues for the tendering procedures;**  **· Ensure proper data collection and sharing in usable formats;**  **· Ensure PMU will be fully operative at the beginning of phase 2;**  **· Independent evaluations are extremely valuable for course correction and catalyzing improvements. New evaluation, particularly at their mid-term, should be scheduled in**  **due time in order to be carried out and provide recommendations to be adopted during**  **the project implementation.**  **· When working with communities, underline the importance of economic benefits and/or create incentives for the communities and its members to incorporate sustainable management practices in their productive patterns.**  **- Expansion of visibility of the EU “GCCA+ Suriname”, clear branding within the GCCA+ global community.**  **-Ensure solid and strategic foundation for developing communication and awareness material.**  **-Regular sharing of photos, stories and case studies on GCCA+ Suriname for further disseminated through the EUD and European Commission (social) media channels** | **Time Frame**  **30 March 2022** | **Responsible Unit(s)**  Environment and Natural Resource Management Programme | **Tracking** | |
| **Status**  **In progress** | **Comments**  **Project has started as per agreed date, evaluation of level of completion planned during Midterm Evaluation** |

\* The implementation status is tracked in the ERC.

Prepared by: Cleared by: Approved by:

Haidy Malone Bryan Drakenstein Margaret Jones Williams

Project Manager Programme Specialist Deputy Resident Representative

Input into and update in ERC

Ruben Martoredjo

Programme Associate