Youth Employment and Empowerment through Private Sector and Value Chain Development

Agreement Number: 6003382

UNDP Project Number: 00113334

2020 Annual Report

February  2021

Responding to COVID-19 pandemic; A single mother and tailor engaged in facemask production at Yambio Vocational Training Centre, UNDP. 2020

| Project Summary | Country: South Sudan Project Duration: October 2018 – 31 December 2022 Project Budget: US$ 15,450,710 Annual Budget: US$ 4,582,117 Donor; Annual Budget in USD; Cumulative Expenditures. Netherlands; 3,431,067.00; 3,145,405.22. UNDP; 1,151,050.00; 1,090,992.39. TOTAL; 4,582,117.00; 4,236,397.61. Contact Persons: Samuel Doe Resident Representative Tel. +211 926 221 701 samuel.doe@undp.org Daniel Kir Team Leader Stabilisation, Recovery and Stabilisation (STARR) Tel. +211 920887780 daniel.kir@undp.org |
| --- | --- |
| Responsible Parties: Ministry of Labour, Ministry of Youth and Sport, Chamber of Commerce and Industry, State Governments (Central Equatoria, Western Equatoria, Eastern Equatoria, Lakes, Jonglei), collaborating UN Agencies, and Civil Society Organizations. |  |

# Table of Contents

Table of Contents	iii

Acronyms	4

Executive Summary	5

Situation Background	8

Progress towards development results	9

Progress towards project outputs	9

Youth Empowerment	16

Human Interest Story	19

Cross Cutting Issues	20

Gender Results	20

Partnerships	20

Environmental considerations	22

Strengthening national capacity	22

Risk Management	22

Challenges	23

Lessons Learned	24

Conclusions and way forward	25

Financial Summary	27

# Acronyms

| AU AWP B2B | African Union Annual Work Plan Business-to-business |
| --- | --- |
| CAPS | Career Advice and Placement Services |
| CPD GoSS | Country Projectme Document Government of South Sudan |
| HDIGU | Human Development and Inclusive Growth Unit |
| IDO | Integrated Development Organization |
| IDP | Internally Displaced Person |
| IOM MSE MTC | International Organization for Migration Micro- and small-scale enterprise Multi-Purpose Training Centre |
| M&E | Monitoring and Evaluation |
| PaCC | Peace and Community Cohesion |
| PBF | Peacebuilding Fund |
| PfRR | Partnership for Recovery and Resilience |
| PMSU | Partnership and Management Support Unit |
| PoC | Protection of Civilians site |
| TVET | Technical vocational education and training |
| UN | United Nations |
| UNCT | United Nations Country Team |
| UNDP | United Nations Development Projectme |
| UNICEF UNIDO UNMISS | United Nations Children’s Fund United Nations Industrial Development Organization United Nations Mission in South Sudan |
| VTC | Vocational Training Centre |
| YEEP | Youth Employment and Empowerment through Private Sector and Value Chain Development Project |

# Executive Summary

The Youth Empowerment and Employment through Private Sector and Value Chain Development Project (YEEP) is a four-year (December 2018-December 2022) project implemented by UNDP, with the support of the Royal Kingdom of the Netherlands and UNDP. The project seeks to empower youth in the five targeted locations of Central Equatoria (Juba), Western Equatoria (Yambio), Eastern Equatoria (Torit), Jonglei (Bor) and Lakes (Rumbek) through nurturing of their entrepreneurial culture and market-linked skills to enhance their employability and productive engagement in economic activities. The YEEP aims at contributing to the progressive transformation of South Sudan towards durable peace and sustainable development by supporting livelihoods trainings, infrastructure renovations and rehabilitations; re-establishing and improving institutions that can effectively serve the youth of South Sudan.

Implemented as part of the United Nations Country Team’s (UNCT) Interim Cooperation Framework, the joint United Nations (UN) Recovery and Stabilization framework and the UNDP Country Project Document (CPD) 2019-2021, the project collaborates with partners that include the Ministry of Labour, Ministry of Youth and Sport, Chamber of Commerce and Industry, State Governments, UN Agencies, and Civil Society Organizations.

The reporting period (2020) is the most challenging year of implementation for the Project so far. The onset of the COVID-19 pandemic severely disrupted project plans and hindered implementation processes with the lockdowns that were declared and the need to subscribe to COVID-19 mitigation and control protocols. Nonetheless, the COVID-19 pandemic also pushed the Project to be creative in the manner of which it conducts business, identifying opportunities where the Project is able to contribute positively towards the wider national effort on COVID infection prevention and control. Through a proactive and innovative manner of conducting business, the Project was able to achieve substantial results during the year and has enabled it to remain on track with regards to the realization of wider project results and impacts.

Main Achievements During The Year

Enhanced vocational, technical, and entrepreneurship skills training – The project successfully enhanced the skills of 5,407 youth (3,807 women) in at least 22 (sub)trades. Of the said number, 3,831 youth (84% women) were trained on community-based sustainable livelihood which focused on initiatives on agribusiness, food preparation, among other areas while the balance of 1,020 youth had their skill set developed through vocational training. At least 11 percent of those trained are ex-combatants.

Provision of employment and income:  A total of 1,961 youth were able to find employment and secure income through the support of the Project. The bulk of those employed (1,325 youth) were through the establishment and running of own businesses with the balance (636 youth) finding employment as carpenters, tailors, masons, hairdressers, etc.

Private sector development: The Project supported the expansion of the private sector and facilitated the formation of 60 micro and small enterprises, and the registration of 47 individual and 36 group businesses in agriculture, catering and hairdressing. The Project also facilitated the formation of 25 Village Savings and Lending Associations (VSLAs) that are currently operational and which are enhancing the income earning capacities of youths while also empowering them with savings capabilities to support future growth or expansion of their initiatives.

COVID-19 infection prevention and control:  More than a million face masks were produced and distributed to vulnerable persons. A total of eight facilities (3 in Juba and 1 each in Torit, Rumbek, Bor, Yambio and Aweil) were established for facemask production to allow for decentralized and increased facemask production and distribution. The facemask initiative is a primary intervention on COVID-19 infection prevention and control and was undertaken in collaboration with IOM, UNICEF, WFP, Office of the Vice President, and various state governments.

Informed and responsive project interventions:  Two crucial studies - Agricultural and Natural Resource Value Chain and Labour Market - were completed and are used to inform the value chains being established through the community-based livelihoods skills training and the vocational skills training that are on offer in the VTCs.

Challenges faced during the implementation period;

During the reporting period, the project faced several challenges that slowed the pace of implementation of activities at national and sub-national levels. These challenges are as follows:

- The Corona Virus (COVID-19) pandemic brought immense challenges in implementation as lockdown and movement restrictions hampered mobility, VTCs were declared closed, and trainings and other public and social gatherings suspended.

- The relaunching and conduct of the Labour Market and Agricultural Value Chain and Natural Resources Management studies under pandemic conditions delayed the identification of trades and livelihoods skills training to be offered to the youth.

- Delays in provision of start-up kits for the graduates/ trainees impacted on the timely graduation of trainees.

Lessons Learnt

Enhancing ownership and project delivery through partnerships: The engagement of implementing partners not only ensures the ownership of project initiatives but also boosts delivery and contributes significantly towards the achievement of project goals. By extension, it also builds the capacities of partners, enhances complimentarity between UNDP and local stakeholders and supports the empowerment of local institutions. The training of 4,851 youths in the midst of a pandemic is a significant achievement realized through the close cooperation and partnership with partners.

Responsiveness of community-based organization and operations: The engaged National NGOs quickly came to action as soon as COVID-19 restrictions were relaxed to enable the completion of trainings and eventual graduation of the first batch of the sustainable livelihood skills trainees. This was made possible because the national NGOs are all based in the state and are thereby able to easily mobilize and maneuver in the operational areas when the situation becomes viable.

Opportunism, flexibility, and realistic contingency planning: By identifying opportunities to leverage project activities and assets to support the COVID-19 pandemic response, and with the flexibility exhibited by the Donor (Netherlands) and the project team, a highly relevant and impactful response through the provision of facemasks  to service frontliners, vulnerable people, PWDs, etc. was embarcked on. By doing so, the project was not only able to mitigate the impact of the COVID-19 pandemic by contributing significantly towards infection prevention and control but also created income generating capacities for vulnerable women and trainees.

Budget Performance;

The total cumulative project expenditure for 2020 was US$ 4,236,397.61, representing 92 percent delivery of the total 2020 project budget of US$ 4,582,118.00.

# Situation Background

The Revitalised Agreement on the Resolution of Conflict in the Republic of South Sudan (R-ARCSS) of September 2018 laid the foundation for ceasefire and negotiations for a transitional political roadmap that led to the formation of the Revitalised  Transitional Government of National Unity (R-TGoNU) in February 2020 and brought hope and renewed impetus towards stabilizing the fragile situation in the country. Even so, South Sudan continues to face immense political, institutional, social and economic challenges which include the exclusion of youth, women, minorities and other special interest groups in livelihood initiatives that enable nation-building. The R-ARCSS provides the R-TGONU with a mandate to implement the agreement on the promise of no return to war; to reintegrate refugees and IDPs; to undertake legal and institutional reforms; and to develop national security architecture. It also offers special consideration to conflict-affected persons (children, orphans, women, people with special needs, etc.), in the public services delivery, including access to education services.

On 11 March 2020, the World Health Organization declared COVID-19 a pandemic. This declaration resulted in a quick and sudden global chain of events that did not spare South Sudan. By 16 March 2020, a presidential statement ordering the mandatory self-quarantine for travelers from countries with escalating confirmed cases, postponement of social gatherings, as well as, other preventive measures was issued. A national directive closing all schools, training centers, among other actions was decreed on 20 March 2020. With the threat lurking at the South Sudanese borders, the country closed its borders to travelers particularly its international airport and major border crossings with enhanced border controls on 23 March 2020. A national curfew was then imposed and remains in effect in the country.

The COVID-19 pandemic has brought with it a new normal in South Sudan despite having come with “a crisis on top of crises”. The pandemic is negatively impacting the multiple transitions that are ongoing in South Sudan; from war to peace to stability, humanitarian to development, and from pre-transition to transition phase in the implementation of the peace agreement. The socio-economic impact of the pandemic is widely evident. A palpable concern is shared by citizens with regards to COVID-19, cognizant of the limits of the health system that can be exacerbated by cultural practices on the sick and the deceased. Social distancing measures are not strictly observed despite the effort being made to raise awareness on preventive and mitigation measures. Food prices have escalated as movement restrictions make it more difficult for logistics in this landlocked country to flow and businesses have closed and many people who are daily wage earners have lost jobs and income. Moreover, basic protective materials like face masks which are a major factor in controlling and preventing the spread of the virus were in short supply and with prices inflated by several folds due to the sudden spike in demand during the start of the pandemic.

UNDP’s efforts through the project are anchored in the United Cooperation Framework (UNCF), the Partnership for Resilience and Recovery (PfRR) and the UNDP Country Project Document (CPD) 2019-2021. It specifically responds to the CPD’s Pillar II: ‘Inclusive and risk-informed economic development’ where the implementation strategy is embedded within the UNCT’s project criticality principles of addressing the immediate needs of the conflict-affected population, as well as, build the foundations for early recovery. The project responds to the COVID-19 pandemic through the production and distribution of face masks and the sanitation of various government buildings.

The project seeks to engage the youth to ensure their productive capacities are enhanced through the nurturing of their livelihood and employable skills inorder to improve their economic well-being and contribute towards the achievement of resilience and peaceful co-existence among youth in and around targeted areas in South Sudan (impact). The realization od the intended impact isusing using a two-pronged outcome approach in its theory of change:

- If local private sector enterprises, agricultural and natural resource -linked value chains and services for young men and women are enhanced then new business and income generating opportunities will be created whilst productivity and labour absorptive capacities of new and existing local private sector enterprises and value chains will be boosted (outcome 1).

- If the youth are provided with vocational, technical and entrepreneurial skills, psychosocial and business management advisory support then the employability and engagement in economic and livelihood initiatives and productivity and incomes for young men and women in targeted areas will be increased (outcome 2).

# Progress towards development results

## Progress towards project outputs

Project Output 1.1: Young men and women in Bor, Jubek, Rumbek, Torit, Bentiu, Aweil and Yambio are provided with vocational and entrepreneurial skills

Summary achievement against 2020 Annual Work Plan (AWP) target

| Indicator | Target (2020) | Summary achievement | Status |
| --- | --- | --- | --- |
| 1.1.1 Number of enrolled youth that complete the vocational, technical and entrepreneurship skills training, disaggregated by gender and location | 1,600 | 4,851 youth (3,388 women) completed vocational, technical and entrepreneurship training. | Achieved |
| 1.1.2 Proportion of young entrepreneurs utilizing innovation centers, business incubators and development hubs for skills enhancement | 50% | 60% (30 of the 50) of young entrepreneurs seconded to the Tony Elumelu Foundation at beginning of year benefited from global mentoring and networking. 79% of youth provided with entrepreneurship training as part of the training program. | Achieved |
| 1.1.3 Proportion of youth previously involved in conflict recruited for skills training | 20% | 11% of the youths enrolled for skills training were previously involved in conflict | Partially achieved |
|  | Overall status |  | Ongoing |

Youths training in Welding and Metal Fabrication in Yambio, Nov. 2020

Baking trainees during a lesson in Torit, September 2020, UNDP

Indicator 1.1.1: Number of enrolled youth that complete the vocational, technical and entrepreneurship skills training, disaggregated by gender and location

A total of 5,407 youth (3,807 women) were enrolled in various skills training including vocational, technical and entrepreneurship. Of the number of youth enrolled, 90 percent            (4,851 youth) were able to complete the training courses. About 21 percent (1,020 youth) – with a 71 percent completion rate – finished the institution-based vocational training across 22 sub-trades (automotive, carpentry, joinery,  electrical, solar and photo-voltaic installation, welding, masonry, painting, tiling, etc.). The completion rate was affected by the prolonged COVID-19 lockdown which reduced the interest of youth undergoing instruction to continue the training. The remaining 79 percent of trained youth (3,831 youth) – and a completion rate of 97 percent - acquired the necessary skills on agriculture and natural resource value chain and entrepreneurship covering seven trades (apiculture, food preservation and processing, housekeeping, food preparation, bakery and dairy processing).  The high completion rate was due to the fact that with the training conducted in the communities, it is more accessible to the targeted beneficiaries/trainees.

Western Equatoria and Central Equatoria registered the most number of trained youth with 1,351 (67% women) and 1,346 (67% women), respectively. The states of Lakes, Central Equatoria, and Jonglei were able to train 900 (89% women), 855 (55% women), and 99 (15% women) youths during the resporting period. The 99 youths trained in Jonglei were wholly through institution-based vocational skills as community-based agriculture and natural resource value chain skills could not be undertaken due to the massive flooding and displacement that occurred in the state. Due to delays and limitations brought about by the COVID-19 pandemic, the bulk of the youth who completed the training are slated for graduation and distribution of start up kits in the first quarter of 2021.

To further boost the delivery of vocational skills training to the youth, the engineering assessment of Rumbek VTC was conducted and the procurement process initiated for the engagement of a contractor to rehabilitate the said facility following the State Government’s confirmation that it has secured operational control of the facility. The complete rehabilitation of Rumbek VTC is slated to be completed by the second quarter of 2021 and will bring to a total five the VTCs in operation for the YEEP Project.

Indicator 1.1.2: Proportion of young entrepreneurs utilizing innovation centers, business incubators and development hubs for skills enhancement

Of the 50 youth entrepreneurs facilitated to benefit from global coaching, mentoring, and networking through the partnership between UNDP and the Tony Elumelu Foundation (TEF), 30 youth entrepreneurs (60%) successfully completed the training in the first quarter of 2020. The 3,831 youth who completed the community-based agriculture and natural resources value chain skills training program benefited from the provision of entrepeneurship and business development support.

The Project managed to complete two online portals (business portal and employment portal) which are meant to initiate e-commerce and digitize the aspect of job placement and recruitment. The Employment Portal is hosted by the Ministry of Labour and is linked to business networks and the Chamber of Commerce inorder to raise the level of accessibility and transparency of jobs to the youth. On the other hand, the Business Portal is made part of the e-commerce initiative of the Ministry of Trade and Industry and features an effective means of business networking and linkaging towards trade enhancement.

Two workshops built in VTC Bor, UNDP, 2020)

The Integrated Business, Employment, and Innovation Hubs (iHubs) in Torit, Yambio, Bor, Rumbek and Juba received materials and equipment (furniture and ICT equipment) to allow for the start of activities in early 2021. Juba, Rumbek, and Bor iHubs are under construction and slated for completion in the second quarter of 2021. All hubs will be linked to the two online portals (business portal linked with the business and e-commerce initiative  - hosted by the Ministry of Trade and employment portal linked with business networks - hosted by the Ministry of Labour) which are meant to provide remote support to businesses and job seekers. Young entrepreneurs and private sector businesses registered with the Chamber of Commerce are likely to benefit from the linkages and relationship building to be promoted by the portal.

Indicator 1.1.3: Proportion of youth previously involved in conflict recruited for skills training

Despite challenges in collecting this sensitive data, the Project was able to identify 569 persons previously involved in conflict to be amongst the beneficiaries of the project. This number represents 11 percent of those enrolled for training. Vulnerable groups (including Internally Displaced Person (IDP)s, returnees, former soldiers/ fighters, Children Associated with Armed Forces and Armed Groups (CAAFAGs), as well as, women associated with armed forces are also benefiting from the trainings.

Project Output 1.2: Technical Vocational Education and Training (TVET) and university graduates have increased access to career development and employment opportunities

Summary achievement against 2020 AWP target

| Indicator | Target (2020) | Summary achievement |  | Status |
| --- | --- | --- | --- | --- |
| 1.2.1 Number of skills training graduates that secure jobs from UNDP-supported private sector enterprises and value chains disaggregated by gender | 450 |  | 1,438 graduates (1,400 females) skills training graduates engaged in gainful livelihood activities. Total of 1,961 jobs/employment created. | Achieved |
| 1.2.2 Proportion of tertiary education students in the targeted locations receiving career guidance and mentoring through Career Advice and Placement Services (CAPS), disaggregated by gender | 30% | 3 hubs constructed and all 5 hubs equipped to start supporting CAPS |  | Delayed |
| 1.2.3 Number of jobs traded through jobs fairs | 150 | None as job fair could not be conducted due to COVID-19. 523 jobs created thru COVID-19 pandemic response. |  | Delayed |
|  | Overall status |  |  | Ongoing |

Indicator 1.2.1 Number of skills training graduates that secure jobs from UNDP-supported private sector enterprises and value chains disaggregated by gender

A total of 1,438 youth who graduated from the skills training courses were able to find employment and income either through the establishment of own businesses or employment in existing companies. At least 113 (74 females) vocational skills training graduates secured jobs from private enterprises and were engaged in carpentry, masonry, hairdressing, food preparation and processing among others. An additional 523 jobs were created through the project’s COVID-19 pandemic response bringing the total number of jobs created/supported under the project to 1,961.

With a source of income, graduates are able to enhance their resilience to shocks. The project is also following up on the 44 organisations that underwent screening (due diligence exercise) inorder to engage the said organizations in the enterprise-based training (internship) and asset-linked job placement.

Indicator 1.2.2 Proportion of tertiary education students in the targeted locations receiving career guidance and mentoring through Career Advice and Placement Services (CAPS), disaggregated by gender.

The project was not able to provide CAPS due to the suspension of job fairs given the high level of risk associated with the spread of the COVID-19 virus. In preparation to the conduct of this service once trainees were graduated, the project initiated the construction of integrated business, employment, and innovation hubs (iHubs) in Bor, Rumbek, and Juba (Yambio and Torit were completed in 2019) and procured and delivered furniture and ICT equipment (50 top-of-the line desktop computers, 5 printers, 5 public address systems, 5 LCD projectors and screens, and 5 generators) that will be utilized in the delivery of the said services in 2021.

Indicator 1.2.3 Number of jobs traded through jobs fairs

The planned conduct of the massive job fair in Juba was not conducted due to the advent of the COVID-19 pandemic and the extremely high reputational and health risk such an activity brings towards furthering infection rates and non-subscription to global protocols on COVID-19 infection prevention and control. Nonetheless, the project successfully explored opportunities in the COVID-19 pandemic to create jobs that resulted to the engagement of 523 vulnerable persons (78% women) in the production of face masks.

Through a special intervention by the project that leveraged the assets (VTCs, machines, etc.) and human resources (trained youth) under it, a massive production initiative on face mask production was embarked on and serves as a major contribution towards the national effort on COVID-19 infection prevention and control. A total of 1,023,847 units/pieces of face masks were produced and distributed to the frontliners, security personnel, vunerable persons, persons with disabilities, etc. protecting them from the spread of the deadly disease.

Project Output 2.1: Young men and women in targeted areas benefit from jobs, livelihood and income-generating initiatives created through strengthened private sector enterprises and local value chains

Summary achievement against 2020 AWP target

| Indicator |  | Target (2020) |  | Summary achievement | Status |
| --- | --- | --- | --- | --- | --- |
| 2.1.1 Number of new jobs created through value chains and private sector enterprises supported by UNDP |  | 600 | 1,432 new jobs were created by skills training graduates who established private businesses within the agriculture and natural resource value chains. 107 new jobs were created by the expansion of these businesses. |  | Achieved |
| 2.1.2 Number of new MSEs created by supported youth |  | 40 | 60 new MSEs were formed. In addition, 36 cooperative groups have been established and 25 VLSAs formed. |  | Achieved |
| 2.1.3 Proportion of trained youth engaging in livelihood and income-generating activities (individually or in groups) |  | 30% | 35% of the trained youth graduated, received start-up kits, entrepreneurship training and running their own businesses. |  | Achieved |
| 2.1.4 Number of youth-oriented facilities benefiting from clean energy solutions |  | 4 | 4 VTCs are already supported by a renewable energy source (2019). |  | Achieved |
|  | Overall status |  |  |  | Ongoing |

Indicator 2.1.1 Number of new jobs created through value chains and private sector enterprises supported by UNDP

Young women being trained on automotive maintenancein Rumbek, UNDP, 2020

A total of 1,325 new jobs/employment were created by skills training graduates who got engaged and established businesses within the agricultural and natural resource value chains. The establishment of businesses is playing a significant role in recovery following the closure of businesses due to the COVID-19 pandemic. In the few months the said enterprises were operational an additional        107 new jobs were created with              63 percent of those jobs filled by women workers.

Additionally, the project managed to conduct the Agricultural and Natural Resources Value Chain study and the Labour Market Study despite the constraints due to the pandemic. Following COVID-19 protocols and utilizing digital and mobile technology, the studies were completed in all 5 states and informs the type of support that the project will provide toward enhancing agricultural value chain and private sector actors in the project implementation areas in 2021. Furthermore, the study will inform the jobs and job types that will be created by the various agricultural trade and crops that are worth investing in.

Indicator 2.1.2 Number of new micro- and small-scale enterprises (MSEs) created by supported youth

The Project was able to formally support the establishment and registration of 60 new MSEs with the local Chambers of Commerce. These new MSEs will lead local economic recovery and will be the center for the provision of business development services to ensure their continued operation and sustainability. It also raises the cumulative number of MSEs established, registered, and supported under the project to 86 MSEs.

Indicator 2.1.3 Proportion of trained youth engaging in livelihood and income-generating activities (individually or in groups)

Of the 3,831 youth that completed the community-based agriculture and natural resource value chain trainings, approximately 35 percent (1,325 youth) engaged in livelihood and income generating activities following graduation and provision of start-up kits and entrepreneurship training. The remaining 65 percent of trained youth will be graduated and

supported in the establishment of their businesses in early 2021.

Significantly, the project was also able to organize the at least 360 individual businesses into 36 cooperative groups to enhance the viability of said private enterprises through business complementation and organized support. The project also managed to form 25 Village Loan and Savings Association (VSLA) that involved 500 businesses inorder to develop a saving culture while providing members with access to financing for business operation and expansion.

Indicator 2.1.4 Number of youth-oriented facilities benefiting from clean energy solutions

The three VTCs in Bor, Torit, and Yambio which were previously (2019) equipped with solar panels continue to operate and are using the said energy source in providing lighting and power for the administration and classroom blocks. Moreover, the boreholes of all the three VTCs are powered by wind and solar energy and this has minimized environmental pollution including those associated with oil spillage, carbon emission and sound pollution that may arise from the use of fossil fuels during the operation of generators. Unfortunately, solar power was not included in the renovation of Rumbek VTC and the construction of Juba iHub due to budgetary limitations.

# Youth Empowerment

A key thrust and component of the Project is the aspect of youth empowerment. During the reporting period, the Project was able to conduct four youth engagement forums – two in Yambio, 1 in Juba, and 1 in Torit - that saw the engagement of 575 youth (180 females). These engagements were not only confined amongst the youth groups inorder to establish coherence, proper articulation of concerns, and organization in finding solutions to the challenges confronting the youth but, more importantly, with the State leadership (Governors) and senior officials at national and continental levels. Through the engagement with national and state leaders, the youth were able to express the unique issues and concerns confronting them and in such manner advocate for their representation and involvement in decision-making processes.

The engagements also revolve around relevant issues that not only affect the youths but also necessitate their support.  An example is the support to the activity on garnering the youths’ commitment to the formation of the RTGoNU wherein engagement between leaders, youths from “town” and youths from the IO areas of Yambio committed to supporting the expected new crop of leaders.  Through such initiatives, youths from IO areas not only voiced their commitment to peace but also requested livelihood support as their town counterparts had access to.

The Project also organized the visit of the African Union Youth Envoy, HE Aya Chebbi, to South Sudan on the occasion of the celebration of the Africa Youth Month. The high-level visits to Rumbek and Juba allowed the AU Youth Envoy to hold discussions with youth orgaizations and the national leadership and championed the concerns of the youth and in articulating such in continental frameworks,plans, and priorities.

As can be noted, a key feature of the Project is the integration of life skills, human rights, and literacy in the delivery of the vocational sills training to the youth. This deliberate approach of the Project to incorporate these modules into the standard vocational skills training course is borne out of the unique challenges faced by youth on the ground (illiteracy, lack of appreciation of human right, conflict background, etc.). Through these efforts of ensuring holistic interventions, the Project is working at not only enhancing the technical skills of the youth that would make them economically productive, but also improving on their social behavior and understanding to enable the youth to be better citizens of citizens, respectable of their and the rights of others.  These efforts help develop a crop of youths who are active partners in economic recovery and social stability but also in rebuilding the country’s social fabric to contribute to community resilience building.

# Human Interest Story

Applying Sustainable Livelihood Skills Training to Practice- From  Student to Business Owner

Sophia preparing to serve her guests tea, photo by UNDP, July 2020

Sophia Yom Dhokpou, 32, is a mother of five, who lives with her family in Akuac, a residential area in Rumbek. She holds a High School certificate. Due to financial constraints she could not further her studies at tertiary level.

She first heard of the sustainable livelihoods training opportunity via a radio advertisement in November 2019 and she decided to enroll.  She thought of challenges faced by her family which is depending on government salary which at times can take ages to be paid. Her family supported her when she decided she wanted to enroll for the Food Processing course. Her dream of forming her own business was a step away.

Diligently, she attended all sessions. The coming of COVID-19 almost spoiled her dream. “I was frustrated when our training came to an indefinite close. However, the knowledge and skills I gained in Business Management and the three-week food processing training were eye-opening.  With the support I got from my husband, I started a tea place where I sell tea and make quality bread and mandazi."

Sophia admittedly said that the tea business is rewarding. She got a range of customers from young children to adults. She uses her income to support her family." I used to depend on my husband for almost everything. But now, I have reduced his burden. My needs and those of children are no longer the problems." said Sophia. She said when schools re-opened, she could pay her children’s school fees .

Sophia believes that she has gained appropriate skills necessary to make fresh food and cakes. What thrills her so much is her ability to make birthday and wedding cakes.

Sofia confessed that before she joined the training, she used to face a lot of financial-related challenges, and sometimes it could be very difficult to put the daily bread on the table for her family. "...I make an average of 28,000 South Sudanese Pounds per week. It is an enormous sum of money if I could save most of it. But due to overdependence of other close family members, I save a little money."

After the graduation, she received a startup kit. Sophia plans to maintain her business but would venture into a restaurant business with a group of women. She has gained  respect from her community. Some men encouraged their wives to take her as their role model so that her success can inspire them.

Sophia saves in a VSLA group at their residential area and her ambition is to open her restaurant next year with the savings she would have accumulated then.

# Cross Cutting Issues

## Gender Results

| Gender results | Evidence |
| --- | --- |
| Gender result 1: Increased access to emergency assistance, alternative livelihood and employment opportunities for families in conflict and disaster-prone communities. 1,545 (95% women) persons gainfully employed in various trades. 523 (78% females) for facemask initiative. | Evidence 1: Project reports. |
| Gender result 2: Young men and women in Bor, Jubek, Rumbek, Torit, Bentiu, Aweil and Yambio are provided with vocational and entrepreneurial skills 4,851 (3,388 women) completed vocational, technical and entrepreneurship training in Juba, Torit, Bor, Rumbek, and Yambio . | Evidence 1: UNDP field staff reports, Implementing partners reports. |
| Gender result 3: Young men and women in targeted areas benefit from jobs, livelihood and income generating initiatives created through strengthened private sector enterprises and local value chains. 1,961 (92% females) youth benefit from jobs, livelihood and income generating activities | Evidence 1: UNDP field staff reports, |

## Partnerships

The YEEP is within the Recovery and Resilience Programme of the Stabilization, Recovery, and Resilience (STARR) Team/Unit of UNDP South Sudan.

Projects within UNDP: The Project collaborates and works closely with projects and units within UNDP.  For example, the project is leading in face masks production and is partnering with Access to Justice and Rule of Law (A2J/ RoL) and the Peace and Community Cohesion (PACC) on production and distribution. A total of 1,023,847 face masks were produced and distributed to service frontliners, vulnerable people, persons with disabilities, etc. The project is also partnering with the Accelerator Lab in following up with the innovation challenge winners in development of prototypes and testing of inventions.

UN Agencies: The Project also collaborates and works closely with other UN agencies in project implementation. UNIDO is a sub-recipient under the YEEP for the provision of vocational and entrepreneurial skills. UNICEF, UNMISS, IOM and WFP partnered with UNDP on the COVID-19 pandemic response through the face mask production and distrbution which is a key intervention for infection prevention and control.

Local NGOs: The Project works closely with local NGOs in the provision of sustainable livelihood skills training in the following locations: Yambio (Star Trust Organisation- STO), Torit (Action for Recovery and Transformation- ART), Wau (RCDI) and Rumbek (Vocational Skills Development Organisation- VOSDO). The local NGOs worked on an accelerated delivery plan for completion of the women’s sustainable livelihoods training that graduated 1,585 women from the four mentioned states.

Government: UNDP works closely with the Government of South Sudan (GoSS). For the conduct of the vocational skills training, the program works in close cooperation with the Ministries of Labour, Youth , Agriculture and Education both at national and State levels. The Project works also in close collaboration with local authorities such as the State Government and municipal authorities, as well as, the Vocational Training Centres. The Project  is also working with the COVID-19  reponse task forces at national and state level.

Partnership for Recovery and Resilience (PfRR): The Project is working on the recovery and resilience front through its active involvement and engagement in the Partnership for Recovery and Resilience. At the national level, UNDP is a member of the Joint Analysis, Monitoring and Measurement Group (JAMMG), the Technical Advisory Group (TAG) as well as the communication task force. At the local/ state level, in Yambio, UNDP is the co-lead for Pillars 1 and 4, while it is also a member of Pillar 3 of the PfRR. It also acts as the Secretariat for the UN Joint Project for Recovery and Resilience in Yambio.  In Torit, UNDP acts as the Secretariat together with United Nations Mission in South Sudan (UNMISS).

Vulnerable community members benefiting from facemasks, (July 2020, UNDP)

## Environmental considerations

The Project thrives to ensure compliance with UNDP environmental policies and standards. The construction and rehabilitation works underwent environmental impact assessments to minimize damage to the environment. It also ensured that no existing trees were cut during the implementation. Most construction wastes like cement bags were collected and disposed off by contractors away from site to designated disposal points in an enviromentally friendly manner.

The Project made use of existing structures for facemask production initiative thereby ensuring environmental sustainability and friendliness. Avoiding the use of plastics, recycled food carton boxes were used instead for packaging and storage ofproduced face masks. The Project’s renovated VTCs have installed solar panels and wind powered boreholes for enhanced environmental sustainability and adoption of clean energy initiatives.

## Strengthening national capacity

| Results achieved | Institution | National capacity strengthened |
| --- | --- | --- |
| - Private sector enhancement | Ministry of Trade and Industry, Chambers of Commerce | Online business portal to facilitate e-commerce and enable business linkages given COVID-19 protocols. New MSEs established enhances private sector development at local level. |
| - Improved monitoring and reporting capacity | CSOs | Technical support towards monitoring and report writing. |
| - Provision of vocational skills trainings | Ministry of Labour | Provision of equipment and tools to expand vocational skills offering in Torit, Bor, Juba and Yambio. Standarized delivery and assessment of vocational skills development. |

# Risk Management

| Risks | Mitigation Measures |
| --- | --- |
| Political: Changes in political leadership may impact the commitment to and ownership of projects by local governments. | The project continues to work closely with all levels of government to ensure ownership that is not depending on individual leaders. |
| Security: The recommencement of hostilities could prevent or hinder implementation of project activities as well as access to project locations. | UNDP will continue to make contingency plans. The project is focused on hubs of peace and supports stabilization and resilience. |
| Financial: Lack of access to micro-financing can hinder the successful establishment and running of businesses by beneficiaries trained by UNDP. | UNDP encourages innovative thinking and communal support mechanisms such as VSLAs. |
| Operational: Delays in operational issues, such as procurement of start-up kits, may depress the benefits of the project for trained beneficiaries. | UNDP will continue to prioritize the acceleration of procurement processes and other operational issues that may delay project activities. |
| Health/Environmental: Delays and stoppage in project implementation due to the COVID-19 pandemic. | UNDP will continue monitoring trends and adjust implementation plans and targets following WHO and CDC protocols and guidelines. |

# Challenges

The main challenges affecting the implementation of projectme activities are mainly of an operational nature. Below are the key challenges and the actions taken:

- The Corona Virus (COVID-19) pandemic brought immense challenges in implementation as the Government and partners shuttered training institutions, suspended the conduct of trainings and public gatherings, imposed movement restrictions, among others.

Action: The project adapted to the measures and guidelines introduced by the government by proactively engaging with partners and identifying opportunities (like face mask production) that resulted to employment generation, opening of the VTCs, and provision of income to vulnerable population.

- Delays in the conduct of the Labour-Market Sutdy and the Agricultural Value Chain and Natural Resources Management Study. The initial firm engaged to conduct the studies backed out and COVID-19 movement restriction imposed severe constraints in the conduct of the studies.

Action: UNDP immediately relaunched the procurement process, engaged a new firm and utilized digital and mobile technologies in the conduct of the study and which resulted to its completion.

- Delays in completion of the first batch of vocational skills training. This was caused principally by the delays in identification of training offerings on additional trades (UNIDO identified with the VTCs) as well as the COVID- 19 restrictions which required the suspension of trainings and closure of training centres.

Action: UNDP engaged partners to resume trainings which can be conducted in smaller numbers observing social distance and other COVID-19 protocols. The partners also developed plans for resumption of trainings in liason with state level authotities as guided by local state COVID-19 task forces.

- Significant number of trainee drop-out due to VTC closure and suspension of training that dampened the interest and enthusiasm of the youth to underog the trainings.

Action: UNDP and partners mobilized massively and engaged with the trainees to bring back interest and allow them to return upon recommencement of vocational skills training.

# Lessons Learned

Enhancing ownership and project delivery through partnerships: The engagement of implementing partners not only ensures the ownership of project initiatives but also boosts delivery and contributes significantly towards the achievement of project goals. Training                    4,851 youths in the midst of a pandemic is a significant achievement realized through the close cooperation and partnership with five implementing partners.

Responsiveness of community-based organization and operations: The engaged National NGOs quickly came to action as soon as COVID-19 restrictions were relaxed to enable the completion of trainings and eventual graduation of the first batch of the sustainable livelihood skills trainees. This was made possible because the national NGOs are all based in the state and are thereby able to easily mobilize and maneuver when the situation becomes viable.

Opportunism, flexibility, and realistic contingency planning: By identifying opportunities to leverage project activities and assets to support the COVID-19 pandemic response, and with the flexibility exhibited by the Donor (Netherlands) and the project team, a highly relevant and impactful response through the provision of face masks  to service frontliners, vulnerable people, PWDs, etc. was embarcked on. By doing so, the project was not only able to mitigate the impact of the COVID-19 pandemic by contributing significantly towards infection prevention and control but also created income generating capacities for vulnerable women and trainees.

# Conclusions and way forward

The project has exceeded the achievement of most targets despite several major challenges brought about mainly by the COVID-19 pandemic. This year tested the mettle of UNDP and demonstrated its ability to re-focus and calibrate its interventions on strengthening the private sector and facilitating employment for the youths. Exceeding its set annual targets, the project is a testament to the flexibility of the donor (Netherlands) and the adaptability of the project team and partners to not be deterred but instead use the challenge of the pandemic as an opportunity to make a significant contribution towards infection prevention and control while creating employment opportunities and continuing skills development. The face mask initiative was able to assist local tailoring businesses which were otherwise significantly affected by the economic lockdown as well as youths whose training sessions were disrupted to engage in productive, paid livelihoods while contributing to the disease’s mitigation.  As the production team was community based, in many areas, it was composed of people from several groups - local tailoring businesses, start-up tailors, tailoring trainees, demobilized youths who trained in tailoring, refugees, among others- bringing communities together towards a common cause.

The pandemic compelled UNDP and the project to shift its mode of implementation and to increasingly tap on digital and mobile technology to deliver on project activities. Video-conferencing and telephony has made it possible to gather data, undertake consultations , and coordinate activities while subscribing to COVID-19 protocols on social distancing and hurdling restrictions on movement.  The conduct of the Labour-Market and Agriculture and Natural Resources Value Chain Studies proved very challenging but provided a lot of experience and lessons that the project team was able to build on. The use of digital technology created links between local CSOs and UNDP’s service provider through which CSOs worked in tandem  with the service provider through virtually guided interactions.  These not only enabled the facilitation of the studies despite the limits of the pandemic but also created opportunites for capacity building for the CSOs and advancing the utilization of digital tools.

Considering that a new normal has evolved, the project will need to ensure its relevance and focus on outcomes.  In this regard, the project will need to enhance its engagement and strengthen relations with state institutions and national NGOs, capitalizing on their presence and unique capacities on the ground to ensure continuity and sustainability of services and initiatives even beyond the project’s life. With the first cohort of vocational skills trainees graduated, and with two cohorts planned in 2021, there will need to be greater focus on channeling the trained youth towards jobs and employment opportunities. To this end, referral and job placements will need to be complemtned by the implementation of productive social safety net programmes inorder to create adequate employment opportunities and spur local economic revitalization.

The graduation of subsequent cohorts of trainees on community-based agriculture and natural resource value chain skills training will require greater business development support and organization (into cooperatives and VSLAs) as the private sector is expected to play a more crucial role driving the economic recovery of states following the pandemic. The integrated business, employment, and innovation hubs will be the primary platform using a range of technology and approaches to delivery these support services to the trained youth while cultivating innovative thinking.

The Labour-Market and Agriculture and Natural Resources Value Chain Study were completed towards the end of the year and findings shall inform and assist in calibrating the interventions under the project in the coming year to ensure the relevance and sustainability.  It shall also enhance the project’s endeavor to create a training and skills development market that is demand-driven and, in the longer-term with effective support to private enterprises.

The project is well on track of achieving many of its set targets (number of youth trained, number of youth employed, MSEs established, etc.) in 2021. Nonetheless, UNDP and the project team will not rest and will do its utmost to reach the highest numbers possible inorder to ensure that the benefits of the project are provided to as many vulnerable South Sudanese youth as possible. As the need for economic recovery from COVID-19, conflict, etc. looms and society works towards greater peace and stability, the role that this project will play in economic revitalization and youth empowerment gains more prominence. The COVID pandemic has and will likely continue to create challenges for the project, but as already proven in 2020, it also provides opportunities to strengthen implementation mechanisms and prime strategies on the ground inorder to improve on the achievement of project outcomes and the realization of intended impacts.

# Financial Summary

| Outputs / Activity Result |  | Annual Budget (US$) (Jan - Dec 2020) | Cumulative Expenditures | % of Expenditure |
| --- | --- | --- | --- | --- |
|  |  | A | B | B/A*100 |
| Output 1: 113334- Job & Employment creations through the development of inclusive value chains & private sector enterprises |  |  |  |  |
| Activity Result 1 | Vocational & Entrepreneurship for Youth | 2,309,685.00 | 2,485,060.93 | 107.59% |
| Activity Result 2 | TVET Development & Employment Opportunities | 1,084,207.00 | 790,579.64 | 72.92% |
| Activity Result 3 | Income Generating Initiatives | 533,223.00 | 32,921.02 | 6.17% |
| Activity Result 4 | Effective Project Management | 655,002.00 | 940,635.15 | 143.61% |
| Output 1 Sub-total |  | 4,582,117.00 | 4,236,397.61 | 92.41% |

The R-TGoNU was formed on 22 February 2020 after missing two deadlines, June and November 2019