

Government of Malawi

**MINISTRY OF CIVIC EDUCATION, CULTURE AND COMMUNINITY DEVELOPMENT**

**STRATEGIC PLAN**

**2016 - 2021**

# 

**TABLE OF CONTENTS**

[FOREWORD iii](#_Toc503515903)

[PREFACE iv](#_Toc503515904)

[ABBREVIATIONS AND ACRONYMS v](#_Toc503515905)

[EXECUTIVE SUMMARY vii](#_Toc503515906)

[**1.0** **INTRODUCTION AND BACKGROUND** 1](#_Toc503515907)

[1.1 Introduction 1](#_Toc503515908)

[1.2 Background to the Establishment of MoCECCD 1](#_Toc503515909)

[1.3 Rationale for the Development of the Strategic Plan 2](#_Toc503515910)

[1.4 Institutional Set-up of the Ministry 3](#_Toc503515911)

[1.4.1 Civic Education 3](#_Toc503515912)

[1.4.2 Arts 3](#_Toc503515913)

[1.4.3 Museums and Monuments 4](#_Toc503515914)

[1.4.4 National Records and Archives Services 4](#_Toc503515915)

[1.4.5 Community Development 5](#_Toc503515916)

[1.4.6 Administration and Management 5](#_Toc503515917)

[1.5 Alignment of MoCECCD Strategic Plan with National, Regional and International Development Policies. 6](#_Toc503515918)

[1.6 Strategic Plan Development Process 7](#_Toc503515919)

[**2.0** **THE STRATEGIC ANALYSIS** 9](#_Toc503515920)

[2.1 Overview 9](#_Toc503515921)

[2.2 MoCECCD Key Result Areas 9](#_Toc503515922)

[2.3 SWOT Analysis 9](#_Toc503515923)

[**3.0** **MoCECCD’s STRATEGIC DIRECTION FOR 2016 - 2021** 14](#_Toc503515924)

[3.1 Overview 14](#_Toc503515925)

[3.2 Mandate, Vision, Mission and Core Values 14](#_Toc503515926)

[**3.3** Key Result Areas, Strategic Outcomes and Outcome Targets 15](#_Toc503515927)

[3.4 Outputs and Annual Output Targets 18](#_Toc503515928)

[3.5 Strategic Plan Implementation Resource Requirements 40](#_Toc503515929)

[3.6 The Results-Based Logical Framework 41](#_Toc503515930)

[**4.0** **GOVERNANCE AND COORDINATION MECHANISMS FOR IMPLEMENTING THE STRATEGIC PLAN** 44](#_Toc503515931)

[4.1 Overview 44](#_Toc503515932)

[4.2 Institutional Arrangements for Implementing the Plan 44](#_Toc503515933)

[4.3 Roles and Responsibilities of Management 44](#_Toc503515934)

[4.4 Risks and Mitigation Measures 46](#_Toc503515935)

[**5.0** **CRITICAL SUCCESS FACTORS** 47](#_Toc503515936)

[5.1 Strategic Leadership 47](#_Toc503515937)

[5.1.2 Financial Resources 47](#_Toc503515938)

[5.1.3 Political Environment 47](#_Toc503515939)

[5.1.4 Supportive and Collaborative Stakeholders 47](#_Toc503515940)

[**6.0 MONITORING AND EVALUATION** 48](#_Toc503515941)

[6.1 Purpose and Scope 48](#_Toc503515942)

[**7.0 FINANCIAL RESOURCES MOBILIZATION** 48](#_Toc503515943)

[7.1 Rationale for Alternative Sources of Funding 48](#_Toc503515944)

[ANNEXES 49](#_Toc503515945)

[Annex 1: List of Members of the Planning Team 49](#_Toc503515946)

[Annex 2: List of Participants who participated in the Strategic Planning 50](#_Toc503515947)

[Annex 3: List of Reference Materials consulted 53](#_Toc503515948)

[Key Result Area: Civic Education 54](#_Toc503515949)

[Strategic Outcome 3: Improved resource mobilization for cultural development 58](#_Toc503515950)

[Strategic Outcome 4: Increased community participation in development projects and community based population education 59](#_Toc503515951)

# FOREWORD

The Ministry of Civic Education, Culture and Community Development was established in order to contribute towards the achievement of national development agenda through the provision of civic education, cultural and community development services. Government recognizes that the important roles played by civic education, culture and community development in society and the nation as a whole cannot be overemphasized; without national identity one is completely lost, development cannot take place in a nation when its citizenry are not empowered and when they do not have an understanding of the ideals of democracy and how government operates. It is therefore the responsibility of my Ministry to create an enabling environment where citizens actively participate in development initiatives.

There are a number of challenges that impinge the citizen’s contribution to the national development such as; high illiteracy rate, harmful cultural practices, loss of cultural identity, and lack of knowledge. In this regard, this Plan contains strategies that will contribute substantially to the vision of a nation that is well informed, culturally vibrant and empowered.

This Plan will guide implementation of my Ministry’s activities from 2016 to 2021 and has been developed in line with Government priorities as outlined in the Malawi Growth and Development Strategy (MGDS ) III which was developed as a medium term tool for attaining long term aspirations of our nation as spelled out in the Vision 2020. Furthermore, this Plan has been developed in line with Agenda 2030 for Sustainable Development and the Sustainable Development goals (SDGs).

The Strategic Plan is based on four Key Result Areas (KRAs) of Civic Education, Cultural Development, Community Development, and Administration and Management. Their functions are drawn from these KRAs which are operationalised by Departments of Civic Education, Arts, Museums and Monuments, National Records and Archive Services and Community Development.

Grace Obama Chiumia (M.P.)

**MINISTER OF CIVIC EDUCATION, CULTURE**

**AND COMMUNITY DEVELOPMENT**

# PREFACE

The Ministry of Civic Education, Culture and Community development has developed this Strategic Plan to provide direction and guidance in the implementation of its activities with the aim of making a substantial contribution to the national development plan. The Strategic Plan outlines measurable goals and will act as a tool upon which performance will be measured. It is therefore, expected that the implementation of the Strategic Plan will result into effective and efficient delivery of services. As required by any public institution, this Strategic Plan is in line with Government priorities aimed at contributing towards the reduction of poverty through sustainable economic growth and development.

The development of this Strategic Plan is a result of concerted efforts of various stakeholders from Public Institutions and Development Partners at different fora. The Strategic Plan has a lifespan of five years from 2016 to 2021. However, it may be reviewed in response to emerging issues.

The Ministry would like to express its gratitude to the task force and all the stakeholders who contributed to the development of this Strategic Plan. Special thanks should therefore, go to the Department of Human Resources Management and Development (DHRMD), National Initiative for Civic Education (NICE) Trust, Copyright Society of Malawi (COSOMA), United Nations Development Programme (UNDP), and United Nations Women for their financial assistance and technical guidance in the formulation of this plan.

Ivy J. Luhanga (Mrs.)

**SECRETARY FOR CIVIC EDUCATION, CULTURE**

**AND COMMUNITY DEVELOPMENT**

# ABBREVIATIONS AND ACRONYMS

ADC Area Development Committee

VDC Village Development Committee

AWP Annual Work Plan

CDA Community Development Assistant

COMSIP Community Savings and Investment Promotion

COSOMA Copyright Society of Malawi (COSOMA)

NCHE National Council for Higher Education

CSF Critical Success Factor

DC District Council

DHRMD Department of Human Resource and Management Development

GVH Group Village Headmen

IPSAS International Public Sector Accounting Systems

ICT Information, Communication and Technology

IEC Information, Education and Communication

KRA Key Results Area

MoCECCD Ministry of Civic Education, Culture and Community Development

MDAs Ministries, Departments and Agencies

MGDS Malawi Growth and Development Strategy

MPSR Malawi Public Service Regulations

NAHeC National Arts and Heritage Council

NICE National Initiative for Civic Education

NDP National Development Program

OAU Organization of Africa Unity

OPC Office of the President and Cabinet

PSIP Public Sector Investment Program

SDGs Sustainable Development Goals

SPIC Strategic Plan Implementation Committee

SWOT Strength, Weakness, Opportunities and Threats

TEVETA Technical Education, Vocational and Entrepreneurship Training Authority

ToRs Terms of References

UNDP United Nations Development Programme

VDC Village Development Committee

VSL Village, Savings and Loans

# EXECUTIVE SUMMARY

This is the first Strategic Plan that the Ministry of Civic Education, Culture and Community Development (MoCECCD) has developed to provide an operational guidance for the next five years from 2016 to 2021. The Plan translates the aspirations of its mandate into achievable actions and is aligned to MGDS III.

The development of this Strategic Plan follows the re-organization of Government Ministries, Departments and Agencies (MDAs) as announced in a Press Release on 5th September, 2016 which led to the establishment of MoCECCD, comprising three functional areas of Civic Education, Cultural Development and Community Development.

The development of the 2016 – 2021 Strategic Plan signifies the Ministry’s commitment to formulate a robust response to the implementation of its mandate by aligning its strategic direction and priorities with the emerging issues in Malawi. The Plan blends the desired state the Ministry would want to have, objective analysis of its Key Result Areas (KRAs) and the determination of desired outcomes and output targets.

The Plan identifies four KRAs namely: the provision of civic education, cultural development, community development and administration and management services. The identified KRAs are meant to provide the Ministry with a clear direction and focus in the achievement of its mandate.

Thus, in developing this plan, the Ministry considered its mandate, vision, mission and core values which constitute the foundation for its strategic framework in reference to the situation analysis of KRAs. The Ministry’s strategic framework is as outlined below:

**Mandate**

To contribute to sustainable national development through the provision of civic education, cultural and community development services.

**Vision**

A knowledgeable, culturally vibrant and empowered nation

**Mission**

To provide and promote effective civic education, cultural and community development services through participatory programmes for sustainable socio-economic development**.**

In ensuring that the above outcomes are achieved, the Ministry has determined outcome targets that will act as milestones in the implementation process. Given that the implementation of the Strategic Plan cannot happen in a vacuum, various tools and institutional arrangements will be put in place. The tools include: The Risk and Mitigation Strategy, Financial Mobilization Strategy and the Results-Based Logical Framework to guide in monitoring and evaluating the implementation of the Plan. In terms of institutional arrangements, the Ministry will set-up a Strategic Plan Implementation Committee (SPIC) which will be responsible for receiving and reviewing quarterly and annual progress reports on the implementation of the Plan.

1. **INTRODUCTION AND BACKGROUND**

## 1.1 Introduction

This is the first Strategic Plan that has been developed for MoCECCD for the period 2016 - 2021. The purpose of this Strategic Plan is to advance the Ministry’s mandate of contributing to sustainable national development through the provision of civic education, cultural development and community development services. In addition, the Plan intends to provide the institution with a clear direction for achieving its vision.

The 2016 – 2021 Strategic Plan:

1. Presents the vision, mission, core values and desired outcomes and is supported by more detailed matrices of outputs and output targets that will assist in achieving the outcomes; and the results logical framework for monitoring and evaluating the achievements;
2. Underpins the high priority placed on civic education, cultural and community development programmes at grassroots level as bedrocks for socio-economic development in the country and ensures that the Ministry will undertake these responsibilities as per its mandate; and
3. Informs MoCECCD staff and all other stakeholders on how the Ministry intends to operationalize and fulfill its mandate.

## 1.2 Background to the Establishment of MoCECCD

The Ministry was instituted in September, 2016 as a result of the restructuring of Ministries. The Department of Civic Education was in the Ministry of Information and Communications Technology; the Department of Culture belonged to the now defunct Ministry of Sports and Culture; whereas the Department of Community Development was in the Ministry of Gender, Children, Disability, and Social Welfare. The three technical departments were brought together to form what is now called Ministry of Civic Education, Culture, and Community Development.

The Department of Civic Education was established in 2007 to educate the citizenry on various socio-economic issues with the aim of imparting knowledge and influencing positive behavior change.

Legislation for cultural institutions can be traced back as far as 1947. However, the divisions that constituted the Department of Culture comprised of Arts and Crafts, Antiquities, Museums of Malawi, National Archives, and the Malawi Censorship Board. The then Department of Culture had been in various Ministries which in a way affected its stability in terms of operational efficiency. The Department underwent a functional review in 2014 which resulted in splitting it into three departments namely: Arts; Museums and Monuments; and National Records and Archive Services.

The Department of Community Development draws its history from three distinct phases namely: the colonial era 1891-1963, the Kamuzu era 1964 – 1993 and the multiparty era 1994 to date. However, the main policy document guiding community development in the country was the 1969 Principles of Community Development which outlined the country’s philosophy of community development. This was aimed at stimulating the interest of people living in rural and urban areas to participate and undertake self-help projects so as to support national development programmes which were meant to raise living standards. These principles were espoused in the Statement of Development Policies I and II (DEVPOL, 1960s) and translated into various community development programmes. The programmes included Community Mobilization; Community Capacity Building; National Adult Literacy; and Home Economics i.e. Women in Development (WID) approaches which later became a fully-fledged department of Gender Affairs.

The Ministry is governed by various Acts and Policies which take cognizance of regional protocols and international conventions as outlined in Table 1 below:

Table 1: Acts and Policies Governing the Ministry

|  |  |  |
| --- | --- | --- |
| **Programmes** | | **Act/Policy** |
| 1 | Civic Education | National Civic Education Policy (Draft) |
| 2 | Culture Development | National Cultural Policy 2015;  The Monuments and Relics Act 1990;  The Arts and crafts Act 1990;  The Printed Publications Act 1947;  The Censorship and Control of Public Entertainment Act 1968;  The National Archives Act 1975; and  The Museums Act 1989. |
| 3 | Community Development | National Community Development Policy 2016 |
| 4 | Administration and Management Services | Public Finance Management Act, 2003;  Public Procurement Act, 2003;  Public Audit Act, 2003; and  Malawi Public Service Regulations 1993. |

## 1.3 Rationale for the Development of the Strategic Plan

The Strategic Plan is an important tool for the provision of civic education, cultural and community development services. The rationale of coming up with this Strategic Plan is to:-

1. Provide a clear and strategic direction for the Ministry’s desired future operations and outline measurable goals for reporting to the Office of the President and Cabinet (OPC);
2. Establish clear and specific achievable outcomes, outcome targets, outputs and output targets as desired results that the Ministry would want to see;
3. Create a common understanding of expected results among stakeholders, management and staff;
4. Set the basis for proper and defensible budgeting process, financial projections and financing mechanisms;
5. Use the strategy as a resource mobilization tool;
6. Align the Ministry members of staff to a common goal(s) and focus thereby enabling everyone to be working towards the achievement of one goal; and
7. Define specific action items and help establish an action plan for effective implementation.

## 1.4 Institutional Set-up of the Ministry

The Ministry is headed by the Principal Secretary and the five technical Departments are headed by Directors. Each Department has several divisions or sections that help in the implementation of their core functions. The Ministry’s operational technical departments are: Civic Education; Arts; Museums and Monuments; National Records and Archives Services; and Community Development. The main functions of the Departments and Sections are highlighted below:

### 1.4.1 Civic Education

The Civic Education Department exists to educate the citizenry on various socio-economic issues with the aim of imparting knowledge and influencing positive behavior change in order to create an informed, knowledgeable, and proactive nation. The Department performs the following functions:

1. Provide policy guidance in civic education matters;
2. Educate the citizenry on government development policies and programmes;
3. Educate the citizenry on various topical and emerging issues;
4. Create popular support for government development agenda; and
5. Promote popular participation in development and democratic processes.

### Arts

The Department of Arts came into being after merging two divisions of Arts and Crafts and Censorship Board. Currently, there are two divisions namely: Arts and Regulatory Services. This Department implements the Arts and Crafts Act of 1990 and the Censorship and Control of Public Entertainment Act of 1968. The Department has offices in Blantyre and Lilongwe.

Through the division of Arts, the Department performs the following functions:

1. Conduct research in the arts, crafts and expressions of folklore;
2. Preserve and present Malawi’s culture through performing arts e.g. traditional dances, theatre, music, song and dance; visual arts; and
3. Provide guidance and assistance to artistic associations

Through the division of Regulatory Services, the Department regulates and controls the following;

1. The making and the exhibition of cinematographic pictures;
2. The importation and production of publications, pictures, statues and records;
3. The performance or presentation of stage plays and public entertainment; and
4. The operation of public entertainment facilities.

### 1.4.3 Museums and Monuments

The Department implements the Museums Act of 1989 and the Monuments and Relics Act of 1990. This Department has three divisions namely: Antiquities, Museums and Research and Outreach.

The mandate of this Department is to preserve, conserve, promote, study and present the natural and cultural heritage of Malawi and interpret this heritage to all Malawians and visitors alike for national identity, posterity and socio-economic development.

The Museums Division consists of six museum facilities, namely: The Top Mandala and Chichiri Museums in Blantyre; Lake Malawi Museum in Mangochi; the Regional Museum in Mzuzu; Karonga Museum in Karonga and Mtengatenga Postal Hut Museum at Namaka in Chiradzulu**.** The Monuments Division has monuments located across the country.

To fulfill its objectives, the Department performs the following functions:

1. Collect and preserve natural history specimens, historical and ethnographic objects;
2. Provide Museum Education Programmes that include: public gallery tours; school guided tours; traditional dance performances; drama performances;
3. Conduct pre-historic, natural history, anthropological and ethnographic research;
4. Identify and ascertains the significance of monuments across the country and preserve and conserve them; and
5. Conduct outreach programmes on research findings and other programmes of the Department through public lectures and museum exhibitions.

### 1.4.4 National Records and Archives Services

The Department of National Records and Archives Services was established in 1947, with the mission to collect, organize, preserve and make the country’s documentary heritage accessible to the public for purposes of reference, research and posterity. The Department has two divisions: Records Management Services and Public Archives. The Head office is in Zomba with branches in Lilongwe and Mzuzu. The Department implements the National Archives Act of 1975 and the Printed Publications Act of 1969.

The Department performs the following functions:

1. Regulate the creation, classification, maintenance and disposal of public records regardless of media;
2. Provide economic storage accommodation for semi-current government records;
3. Provide advisory services regarding the creation, maintenance and disposal of records;
4. Conserve archival documents in order to enhance their lifespan;
5. Provide reference services for Government records and published information resources deposited in the National Archives of Malawi;
6. Preserve historical manuscripts and oral history research programmes for Malawi;
7. Register newspapers and preserve printed works published in Malawi;
8. Promote bibliographic services and research through the publication of the Malawi National Bibliography and other select bibliographies on issues of national interest; and
9. Administer the use and application of the International Standard Book Numbering (ISBN) system in Malawi and provide advisory service to publishers in the country with regard to the application of the system.

### 1.4.5 Community Development

The Department aims to mobilize and build capacities of communities for sustainable development. The Department has the following Divisions: Community Mobilization and Capacity Building; Home Management and Nutrition; and Adult Literacy which perform the following functions respectively:

1. Enhances community capacity and participation in community development projects;
2. Improve the living and nutritional standards by promoting home improvement, water sanitation and hygiene, food utilization and dietary diversification; and
3. Provides basic literacy and numeracy skills to illiterate adults and provide post literacy initiatives to graduates of basic adult literacy to ensure that they are active participants in the national development agenda.

### 1.4.6 Administration and Management

The department has five sections, namely: administration, human resources management, finance, procurement, audit, and planning and policy unit. To fulfill its objective, the department performs the following functions:

1. Coordinate, supervise, and provide management direction and logistical requirements for the Ministry;
2. Facilitate human resources management and development;
3. Facilitate finance, procurement and audit services for the Ministry; and
4. Provides guidance and direction on general to specific ministerial policy, programme planning, implementation and evaluation, and the provision of timely information as a guide to the policy making and review process.

## 1.5 Alignment of MoCECCD Strategic Plan with National, Regional and International Development Policies.

The Strategic Plan has been developed in line with Government priorities spelled out in the Malawi Growth and Development Strategy, Sustainable Development Goals (SDGs), the Agenda 2063 for Africa and the Government Reform Program. Specifically, the plan has been developed in line with the following;

**1.5.1 The Malawi Growth and Development Strategy**

The Malawi Growth and Development Strategy (MGDS) III is the overarching medium term strategy for Malawi which spans a five-year implementation period. The MGDS III provides the overall framework for socio-economic development agenda for Malawi and is supposed to be used as a reference document for planning by all institutions in the country. The MGDS III identifies issues of community development, culture and civic education as critical aspects to sustainable socio-economic development. It further identifies key strategic interventions which should be implemented in order to achieve results.

**1.5.2 Sustainable Development Goals**

At global level, the plan takes cognizance of the Sustainable Development Goals (SDGs). Culture is who we are and what shapes our identity. Culture contributes to poverty reduction and paves the way for a human-centre, inclusive and equitable development. No development can be sustainable without it. Therefore, cultural strategies in this plan are well aligned to the SDGs and they constitute an essential investment in the world's future and a pre-condition to successful globalization processes that take into account the principle of cultural diversity.

Implementation of Civic Education strategies takes cognizance and aligns very closely with the SDG 10 on social, political and economic participation of citizens; and SDG 16 on combating corruption, promoting transparency and accountability, inclusion and participatory issues; ensure public access to information. Besides direct linkages with SDGs 10 and 16 which provide a global rationale for civic education strategies which essentially are cross-cutting issues for the global development agenda signalled by the SDGs.

Community Development strategies on the other hand aims at promoting community self-reliance through capacity building and active participation of community members in various development programmes and projects such as Community Mobilization and Governance; Community Construction Projects; Community Resilience, Nutrition and Livelihoods and Adult Literacy services. Community participation is a vital requirement in the achievement of nearly all SDGs.

**1.5.3 Agenda 2063**

Agenda 2063 is a shared framework for inclusive growth and sustainable development which was agreed upon by African leaders during the 50th Anniversary of the Organization of African Unity (OAU), in 2013. It is a continuation of the Pan-African drive over centuries, for unity, self-administration, freedom, progress and collective prosperity pursued under Pan-Africanism and African Renaissance. It builds on, and seeks to accelerate the implementation of past and existing continental initiatives for growth and sustainable development.

Agenda 2063 is anchored on seven aspirations one of which is where it would like to identify the continent as “An Africa with a strong cultural identity, common heritage, shared values and ethics.” The Ministry subscribes to this aspiration as it is mandated to contribute to sustainable national development through provision of civic education, cultural and community development services. Thus, in its contribution to the attainment of Agenda 2063, the Ministry intends to integrate, in its plan, cultural heritage, cultural values and community resilience issues. The Agenda 2063 envisages that Pan-Africanism and the common history, destiny, heritage, respect for religious diversity and consciousness of African people’s and her Diasporas’ will be entrenched by 2063.

**1.5.4 The Public Service Reforms**

The public service plays a key role in national development as it is the catalyst for a vibrant private sector which is the engine of the economy. However, there is considerable evidence demonstrating shortcomings in the capacity and the delivery of public services. Therefore, there is need for a continuous reform process to enhance efficiency and effectiveness in the execution of civic education, cultural and community development programmes. The Ministry, through the Office of the President and Cabinet will make use of the reforms program to:

1. Ensure that systems are established for provision of quality civic education, cultural and community development services;
2. Ensure ethical behavior and professionalism in the Ministry is achieved and maintained;
3. Ensure impartiality in the delivery of civic education, cultural and community development services;
4. Ensure continuous delivery of civic education, cultural and community development services under all circumstances;
5. Facilitate institutionalization of a culture of accountability, integrity, transparency and promotion of values and principles in the Ministry; and
6. Ensure effective, efficient and responsible use of public resources.

## 1.6 Strategic Plan Development Process

The 2016 – 2021 Strategic Plan has been developed following the establishment of the Ministry of Civic Education, Culture, and Community Development. The formulation process of this strategic plan is based on the Results-Based Planning Approach and is as a result of collaborated efforts by all the departments of the Ministry.

To ensure ownership and acceptance of the plan, the Ministry consulted all relevant stakeholders. These include but not limited to:National Initiative for Civic Education (NICE) Trust, Copyright Society of Malawi (COSOMA), the Department of Human Resources Management and Development (DHRMD) which facilitated the development of this Plan, Office of the President and Cabinet (OPC), and the United Nations Development Programme (UNDP), and District Community Development Officers. The Task team was constituted to review inputs from stakeholders which further enhanced the quality of the strategic plan.

1. **THE STRATEGIC ANALYSIS**

## 2.1 Overview

This section highlights the internal and external situation analysis of MoCECCD using the Strengths, Weaknesses, Opportunities and Threats (SWOT) Analysis technique. The analysis has also taken into account information obtained from some background reports leading to the establishment of the Ministry, feedback received from the Office of the President and Cabinet (OPC), Management, members of staff and contributions received from key stakeholders who were consulted prior to the development of this Plan.

It considers the internal factors (strengths and weaknesses) and external factors (opportunities and threats) that have significant impact on the effective delivery of MoCECCD programmes. Specifically, the strategic analysis centered on issues that impact on the identified Key Result Areas. Hence, in proceeding with the SWOT Analysis Key Result Areas were identified on which to base the analysis.

## 2.2 MoCECCD Key Result Areas

The Key Result Areas (KRAs) reflected under this section are basically primary responsibilities of the Ministry of Civic Education, Culture and Community Development. These are key roles and responsibilities that fall directly under its mandate, such that, if it does not act on them, no other institution will deliver the services in question. This is in recognition of the fact that, the MoCECCD was established as an entity solely charged with the responsibility of providing civic education, cultural and community development services.

Four Key Result Areas were identified for the Ministry based on its mandate. These are as follows:

1. Civic Education;
2. Cultural Development;
3. Community Development; and
4. Administration and Management.

## 2.3 SWOT Analysis

A SWOT analysis was conducted to understand both the internal and external environments in which the Ministry operates. The internal perspective looked at the strengths and weaknesses of the Ministry whilst the external environment involved analyzing the opportunities and threats. The strengths highlight areas in which the Ministry can build on as it forges into the future, while the weaknesses highlight areas which the Ministry needs to address, reduce or eliminate, if it is to deliver on its mandate effectively. The opportunities consist of factors prevailing in the market that MoCECCD can exploit to its advantage and the threats are those factors that can adversely affect its operations if not properly addressed. The SWOT for MoCECCD thus set out in Table 1 which cuts across all the Key Result Areas.

**Table 1: SWOT Analysis based on each Key Result Area**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Key Result Area** | **Strengths** | **Weaknesses** | **Opportunities** | **Threats** |
| **A. CIVIC EDUCATION** | * Availability of Legislation (Communications Act 1998) * Professionally qualified and committed staff * Availability of other stakeholders providing civic education services | * Inadequate resources (personnel, equipment & finances) * Lack of office infrastructure at strategic levels (district offices) * Lack of a National Civic Education policy * Lack of career progression * Lack of coordination among civic education entities | * Political will and support * Availability of development partners * Availability of civic education training institutions * Trained human resource for civic education services * Access to institutions carrying out civic education activities | * High illiteracy levels * Undue external influence * Political interference * Cultural beliefs |
| **Key Result Area** | **Strengths** | **Weaknesses** | **Opportunities** | **Threats** |
| **B. CULTURAL DEVELOPMENT** | * Reforms being undertaken in the sector * Well qualified staff * Availability of cultural offices at strategic levels * Affiliation to important international regional bodies * Availability of legislation * Joint bilateral and multilateral programmes * Availability of the National Cultural Policy * Availability of cultural calendar of events * Availability of Devolution Plan and Management Guidelines | * Out-dated legal framework * Under-representation at local and international fora * Inadequate staff within the establishments * Absence of information and data for decision making * Lack of dissemination strategy for cultural information * Inadequate infrastructure * Inadequate financial resources and equipment * Centralized cultural institutions | * Recognition of the sector among government sectors * Existing rich cultural heritage * Availability of non-state cultural institutions * Widening of promotional platforms for cultural products and services * High potential of the Cultural sector to create jobs * Growing usage of ICT world wide * A growing affluent population * Sector related subjects integrated in Malawi’s academic curricula * Access to local and international development partners * Participation of communities in collaborative management * Political will. * Upgrading existing infrastructure for promotion of Culture * Availability of the Decentralization Policy to support fiscal devolution | * HIV & AIDS pandemic affecting staff * Environmental degradation and climate change * Frequent mobility of the Department from one ministry to the other * Conflicting inter-sectoral mandates and policies * Commercialization of cultural products leading to dilution of traditional cultural values * Lack of value addition and profiling to cultural products and services * Lack of attractive incentives to aid the growth of the industry e.g. duty waivers, levies * Inadequate specialized training opportunities for players in the industry; * Culture under threat from some emerging human rights issues |
| **Key Result Area** | **Strengths** | **Weaknesses** | **Opportunities** | **Threats** |
| **C. COMMUNITY DEVELOPMNT** | * Availability of the National Community Development Policy & Draft Adult Literacy Policy * Availability of devolved functions to local government authorities * Availability of a large network of extension workers existing at district and community levels * Availability of training institutions for staff development | * Lack of program of action to operationalize the policies * Existence of vacancies of key positions   Inadequate financial resources at central and district levels   * Underutilized training facilities * Dilapidated training infrastructure and equipment * Low staff motivation | * Political will to make community development visible and operational * Existing linkages with other policies, SDGs & Agenda 2063 * Availability of trained staff on the market to fill senior positions and graduates to fill frontline positions * Availability of development partners/donors to support community development programmes * High community support for community based programmes * Availability of global internet and intranet facilities * Availability of the Decentralization Policy to support fiscal devolution | * Several stakeholders using conflicting approaches * Inadequate coordination among stakeholders * Some training institutions offering substandard community Development Courses * High staff attrition * Unreliability of volunteers who implement community based activities * Unclear division of responsibilities with other key government ministries like the Department of Nutrition, HIV and AIDS |
| **Key Result Area** | **Strengths** | **Weaknesses** | **Opportunities** | **Threats** |
| **D. ADMINISTRATION AND MANAGEMENT** | * Dedicated and hardworking staff * Well qualified specialized staff * Availability of guiding tools e.g. MPSR, Treasury Instructions, PFAM, PPA * Vibrant flow of information | * Inadequate office space * Inadequate office equipment * Inadequate vehicles * Inadequate financial resources * Few capacity building opportunities * Inadequate staff | * Civil Service Reforms * Existence of training institutions * Availability of Establishment Warrant to fill vacant posts | * Frequent restructuring of ministries and departments * Posting away of specialized staff without replacement |

1. **MoCECCD’s STRATEGIC DIRECTION FOR 2016 - 2021**

## 3.1 Overview

This part of the report gives a detailed roadmap for the Ministry which outlines its strategic direction. It highlights the mandate, vision, mission, and core values. In addition, the section gives a picture of the MoCECCD’s Key Result Areas which form the basis for the determination of strategic outcomes and targets as tangible reflections of what it envisages to achieve by 2021.

## 3.2 Mandate, Vision, Mission and Core Values

**3.2.1 Mandate**

To contribute to sustainable national development through provision of civic education, cultural and community development services.

**3.2.2 Vision**

A knowledgeable, culturally vibrant and empowered nation

**3.2.3 Mission**

To provide and promote effective civic education, cultural and community development services through participatory programmes for sustainable socio-economic development.

**3.2.4 Strategic Objectives**

The Ministry has determined five strategic objectives which are tangible reflections of its mandate and vision. The strategic outcomes and their expected targets constitute the strategic direction that the Ministry will take. These are as follows:

1. Improved civic knowledge, management and coordination of civic education programmes;
2. Malawi’s national heritage in all its identifiable forms safeguarded and promoted for national identity, posterity and sustainable socio-economic development;
3. Improved resource mobilization for cultural development;
4. Increased community participation in development programmes;
5. Improved capacity of households to manage their livelihoods and nutritional well-being; and
6. Improved institutional capacity and organizational efficiency of the Ministry.

**3.2.5 Core Values**

The core values or guiding principles for the Ministry are as follows:

**3.2.5.1 Professionalism**

The Ministry shall discharge its duties using highly qualified, competent and skilled staff and ensure that services are provided impartially.

* + - 1. **Integrity**

The Ministry shall exhibit the highest ethical and authentic standards in the performance of duties.

* + - 1. **Transparency and Accountability**

The Ministry shall ensure that its members of staff are open and accountable in the utilization of public and other development partners’ resources.

* + - 1. **Patriotism**

The Ministry will encourage and instill a sense of love for the country and what it stands for in the implementation of its programmes.

* + - 1. **Team Work**

The Ministry shall encourage members of staff to work harmoniously towards a common goal.

* + - 1. **Collaboration and Networking**

The Ministry shall work with other stakeholders in a coordinated manner.

* + - 1. **Goal Oriented**

The Ministry shall ensure that the provision of its services achieves intended results..

* + - 1. **Creativity and Innovation**

The Ministry shall nurture the potential of its staff to conceive new ideas that address contemporary challenges.

* 1. **Key Result Areas, Strategic Outcomes and Outcome Targets**

Based on the Key Result Areas highlighted at 3.2 above, six strategic outcomes have been identified to be achieved by 2021 and sustained beyond the implementation period. The strategic outcomes thus, constitute the strategic direction that the Ministry will take between 2016 and 2021, which are as reflected in Table 2 below:

**Table 2: KRAs, Strategic Outcomes and Outcome Targets**

|  |  |  |  |
| --- | --- | --- | --- |
| **No.** | **Key Result Area** | **Strategic Outcome** | **Outcome Target** |
| A. | **CIVIC EDUCATION** | **1.0** Improved civic knowledge, management and coordination of civic education programmes | **1.1** 50% reduced duplication of civic education activities by 2021 |
| **1.2** 70% of enhanced popular participation in development processes by 2021 |
| **1.3** 80% of enhanced popular participation in democratic processes by 2021 |
| **1.4** 80% transformative and evidence based civic education activities conducted by 2021 |
| B. | **CULTURAL DEVELOPMENT** | **2.0** Malawi’s national heritage in all its identifiable forms safeguarded and promoted for national identity, posterity and sustainable socio-economic development | **2.1** 50% of key stakeholder institutions mainstreaming cultural issues in their programmes by 2021 |
| **2.2** 80% of key institutions involved in preserving tangible and intangible cultural heritage provided with technical know-how by 2021 |
| **2.3** 50% of critical information on cultural issues collected and processed by 2021 |
| **2.4** 20% of cultural and heritage industry capacity strengthened by 2021 |
| **2.5** 60% of cultural industry products showcased, marketed and distributed by 2021 |
| **2.6** 40% improvement in good records management practices by 2021 |
| **2.7** 80% of the country’s literature output collected and preserved by 2021 |
| **3.0** Improved resource mobilization for cultural development | **3.1** 80% of financial resources in the cultural industry mobilized by 2021 |
| **3.2** 80% of natural resource users in the cultural industry equipped with natural resource management skills by 2021 |
| C. | **COMMUNITY DEVELOPMENT** | **4.0** Increased community participation in development programmes | **4.1** 50% of men and women, boys and girls actively participating in community based development projects by 2021 |
| **4.2** 60% of community leaders equipped with leadership and management skills by 2021 |
| **4.3** 16%increased literacy levels for adults and youth by 2021 |
| **4.4** 50% capacity of community development training Institutions strengthened by 2021 |
| **4.5** 60% of men and women, boys and girls oriented in sexuality education (Community based population education) |
| **5.0** Improved capacity of households to manage their livelihoods and nutrition wellbeing | **5.1** 60% of rural households targeted with home management and nutrition interventions by 2021 |
| **5.2** 50 % of rural and urban Village and Savings Loan groups equipped with business and value addition skills by 2021 |
| D. | **ADMINISTRATION AND MANAGEMENT** | **6.0** Improved institutional capacity and organizational efficiency | **6.1** 90% of the programmes implemented efficiently and effectively |
| **6.2** Vacancy rate reduced from 54% to 10% by 2021 |
| **6.3** Institutional performance improved by 80% by 2021 |
| **6.4** 20% of ICT infrastructure in place and operational by 2021 |
| **6.5** 90% of administrative services provided by 2021 |
| **6.6** HIV/AIDS, gender, environmental and disability issues mainstreamed in all programmes by 2021 |
| **6.7** Financial processes in accordance with policies and regulatory requirements strengthened by 2021 |
|  |

## 3.4 Outputs and Annual Output Targets

In order to achieve the outcome targets highlighted in Table 2 above, the Ministry has determined outputs on each outcome target. These are the services that the Ministry will provide to achieve its outcome targets. Table 3 below is an outline of outputs and annual output targets under each outcome

**Table 3: Outputs and Annual Output Targets**

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| **Strategic Outcome 1** | | | **Improved civic knowledge, management and coordination of civic education programmes** | | | | |
| **Outcome Target 1.1** | | | **50% reduction in duplication of civic education activities by 2021 (Baseline 70%)** | | | | |
| **OUTPUT DESCRIPTION** | | | **OUTPUT TARGETS (PER FINANCIAL YEAR)** | | | | |
| **2016/2017** | **2017/2018** | **2018/2019** | **2019/2020** | **2020/2021** |
| Output 1 | National Civic Education Policy developed and implemented by 2020 | | Consultations on National Civic Education Policy conducted | Draft National Civic Education Policy developed | National Civic Education Policy approved by cabinet | National Civic Education Policy launched, disseminated | National Civic Education Policy implemented |
| Output 2 | National civic education forum established by 2021 | |  |  | Stakeholders meeting conducted | Terms of Reference developed (ToRs) | National civic education forum Institutionalized and operationalized |
| Output 3 | Civic education activities in Government MDAs identified and coordinated | |  | Civic education activities in MDAs identified and coordinated | Joint civic education activities with MDAs and stakeholders conducted | Joint civic education activities with stakeholders conducted | Joint civic education activities with stakeholders conducted |
| Output 4 | Stakeholder Strategic plans aligned to the Civic Education Policy (for coordination of civic education) | |  |  |  | Stakeholder's civic education strategic plans aligned to Civic Education Policy |  |
| **Outcome Target 1.2** | | | **70% enhanced popular participation in development processes (Baseline 60%)** | | | | |
| Output 1 | Formative Research conducted & report produced | |  |  | 1 formative research conducted and report produced |  | 1 summative research conducted and report produced |
| Output 2 | Civic Education Officers oriented on how to conduct Civic Education activities (Trainer of Trainers') | |  | 3 regional orientation workshops on how to conduct civic education activities conducted | 3 regional orientation workshops on how to conduct civic education activities conducted | 3 regional orientation workshops on how to conduct civic education activities conducted |  |
| Output 3 | 2,040,000 people mobilized on various social issues through Interactive film shows | | 180,000 people mobilized on various social issues through 36 interactive film shows | 600,000 people mobilized on various social issues through 120 interactive film shows | 420,000 people mobilized on various social issues through 120 interactive film shows | 420,000 people mobilized on various social issues through 120 interactive film shows | 420,000 people mobilized on various social issues through 120 interactive film shows |
| Output 4 | 19,440 people sensitized on topical issues of national importance through Community dialogue sessions | | 2,880 people sensitized on topical issues of national importance through community dialogue sessions | 3,600 people sensitized on topical issues of national importance through community dialogue sessions | 4,320 people sensitized on topical issues of national importance through community dialogue sessions | 4,320 people sensitized on topical issues of national importance through community dialogue sessions | 4,320 people sensitized on topical issues of national importance through community dialogue sessions |
| Output 5 | 28 District Councils (DCs) and 168 ADCs sensitized on the importance of community participation in development programmes | |  | 7 DCs and 35 ADCs sensitized on the importance of community participation in development programmes | 7 DCs and 40 ADCs sensitized on the importance of community participation in development programmes | 7 DCs and 40 ADCs sensitized on the importance of community participation in development programmes | 7 DCs and 45 ADCs sensitized on the importance of community participation in development programmes |
| Output 6 | 81,035 IEC promotion materials on development processes produced and disseminated | | 8,000 Leaflets on development processes produced and disseminated | 15,000 Leaflets on development processes produced and disseminated | 8,000 Leaflets on development processes produced and disseminated | 6,000 Leaflets on development processes produced and disseminated | 6,000 Leaflets on development processes produced and disseminated |
| 1,000 Posters | 3,000 Posters | 2,000 Posters | 2,000 Posters | 2,000 Posters |
| 3,000 brochures | 10,000 brochures | 5,000 brochures | 5,000 brochures | 5,000 brochures |
| 3 comedies | 3 comedies | 3 comedies | 3 comedies | 3 comedies |
| 4 jingles produced and distributed | 4 jingles produced and distributed | 4 jingles produced and distributed | 4 jingles produced and distributed | 4 jingles produced and distributed |
| **Outcome Target 1.3** | | | **80% enhanced popular participation in democratic processes by 2021 (Baseline 60%)** | | | | |
| Output 1 | 2,040,000 people mobilized for civic education on governance issues through Interactive film shows | | 180,000 people mobilized for civic education on governance issues through 36 interactive film shows | 600,000 people mobilized for civic education on governance issues through 120 interactive film shows | 420,000 people mobilized for civic education on governance issues through 120 interactive film shows | 420,000 people mobilized for civic education on governance issues through 120 interactive film shows | 420,000 people mobilized for civic education on governance issues through 120 interactive film shows |
| Output 2 | 19,440 people sensitized through community dialogue sessions on governance issues | | 2,880 people sensitized on governance issues through community dialogue sessions | 3,600 people sensitized on topical governance issues through community dialogue sessions | 4,320 people sensitized on governance issues through community dialogue sessions | 4,320 people sensitized on governance issues of through community dialogue sessions | 4,320 people sensitized on governance issues of through community dialogue sessions |
| Output 3 | 28 District Councils (DCs) and 168 ADCs sensitized on governance issues | | 2 DCs and 10 ADCs sensitized on governance issues | 7 DCs and 35 ADCs sensitized on governance issues | 7 DCs and 36 ADCs sensitized on governance issues | 6 DCs and 34 ADCs sensitized on governance issues | 6 DCs and 45 ADCs sensitized on governance issues |
| Output 4 | 81,035 IEC promotion materials on governance issues produced and disseminated | | 8,000 Leaflets on governance issues produced and disseminated | 15,000 Leaflets on governance issues produced and disseminated | 8,000 Leaflets on governance issues produced and disseminated | 6,000 Leaflets on governance issues produced and disseminated | 6,000 Leaflets on governance issues produced and disseminated |
|  |  | | 1,000 Posters | 3,000 Posters | 2,000 Posters | 2,000 Posters | 2,000 Posters |
| 3,000 brochures | 10,000 brochures | 5,000 brochures | 5,000 brochures | 5,000 brochures |
| 3 comedies | 3 comedies | 3 comedies | 3 comedies | 3 comedies |
| 4 jingles produced and distributed | 4 jingles produced and distributed | 4 jingles produced and distributed | 4 jingles produced and distributed | 4 jingles produced and distributed |
| **Outcome Target 1.4** | | | **80% transformative and evidence based civic education activities conducted by 2021 (Baseline 0%)** | | | | |
| Output 1 | 9 appreciative Enquiry sessions conducted | |  | 1 Appreciative enquiry sessions conducted | 2 Appreciative enquiry sessions conducted | 2 Appreciative enquiry sessions conducted | 4 Appreciative enquiry sessions conducted |
| Output 2 | 17 star performers and role models Increased | |  | 2 community based dialogue sessions with role models conducted | 4 community based dialogue sessions with role models conducted | 5 community based dialogue sessions with role models conducted | 6 community based dialogue sessions with role models conducted |
| Output 3 | 2 civic education resources centers established | |  |  | One civic education resources centers established |  | one civic education resources centers established |
| **Strategic Outcome 2** | | | **Malawi’s national heritage in all its identifiable forms safeguarded and promoted for national identity, posterity and sustainable socio-economic development** | | | | |
| **Outcome Target 2.1** | | | **50% of key stakeholder institutions mainstreaming cultural issues in their programmes by 2021 (baseline 40%)** | | | | |
| **OUTPUT DESCRIPTION** | | | **OUTPUT TARGETS (PER FINANCIAL YEAR)** | | | | |
| **2016/2017** | **2017/2018** | **2018/2019** | **2019/2020** | **2020/2021** |
|  |  | |  |  |  |  |  |
| Output 1 | Key stakeholders institutions oriented on mainstreaming of culture in their programmes | | 15 key stakeholders institutions oriented on mainstreaming of culture in their programmes | 45 key stakeholders institutions oriented on mainstreaming of culture in their programmes | 45 key stakeholders institutions oriented on mainstreaming of culture in their programmes | 45 key stakeholders institutions oriented on mainstreaming of culture in their programmes | 45 key stakeholders institutions oriented on mainstreaming of culture programmes |
| Output 2 | 120 institutional focal persons trained in mainstreaming culture in their programmes | |  | 45 key stakeholders institutions focal persons trained | 45 key stakeholders institutions focal persons trained | 45 key stakeholders institutions focal persons trained | 45 key stakeholders institutions l focal persons trained |
| **Outcome Target 2.2** | | | **80% of key institutions involved in preserving tangible and intangible cultural heritage provided with technical know- how by 2021 (Baseline 50%)** | | | | |
| Output 1 | 100 Institutions oriented on cultural heritage preservation | | 20 institutions oriented on cultural heritage preservation | 20 institutions oriented on cultural heritage preservation | 20 institutions oriented on cultural heritage preservation | 20 institutions oriented on cultural heritage | 20 institutions oriented on cultural heritage |
| Output 2 | 204 Communities mobilized in cultural heritage preservation | | 34 community groups mobilized in cultural heritage preservation | 30 community groups mobilized in cultural heritage preservation | 40 community groups mobilized in cultural heritage preservation | 50 community groups mobilized in cultural heritage preservation | 50 community groups mobilized in cultural heritage preservation |
| Output 3 | 27 movable and immovable cultural heritage maintained | | 5 maintenance/ rehabilitation program implemented | 5 maintenance/ rehabilitation program implemented | 7 maintenance/ rehabilitation program implemented | 5 maintenance/ rehabilitation program implemented | 5 maintenance/ rehabilitation program implemented |
| Output 4 | 5 pieces of legislation for cultural heritage reviewed | | 1 piece of legislation for cultural heritage reviewed | 1 piece of legislation for cultural heritage reviewed | 1 piece of legislation for cultural heritage reviewed | 1 piece of legislation for cultural heritage reviewed | 1 piece of legislation for cultural heritage reviewed |
| **Outcome Target 2.3** | | | **50% of information on cultural issues collected, processed and disseminated by 2021 (Baseline 40%)** | | | | |
| Output 1 | Research on various aspects of culture conducted | | 1 research program conducted | 2 research programmes conducted | 3 research programmes conducted | 3 research programmes conducted | 1 research program conducted |
| Output 2 | Databank for cultural development developed | |  | Data bank developed | Data bank populated | Data bank populated | Data bank reviewed |
| Output 3 | 13 awareness programmes on cultural issues conducted | | 1 awareness programme on cultural issues conducted | 3 awareness programme on cultural issues conducted | 3 awareness programme on cultural issues conducted | 3 awareness programme on cultural issues conducted | 3 awareness programme on cultural issues conducted |
| **Outcome Target 2.4** | | | **20% of culture and heritage industry capacity strengthened by 2021 (Baseline 30%)** | | | | |
| Output 1 | 450 Stakeholders equipped with cultural preservation and conservation skills | | 50 stakeholders trained | 100 stakeholders trained | 100 stakeholders trained | 100 stakeholders trained | 100 stakeholders trained |
| Output 2 | Grant schemes for culture practitioners introduced | |  | Grant scheme in place |  | Second Grant Scheme in place | Grant scheme reviewed |
| Output 3 | Cultural industry coordination structure established | |  | National Arts Heritage Council (NAHeC) draft bill submitted to Ministry of Justice and Constitutional Affairs for vetting | National Arts Heritage Council (NAHeC) draft bill vetted | National Arts Heritage Council (NAHeC) bill enacted | National Arts Heritage Council (NAHeC) established |
| Output 4 | Cultural and heritage infrastructure rehabilitated and developed | | 3 structures rehabilitated | 14 structures rehabilitated | 5 structures rehabilitated | 5 structures rehabilitated | 5 structures rehabilitated |
| **Outcome Target 2.5** | | | **60% of cultural industry and heritage products show cased, marketed and distributed by 2021 (Baseline 50%)** | | | | |
| Output 1 | Cultural industry marketing system developed | | Marketing system developed | Marketing system operational | Marketing system operational | Marketing system operational | Marketing system reviewed |
| Output 2 | 125 cultural industry and heritage events facilitated and promoted | | 25 events facilitated and hosted | 25 events facilitated and hosted | 25 events facilitated and hosted | 25 events facilitated and hosted | 25 Cultural industry events facilitated and promoted |
| Output 3 | 2 cultural industry and heritage production centres developed | |  |  | Production Centre established | Production Centre operational | Production Centers reviewed |
| Output 4 | 4 Cultural heritage sites developed and marketed | |  | 1 heritage site developed and marketed | 1 heritage site developed and marketed | 1 heritage site developed and marketed | 1 heritage sites developed and marketed |
| **Outcome Target 2.6** | | | **40% improvement in good records management practices by 2021 (Baseline 40%)** | | | | |
| Output 1 | National Records Management Policy developed and implemented | |  | Regional consultations on National Records Management Policy conducted | Draft National Records Management Policy developed | Draft National Records Management Policy validated | Draft National Records Management Policy submitted to Ministry of Justice and Constitutional Affairs |
| Output 2 | 1000 Records management registry personnel from the public sector trained in proper records management practices | | 150 record management/registry personnel trained in good records management | 400 record management/registry personnel trained in good records management | 150 record management/registry personnel trained in good records management | 150 record management/registry personnel trained in good records management | 150 record management/registry personnel trained in good records management |
| Output 3 | Records retention and disposal schedules for selected MDAs reviewed | | 2 records retention and disposal schedules for selected MDAs reviewed | 2 records retention and disposal schedules for selected MDAs reviewed | 2 records retention and disposal schedules for selected MDAs reviewed | 2 records retention and disposal schedules for selected MDAs reviewed | 2 records retention and disposal schedules for selected MDAs reviewed |
| Output 4 | 250 MDAs mainstreaming proper records management standards and compliance to records management practices | | 50 MDAs mainstreaming proper records management standards and compliance to records management practices | 50 MDAs mainstreaming proper records management standards and compliance to records management practices | 50 MDAs mainstreaming proper records management standards and compliance to records management practices | 50 MDAs mainstreaming proper records management standards and compliance to records management practices | 50 MDAs mainstreaming proper records management standards and compliance to records management practices |
| Output 5 | 250 Historical 16mm cinematographic films digitised | | 50 films digitised | 50films digitised | 50 films digitised | 50 films digitised | 50 films digitised |
| **Outcome Target 2.7** | | | **80% of the country’s literature output collected and preserved by 2021 (Baseline 50%)** | | | | |
| Output 1 | 5000 Printed and published works in Malawi collected and preserved in National Archives Legal Deposit Library | | 1000 publications collected and preserved | 1000 publications collected and preserved | 1000 publications collected and preserved | 1000 publications collected and preserved | 1000 publications collected and preserved |
| **Outcome Target 2.8** | | | **Malawi’s cultural heritage and public morals protected, preserved and promoted (Regulation for cultural heritage and public morals implemented) by 2021** | | | | |
| Output 1 | 2511 film distributors, producers and entertainment facilities regulated | | 511 licenses for video theatres, video libraries, video shops and entertainment centres issued | 500 licenses for video theatres, video libraries, video shops and entertainment centres issued | 500 licenses for Video theatres, video libraries, video shops and entertainment centres issued | 500 licenses for Video theatres, video libraries, video shops and entertainment centres issued | 500 licenses for Video theatres, video libraries, video shops and entertainment centres issued |
| Output 2 | 43560 film industry and publications regulated | | 9560 Films and publications classified | 10,000 Films and publications classified | 9,000 Films and publications classified | 8,000 Films and publications classified | 7,000 Films and publications classified |
| **Strategic Outcome 3** | | | **Improved resource mobilization for cultural and heritage development** | | | | |
| **Outcome Target 3.1** | | | **50% of financial resources in the cultural industry and heritage mobilized** | | | | |
| **OUTPUT DESCRIPTION** | | | **OUTPUT TARGETS (PER FINANCIAL YEAR)** | | | | |
| **2016/2017** | **2017/2018** | **2018/2019** | **2019/2020** | **2020/2021** |
| Output 1 | Cultural industry resource mobilisation strategy developed | |  | Cultural industry resource mobilisation strategy developed | Cultural industry resource mobilisation strategy implemented | Cultural industry resource mobilisation strategy implemented | Cultural industry resource mobilisation strategy reviewed |
| Output 2 | 550 stakeholders in the cultural industry trained in financial resource mobilisation and management skills | |  | 100 stakeholders trained | 150 stakeholders trained | 150 stakeholders trained | 150 stakeholders trained |
| **Outcome Target 3.2** | | | **50% of natural resource users in the cultural industry and heritage sensitised on natural resource management by 2021 (Baseline 0%)** | | | | |
| Output 1 | Natural resource management challenges within the cultural industry documented | |  | Stakeholders meeting and situational analysis conducted and report produced |  |  |  |
| Output 2 | 200 stakeholder institutions sensitized in natural resources conservation | |  | 40 institutions sensitized | 40 institutions sensitized | 40 institutions sensitized | 40 institutions sensitized |
| **Strategic Outcome 4** | | | **Increased community participation in development projects and community based population education** | | | | |
| **Outcome Target 4.1** | | | **50% of men and women, boys and girls actively participating in community based development projects by 2021(Baseline - )** | | | | |
| **OUTPUT DESCRIPTION** | | | **OUTPUT TARGETS (PER FINANCIAL YEAR)** | | | | |
| **2016/2017** | **2017/2018** | **2018/2019** | **2019/2020** | **2020/2021** |
| Output 1 | Community Development Policy Developed | | Community Development Policy approved | Community Development Policy printed, launched and disseminated | Community Development Policy implemented | Community Development Policy implemented | Community Development Policy implemented |
| Output 2 | 7840 Community Development leaders trained in project management | | 720 VDCs trained in project management | 1800 VDCs trained in project management | 2000 VDCs trained in project management | 2000 VDCs trained in project management | 1000 VDCs trained in project management |
| 150 ADCs trained in project management | 170 ADCs trained in project management |  |  |  |
| Output 3 | Delivery of community mobilization and capacity building services enhanced | |  | Community Development Result Framework aligned to Sustainable Development Goals | Community Development SDGs d, implemented in all districts | Community Development SDGs d, disseminated and implemented in all districts | Community Development SDGs , implemented in all districts |
|  |  | Communication and Advocacy Strategy for Community Development Programmes Developed | Communication and Advocacy Strategy for Community Development Programmes piloted | Communication and Advocacy Strategy for Community Development Programmes reviewed |
| Output 4 | Awareness of Community development programmes enhanced | | 3 commemoration events facilitated (International Literacy Day, World Rural Women’s Day, World Population Day) | 3 commemoration events observed (International Literacy Day, World Rural Women’s Day, World Population Day) and community Development Month | 3 commemoration events observed (International Literacy Day, World Rural Women’s Day, World Population Day, Community Development month) | 3 commemoration events observed (International Literacy Day, World Rural Women’s Day, World Population Day) | 3 commemoration events observed ( International Literacy Day, World Rural Women’s Day, World Population Day) |
| Output 5 | Networking and coordination of community development programmes enhanced | |  | 4 Technical Working Group meetings conducted | 4 Technical Working Group meetings conducted | 4 Technical Working Group meetings conducted | 4 Technical Working Group meetings conducted |
| International conference patronized | International conference patronized | International conference patronized | International conference patronized | International conference patronized |
| Output 6 | Capacity of 240 community development staff enhanced | |  | 60 staff provided in service training in community and social protection | 60 staff provided in service training in community and social protection | 60 staff provided in service training in community and social protection | 60 staff provided in service training in community and social protection |
| Output 7 | Capacity of community development institutions improved | |  | Operational plan for Ntchisi Community Development Training Centre, Liwonde Community Development Training Centre and National Centre for literacy and Adult Education developed | Operational plan for Ntchisi Community Development Training Centre, Liwonde Community Development Training Centre and National Centre for literacy and Adult Education implemented | Operational plan for Ntchisi Community Development Training Centre, Liwonde Community Development Training Centre and National Centre for literacy and Adult Education implemented | Operational plan for Ntchisi Community Development Training Centre, Liwonde Community Development Training Centre and National Centre for literacy and Adult Education implemented and reviewed |
|  |  | Operational plan for Mzuzu, Kwacha and Monkey bay Community Development Training Centre developed | Operational plan for Mzuzu, Kwacha and Monkey bay Community Development Training Centre implemented | Operational plan for Mzuzu, Kwacha and Monkey bay Community Development Training Centre implemented and reviewed |
|  |  | |  |  | Mzuzu Regional, Kwacha, Monkey-bay Community Development Training Centre  rehabilitated | Ntchisi Community Development Training Centre and  National Centre for Literacy and Adult Education rehabilitated |  |
| Output 8 | Community leaders and members mobilized to contribute and actively participate in the implementation of self-help and donor funded projects | |  | Community mobilization strategy and guidelines developed | 5,349 Community leaders oriented in the strategy | 4,400 Community leaders oriented in the strategy |  |
|  | 2000 copies of community mobilization strategy and 2000 copies of guidelines printed and disseminated |  |  |  |
| **Outcome Target 4.2** | | | **60% of untrained community leaders and village development committee (VDC) members equipped with leadership and management skills by 2021 (Baseline - )** | | | | |
| Output 1 | 6660 Community leaders’ skills in leadership and management enhanced | |  |  | Community Leadership Training Manual finalized, and printed | 400 District officers oriented in the Manuals |  |
| 600 VDCs oriented in leadership and management | 1100 VDCs oriented in leadership and management | 1200 VDCs oriented in leadership and management | 1300 VDCs oriented in leadership and management | 1400 VDCs oriented in leadership and management |
| 330 ADCs oriented in leadership and management |  |  | 330 ADCs re-oriented in leadership and management |  |
| **Outcome Target 4.3** | | | **Literacy levels for adults and youth increased by 16 % by 2021 (Baseline - )** | | | | |
| Output 1 | Adult Literacy Policy developed and implemented | | Stakeholders consulted on draft Adult Literacy Policy | Adult Literacy Policy validated | Adult Literacy Policy finalized and implemented | Adult Literacy Policy implemented | Adult Literacy Policy implemented |
| Output 2 | 12,000 male and female Adult Basic Literacy (ABL) Volunteer Instructors recruited and 16,000 trained | | 4000 male and female ABL Volunteer Instructors trained | 4000 male and female ABL Volunteer Instructors trained | 4000 male and female ABL Volunteer Instructors recruited and 2000 trained | 4000 male and female ABL Volunteer Instructors and 2000 trained | 4000 male and female ABL Volunteer Instructors recruited and 4000 trained |
| Output 3 | Delivery of Adult Literacy Program improved | |  | Functional Literacy Instructional Training Manual reviewed and 500 copies printed | 400 District officers oriented on reviewed Manual |  |  |
| Monitoring and supervision of adult literacy classes conducted | Monitoring and supervision of adult literacy classes conducted | Monitoring and supervision of adult literacy classes conducted | Monitoring and supervision of adult literacy classes conducted | Monitoring and supervision of adult literacy classes conducted |
|  | 100 Push bikes procured | 2 motor vehicles, and 4000 Push bikes procured | 4000 Push bikes procured | 2 motor vehicles, 29 motor bikes and 8100 Push bikes procured |
| Audio visual equipment maintained | Audio visual equipment and van procured and maintained | Audio visual equipment and van procured and maintained | Audio visual equipment maintained | Audio visual equipment maintained |
| Print shop maintained | Print shop equipment procured and maintained | Print shop equipment procured and maintained | Print shop maintained | Print shop maintained |
| Output 4 | 540,000 ABL instruction materials for Chichewa Literacy Instructors procured/produced | | 60,000 ABL instruction materials procured | 120,000 ABL instruction materials produced | 120,000 ABL instruction materials produced | 80 000 ABL instruction materials produced | 60,000 ABL instruction materials produced |
| Output 5 | 2,400 ABL Volunteer male and female Supervisors oriented on FLINT manual | | 800 ABL Volunteer male and female Supervisors oriented | 400 ABL Volunteer male and female Supervisors oriented | 400 ABL Volunteer male and female Supervisors oriented | 400 ABL Volunteer male and female Supervisors oriented | 400 ABL Volunteer male and female Supervisors oriented |
| Output 6 | Networking with Adult Literacy service providers strengthened | | 4 coordination meetings conducted at all levels | 4 coordination meetings conducted at all levels | 4 coordination meetings conducted at all levels | 4 coordination meetings conducted at all levels | 4 coordination meetings conducted at all levels |
| Output 7 | CDAs oriented in English Adult Literacy curriculum | |  | 320 CDAs oriented in English Adult Literacy curriculum | 200 CDAs oriented in English Adult Literacy curriculum |  |  |
| Output 8 | 4900 male and female volunteer Instructors in English Adult Literacy curriculum trained | | 600 Volunteer male and female Instructors in English Adult Literacy Curriculum trained | 800 Volunteer male and female Instructors in English Adult Literacy Curriculum trained | 800 Volunteer male and female Instructors in English Adult Literacy Curriculum trained | 1,200 Volunteer male and male Instructors in English Adult Literacy Curriculum trained | 1,500 Volunteer male and female Instructors in English Adult Literacy curriculum trained |
| Output 9 | Post literacy activities promoted | | 80,000 male and female ABL graduates linked to vocational & entrepreneurial skills | 120,000 male and female ABL graduates linked to vocational & entrepreneurial skills | 160,000 male and female ABL graduates linked to vocational & entrepreneurial skills | 200,000 male and female ABL graduates linked to vocational & entrepreneurial skills | 20,000 Male and female ABL graduates linked to vocational and entrepreneurial skills |
| 8,000 easy to read booklets produced for female and male graduates | 16,000 easy to read booklets produced for female and male graduates | 245,000 easy to read booklets produced for female and male graduates | 32,000 easy to read booklets produced for female and male graduates | 32,000 easy to read booklets produced for female and male graduates |
|  | 400 Rural Information centers established | 800 Rural Information centers established | 1200 Rural Information centers established | 1600 Rural Information centers established |
| Output 10 | 230,000 Instructional materials for English Literacy Instructors procured | | 25,000 Instructional materials procured | 40,000 Instructional materials procured | 60,000 Instructional materials procured | 80,000 Instructional materials procured | 25,000 Instructional materials for English Literacy Instructors procured |
| **Outcome Target 4.4** | | | **Capacity of Magomero Community Development College strengthened by 50% by 2021 (Baseline - )** | | | | |
| Output 1 | | Curricular for Community Development programmes reviewed, developed and implemented) | Curriculum for certificate courses reviewed and Diploma curricula for Community Development developed | Diploma curriculum in Home management and Nutrition developed and approved, Diploma curriculum in Community development approved, implemented and Degree curriculum developed | Home management and Nutrition and Community Development and Diploma programmes implemented and Community Development Degree curriculum approved | Certificate, Diploma and Degree programmes implemented | Certificate, diploma and Degree programmes implemented |
|  | 80 students enrolled for Diploma in Community Development and Agro-processing courses | 160 students enrolled for Diploma program in Community Development and Agro processing course and 40 students enrolled for Diploma In Home management and Nutrition | 240 students enrolled for Diploma program in Community Development, Agro processing, Home management and Nutrition and 40 students enrolled for Degree in Community Development | 320 students enrolled for Diploma program in Community Development, Agro processing course, Home Management and Nutrition and degree course in Community Development |
|  | Continuous professional community development courses developed | 40 serving officers enrolled for continuous professional community development courses | 40 serving officers enrolled for continuous professional community development courses | 40 serving officers enrolled for continuous professional community development courses |
|  | E-Learning infrastructure established | ODL programmes developed | 40 participants enrolled in ODL programmes with Magomero Community Development College | Satellite centers for ODL programmes introduced |
| Output 2 | College infrastructure improved | | Appropriate Technology Centre infrastructure rehabilitated | 6 Business units revived | New products introduced |  |  |
|  | Construction of administration block completed and contractor for lecture theatre and library procured | Construction of Lecture theatre commenced,1 Library  , 5 classrooms, 4 hostels, dining hall, office block and institutional houses rehabilitated | Construction of Lecture theatre completed, construction of Library commenced  5 classrooms, 4 hostels, dining hall, office block, Institutional houses rehabilitated and maintained | construction of Library completed5 classrooms, 4 hostels, dining hall, office block, institutional houses rehabilitated and maintained |
| Output 3 | Administrative and academic capacity enhanced | | Tutor supported for a Degree course | Tutor supported for a Master’s Degree course | 3 Tutor supported for a Master’s Degree course and 2 for PhD | 3 Tutor supported for a Master’s Degree course and 2 for PhD | 2 Tutor supported for a Master’s Degree course and 2 for PhD |
|  | |  | In- service training organized for staff | In -service training organized for staff | In -service training organized for staff | In-Service training organized for staff |
| Output 4 | Institution and programmes registration and accreditation status with NCHE and TEVETA attained | | Magomero Community Development College diploma programmes accredited by TEVETA | Magomero Community Development Diploma and Home management and Nutrition programmes accredited by TEVETA | Magomero Community Development Degree Programme accredited by NCHE |  |  |
| **Outcome Target 4.5** | | | **80% of the target population mobilized in Community Based Population Education Program by 2021 (Baseline - )** | | | | |
| Output 1 | Strategy and guidelines for implementation of Community Population Education Program developed, printed and disseminated | |  | Strategy and guidelines for implementation of Community Population Education Program developed | Strategy and guidelines for implementation of Community Population Education Program printed and disseminated |  |  |
| Output 2 | Community based Population Education programme enhanced | |  | 200 Trainers trained on sexuality and family planning | 200 Trainers trained on sexuality and family planning |  |  |
|  | Community based Population Education Manual reviewed | 4000 Community based Population Education Manuals printed and disseminated |  |  |
|  |  | Assorted Training equipment (LCD, Audiovisual equipment, and Flip chart stands procured/ produced | Assorted Training equipment (LCD, Audiovisual equipment and Flip chart stands procured/ produced |  |
|  | IEC materials procured and disseminated through print and electronic media |  | IEC materials procured and disseminated through print and electronic media |  |
|  |  |  | 3500 Community leaders sensitized on Community Based Population Education Program | 3500 Community leaders sensitized on Community Population Education Program |
|  |  | 600,000 boys, girls men and women sensitized and trained in sexuality education using multimedia channels | 800,000 boys, girls men and women sensitized and trained in sexuality education using multimedia channel | 600,000 boys, girls men and women sensitized and trained in sexuality education using multimedia channels |
| **Strategic Outcome 5** | | | **Improved capacity of households to manage their livelihoods and nutrition wellbeing** | | | | |
| **Outcome Target 5.1** | | | **60% of rural households targeted with home management and nutrition interventions by 2021 (Baseline - )** | | | | |
| **OUTPUT DESCRIPTION** | | | **OUTPUT TARGETS (PER FINANCIAL YEAR)** | | | | |
| **2016/2017** | **2017/2018** | **2018/2019** | **2019/2020** | **2020/2021** |
| Output 1 | Community resilience management and nutrition programme promoted | |  | 8000 Community Resilience, Nutrition and Home management Manual and Demonstration Guide finalized printed and distributed |  |  |  |
|  | 200 frontline workers oriented on revised Community Nutrition and Home Management manuals and guidelines | 200 frontline workers oriented on revised Community Nutrition and Home Management manuals and guidelines |  |  |
|  |  | 500 community leaders trained in Community Nutrition and Home Management | 750 community leaders trained in Community Nutrition and Home Management | 750 community leaders trained in Community Nutrition and Home Management |
|  |  | 100,000 mothers and care group members sensitized in early malnutrition case detection and referral | 200,000 mothers and care group members sensitized in early malnutrition case detection and referral | 200,000 mothers and care group members sensitized in early malnutrition case detection and referral |
| 10,000 households trained in good hygiene and sanitation | 20,000 households trained in good hygiene and sanitation | 30,000 households trained in good hygiene and sanitation | 30,000 households trained in good hygiene and sanitation | 30,000 households trained in good hygiene and sanitation |
| 120,000 households reached with information promoting good nutrition practices through open days | 600,000 households reached with information promoting good nutrition practices through open days | 600,000 households reached with information promoting good nutrition practices through open days | 600,000 households reached with information promoting good nutrition practices through open days | 600,000 households reached with information promoting good nutrition practices through open days |
|  |  | 180 VSL promoters trained as Trainer of Trainers in Management of Gender Based Violence | 60,000 VSL members oriented in Management of Gender Based Violence | 60,000 VSL members oriented in Management of Gender Based Violence |
| **Outcome Target 5.2** | | | **80% of the target population sensitized on enhanced HIV and AIDS education by 2021** | | | | |
| Output 1 | He for She campaign promoted in communities | | 60,000 men and boys sensitized on HCT, Treatment, VMMC, Condom use, gender equality and GBV. | 60,000 men and boys sensitized on HCT, Treatment, VMMC, Condom use, gender equality and GBV. | 60,000 men and boys sensitized on HCT, Treatment, VMMC, Condom use, gender equality and GBV. | 60,000 men and boys sensitized on HCT, Treatment, VMMC, Condom use, gender equality and GBV. | 60,000 men and boys sensitized on HCT, Treatment, VMMC, Condom use, gender equality and GBV. |
| **Outcome Target 5.3** | | | **50 % of rural and urban VSL groups equipped with business and value addition skills by 2021 (Baseline - )** | | | | |
| Output 1 | Delivery of economic empowerment programme improved | |  |  | VSL Training Manuals developed and 1000 printed and distributed | Economic Empowerment (Umodzi ndi Phindu) Training Manual reviewed and 1000 printed and distributed |  |
|  |  |  | 400 frontline workers trained in the VSL Training manuals | 400 frontline workers trained in the revised Economic Empowerment Training Manual |
|  | 1,000 rural and urban business groups trained in entrepreneurship | 1,000 rural and urban business groups trained in entrepreneurship | 1000 rural and urban business groups trained in entrepreneurship | 1000 rural and urban business groups trained in entrepreneurship |
|  | 500 VSL groups trained in leadership and financial education | 400 VSL groups trained in leadership and financial education | 300 VSL groups trained in leadership and financial education | 300 VSL groups trained in leadership and financial education |
|  |  | 10 cooperatives trained in effective business management and marketing skills | 10 cooperatives trained in effective business management and marketing skills | 10 cooperatives trained in effective business management and marketing skills |
|  |  | 300 business groups supported to access appropriate technology for value addition | 300 business groups supported to access appropriate technology for value addition |  |
|  | 2 VSL business groups’ products in local trade fairs promoted and marketed | 28 VSL business groups’ products in local trade fairs promoted and marketed | 28 VSL business groups’ products in local trade fairs promoted and marketed | 28 VSL business groups’ products in local trade fairs promoted and marketed |
|  |  | 10 business groups linked to Malawi Bureau of Standards for certification of products | 10 business groups linked to Malawi Bureau of Standards for certification of products |  |
|  |  | 2 trading houses established for rural entrepreneurs |  | 2 trading houses established for rural entrepreneurs |
| **Strategic Outcome 6** | | | **Improved institutional capacity and organizational efficiency** | | | | |
| **Outcome Target 6.1** | | | **90% of the programmes implemented efficiently and effectively by 2021 (Baseline 70%)** | | | | |
| **OUTPUT DESCRIPTION** | | | **OUTPUT TARGETS (PER FINANCIAL YEAR)** | | | | |
| **2016/2017** | **2017/2018** | **2018/2019** | **2019/2020** | **2020/2021** |
| Output 1 | Strategic plan developed and implemented | | Draft Strategic plan developed | Strategic Plan launched, disseminated and implemented | Strategic plan implemented | Strategic plan implemented | Strategic plan implemented & reviewed |
| Output 2 | Annual work plans prepared and implemented | | Annual work plan prepared and implemented | Annual work plan prepared and implemented | Annual work plan prepared and implemented | Annual work plan prepared and implemented | Annual work plan prepared and implemented |
| Output 3 | Budgets formulated and implemented | | Budget formulated and implemented | Budget formulated and implemented | Budget formulated and implemented | Budget formulated and implemented | Budget formulated and implemented |
| Output 4 | Service Charter developed and implemented | | Service Charter developed | Service charter Launched, disseminated and implemented | Service Charter implemented | Service Charter implemented | Service Charter implemented |
| Output 5 | Monitoring and Evaluation System developed and implemented | |  | Stakeholders consulted and TORs formulated | M&E framework developed and implemented | M&E framework implemented | M&E framework implemented and reviewed |
| Output 6 | Performance Contracts developed and implemented | | Performance Contract developed and implemented | Performance Contract developed and implemented | Performance Contract developed and implemented | Performance Contract developed and implemented | Performance Contract developed and implemented |
| Output 7 | 40 Project proposals developed and submitted to PSIP and Development Partners | | 6 Project proposals developed and approved | 8 Project proposals developed and submitted to PSIP and Development Partners | 8 Project proposals developed and submitted to PSIP and Development Partners | 8 Project proposals developed and submitted to PSIP and Development Partners | 8 Project proposals developed and submitted to PSIP and Development Partners |
| **Outcome Target 6.2** | | | **Vacancy rate reduced from 54% to 10% by 2021** | | | | |
| Output 1 | Human resource recruited and deployed | | 40 vacant posts filled | 65 vacant posts filled | 65 vacant posts filled | 65 vacant posts filled | 68 vacant posts filled |
| **Outcome Target 6.3** | | | **Institutional performance improved by 80% by 2021 (Baseline - )** | | | | |
| Output 1 | Training plan developed and implemented | | Training Needs Analysis conducted and Training plan developed and implemented | Training plan implemented | Training plan implemented | Training plan implemented | Training plan evaluated |
| Output 2 | Capacity of human resources enhanced | | 12 employees trained | 35 employees trained | 40 employees trained | 55 employees trained | 60 employees trained |
|  | All employees appraised on their performance | All employees appraised on their performance | All employees appraised on their performance | All employees appraised on their performance |
|  |  | |  | Functional review conducted | Establishment warrant granted | Staff recruited and deployed |  |
| **Outcome Target 6.4** | | | **ICT infrastructure in place and operational by 2021** | | | | |
| Output 1 | Management Information System developed | |  |  | MIS concept developed and resources mobilized | MIS developed | MIS operational |
| Output 2 | Website developed and operationalized | |  | Website developed | Website operational | Website operational | Website operational |
| Output 3 | Network facilities enhanced | |  | Security system upgraded | Security system upgraded | Security system upgraded | Security system upgraded |
| **Outcome Target 6.5** | | | **90% of administrative service provision achieved by 2021 (Baseline - )** | | | | |
| Output 1 | Coordination and networking enhanced | | 12 Management meetings held, minutes produced and shared | 12 Management meetings held, minutes produced and shared | 12 Management meetings held, minutes produced and shared | 12 Management meetings held, minutes produced and shared | 12 Management meetings held, minutes produced and shared |
| Physical asset management enhanced | | 60% of office services and supplies provided | 80% of office services and supplies provided | 90% of office services and supplies provided | 90% of office services and supplies provided | 90% of office services and supplies provided |
| Annual Procurement Plan developed and implemented | Annual Procurement Plan developed and implemented | Annual Procurement Plan developed and implemented | Annual Procurement Plan developed and implemented | Annual Procurement Plan developed and implemented |
| Inventory register prepared | Inventory register updated | Inventory register updated | Inventory register updated | Inventory register updated |
| **Outcome Target 6.6** | | | **HIV and AIDS , gender and disability issues mainstreamed in all programmes by 2021** | | | | |
| Output 1 | Cross-cutting issues mainstreamed in Ministry’s programmes | |  | HIV and AIDS work place committee instituted and issues mainstreamed in all programmes | HIV and AIDS issues mainstreamed in all programmes | HIV and AIDS issues mainstreamed in all programmes | HIV and AIDS issues mainstreamed in all programmes |
| 2% of monthly funding allocated to HIV and AIDS related activities | 2% of monthly funding allocated to HIV and AIDS related activities | 2% of monthly funding allocated to HIV and AIDS related activities | 2% of monthly funding allocated to HIV and AIDS related activities | 2% of monthly funding allocated to HIV and AIDS related activities |
|  | Gender and disability issues mainstreamed in all programmes | Gender and disability issues mainstreamed in all programmes | Gender and disability issues mainstreamed in all programmes | Gender and disability issues mainstreamed in all programmes |
|  | Waste disposal strategies developed | Waste disposal strategies implemented | Waste disposal strategies implemented | Waste disposal strategies implemented |
| **Outcome Target 6.7** | | | Financial processes in accordance with policies and regulatory requirements strengthened by 2021 | | | | |
| Output 1 | Financial management enhanced | | 50% of all payments processed on time | 70% of all payments processed on time | 90% of all payments processed on time | 90% of all payments processed on time | 90% of all payments processed on time |
| 12 monthly financial reports prepared and submitted by 14th of the following month | 12 monthly financial reports prepared and submitted by 14th of the following month | 12 monthly financial reports prepared and submitted by 14th of the following month | 12 monthly financial reports prepared and submitted by 14th of the following month | 12 monthly financial reports prepared and submitted by 14th of the following month |
| Financial, revenue and IPSAS reports prepared and submitted on time | Financial, revenue and IPSAS reports prepared and submitted on time | Financial, revenue and IPSAS reports prepared and submitted on time | Financial, revenue and IPSAS reports prepared and submitted on time | Financial, revenue and IPSAS reports prepared and submitted on time |
| Financial monitoring visits to cost centers conducted | Financial monitoring visits to cost centers conducted | Financial monitoring visits to cost centers conducted | Financial monitoring visits to cost centers conducted | Financial monitoring visits to cost centers conducted |
| Output 2 | 100 % Cost Centers audited | | Audit Framework developed and implemented | Audit Framework implemented | Audit Framework implemented | Audit Framework implemented | Audit Framework implemented |
| Audit queries responded to on time | Audit queries responded to on time | Audit queries responded to on time | Audit queries responded to on time | Audit queries responded to on time |

## 3.5 Strategic Plan Implementation Resource Requirements

Annex 4 shows an estimated cost of outputs for implementing the Strategic Plan. This has been derived from costing of all outputs that will assist the Ministry to achieve the intended outcomes. It is envisaged that the implementation of the Plan will largely be financed by Government through monthly subventions from Treasury and funding for specific projects through the Public Sector Investment Program (PSIP) and development partners. It is recognized that resources may not match all the needs of the Ministry as such; key intervention areas will be prioritized. Thus, the budget matrix appended below shows the resource requirements summarized and disaggregated at outcome, outcome target and output level.

## 3.6 The Results-Based Logical Framework

The Results-Based Logical Framework presented below is a quick tool that will be used to monitor and evaluate progress towards achievement of expected results, and is a handy reference of key components of our Strategic Plan. It gives a snapshot of the KRAs and desired outcomes. The framework will basically be used for monitoring and evaluating the achievement of the results through the given indicators and their means of verification.

|  |  |  |  |
| --- | --- | --- | --- |
| **KEY RESULT AREA 1: Civic Education** | | | |
| **Expected Results/Outcomes** | **Objectively Verifiable Indicator** | **Source and Means of Verification** | **Risks and Assumptions** |
| **1.0** Improved civic knowledge, management and coordination of civic education programmes | Percentage change in overlapping activities with other institutions | Monitoring and Evaluation reports | Insufficient funding to conduct review of conflicting policies |
| Percentage change in community participation in development & democratic processes | Monitoring and Evaluation reports | Communities not willing to participate |
| Percentage change in transformative & evidence-based education activities | Monitoring and Evaluation reports | Inadequate resources |
| **KEY RESULT AREA 2: Cultural Development** | | | |
| **2.0** Malawi’s national heritage in all its identifiable forms safeguarded and promoted for national identity, posterity and sustainable socio-economic development | Percentage of institutions mainstreaming cultural issues in their programmes | Implementation progress reports | Inadequate resources for monitoring |
| Percentage of institutions preserving tangible and intangible heritage | Joint sector review reports | Lack of funding for reviews |
| No. of public entertainment facilities, performances and articles regulated | Issuance of licenses and permits | Inadequate human and financial resources to enforce regulations |
| Percentage of cultural products showcased and marketed | Cultural exhibitions/shows and marketing reports | Lack of value addition and profiling to cultural products and services |
|  | No. of MDAs mainstreaming records management standards | Assessments reports | Limited resources for monitoring  Unwillingness of MDAs to mainstream records management standards |
| **3.0** Improved resource mobilization for cultural development | Percentage change in financial resources mobilized | Budget/Annual financial reports | Financial resources mobilized are re-invested in the sector |
| Percentage of critical human resource in the industry provided for. | Capacity development and recruitment reports | Trained members/staff retained in the industry  Inadequate specialized training opportunities for players in the industry |
| **KEY RESULT AREA 3: Community Development** | | | |
| **4.0** Increased community participation in development programmes and community based population education | Percentage of men, women, boys & girls participating in development programmes | Monitoring and Evaluation reports | Communities are willing to participate |
| Percentage change in literacy levels | Training reports | Willingness to enroll in adult literacy classes |
| No. of households mobilized in community based programmes | Community mobilization reports | Communities are sensitized |
| **5.0** Improved capacity of households to manage their livelihoods and nutritional wellbeing | No. of rural households targeted | Household survey reports | Inadequate resources to conduct survey |
| No. of rural & urban Village and Savings Loan groups equipped with skills | Capacity building reports | Sponsored trainings and initial capital provisions made available |
| **KEY RESULT AREA 4: Administration and Management** | | | |
| **6.0** Improved institutional capacity and organizational efficiency | No. of staff trained, promoted and deployed | Staff training, promotion and deployment reports | Adequate funding is provided |
| Vacancy reduction rate | Annual recruitment reports | Vacancies are reported and requisite personnel identified and filled |
| No. of cross-cutting issues mainstreamed | Institutional reports | Readiness of the Ministry to mainstream cross-cutting issues |
| Percentage change in administrative provisions | Finance and administration reports | Realistic budget developed, approved and funding levels adhered to |

**4.0 GOVERNANCE AND COORDINATION MECHANISMS FOR IMPLEMENTING THE STRATEGIC PLAN**

## 4.1 Overview

This section summarizes the Strategic Plan implementation arrangements which include; organizational or institutional arrangements, coordination mechanisms, risks and mitigation measures. The implementation of a Strategic Plan cannot happen in a vacuum; hence set out below are the institutional arrangements that provide guidance to the various organs that are expected to play critical roles in its implementation.

## 4.2 **Institutional Arrangements for Implementing the Plan**

The successful implementation of this Strategic Plan will depend on the following institutional arrangements:

1. Setup a Strategic Plan Implementation Committee (SPIC) to be chaired by the Director of Policy and Planning; and
2. The SPIC appoints an officer to act as its secretariat and to report on progress made;

The following are proposed ToRs for the SPIC: -

1. Report progress to the Secretary for Civic Education, Culture and Community Development on quarterly basis;
2. Ensure that each Department or Section develops its Annual Work Plan (AWP);
3. Ensure that the Strategic Plan is circulated to all relevant stakeholders as soon as it is finalized and launched; and
4. Receive and examine quarterly Departmental or Sectional reports on implementation progress.

## 4.3 Roles and Responsibilities of Management

The successful implementation of the Strategic Plan rests with the Principal Secretary (PS) and the Ministry’s senior management team. In this regard, the PS shall spearhead the implementation of the strategy. The strategic plan takes cognizance of Management’s roles at all levels.

Management shall take the sole responsibility of ensuring internalization and ownership of the vision, mandate, mission and strategic outcomes by all members of staff in the Ministry. This will be done by ensuring that the Strategic Plan is translated into Annual Work Plans. The AWP shall be reviewed quarterly and evaluated annually to ensure that resources are allocated and utilized effectively. In addition, Management shall also be responsible for:

1. Analyzing and reviewing consolidated data and reports;
2. Propose recommendations and corrective measures on the reviewed consolidated data and reports;
3. Participating in regular field monitoring visits; and
4. Organizing review meetings and external evaluations.

## 4.4 Risks and Mitigation Measures

The Ministry’s Strategic Plan envisages transition from the previous scenario where its programmes and activities were coordinated and implemented by other ministries. It is against this background that the Ministry has identified the following key risks that may affect the realization of its strategic outcomes.

|  |  |  |  |
| --- | --- | --- | --- |
| **No.** | **Risk** | **Consequences** | **Mitigation Measures** |
| 1. | Insufficient funds to implement plans | This may derail the implementation of programmes | Prioritize implementation of key activities that will generate quick wins for the attainment of its strategic outcomes. |
| 2. | Dependence on Development Partners’ resources | Reduced or no funding may negatively affect the overall service delivery and operations of the Ministry | Develop and implement a sustainable financial resource mobilization strategy |
| 3. | Weak collaboration with key stakeholders | Weak collaboration with key stakeholders could result into poor service delivery | Enhance engagement and collaboration with key stakeholders. |
| 4. | Weak coordination and communication within the Ministry and other institutions in the sector | Information gaps that may be detrimental to programmes implementation | Comprehensively sensitize the staff and stakeholders on the need for coordination, communication and team work as pre-requisites for effective implementation of its programmes |
| 5. | Poor publicity and knowledge about the Ministry | Some potential Development Partners may not be aware of the Ministry’s mandate and objectives | Set up a Public Relations Office and conduct awareness campaigns and develop a communications strategy |
| 6. | Lack of integrity in use of resources | Misappropriation and diversion of funds | Develop document and implement accountability systems in all areas of operation |

1. **CRITICAL SUCCESS FACTORS**

The Ministry is aware that there are certain critical elements that must be made available for the outcomes to be successfully attained and sustained. Critical Success Factors (CSF) may change overtime, hence the need to make necessary adjustments to the set targets. The following are some of the CSFs assumptions required to achieve the Ministry’s outcome targets:

## 5.1 Strategic Leadership

Leadership is the driving force for the accomplishment of any organization’s goals and objectives. It is therefore, imperative that the Ministry’s leadership is proactive; visionary; inspiring; accommodative of other people’s views; able to delegate responsibilities and committed to see through the implementation process.

* + 1. **Human Resource**

Human resource is very critical for any organization. The Ministry’s leadership shall ensure that well qualified human resource is recruited and trained to acquire core competencies to enable efficient and effective service delivery.

**5.1.2 Financial Resources**

All the activities of the Ministry will require financial resources for implementation. Therefore, the Ministry is expected to lobby for adequate financial resources from Treasury and Development Partners to match with the requirements of the planned outcome targets and the sustainability of its operations.

**5.1.3 Political Environment**

It is assumed that the current political environment will remain stable for the entire Strategic Plan implementation period and that the political leadership will continue supporting the activities of the Ministry.

**5.1.4 Supportive and Collaborative Stakeholders**

It is assumed that the Ministry will receive adequate support from its development partners.

# 6.0 MONITORING AND EVALUATION

Monitoring and Evaluation (M&E) is an ongoing process that provides regular feedback and early indications of whether interventions are making progress or not towards their intended objectives. This mechanism will be used to assess if the Ministry’s strategic outcomes and targets are being met. The process will track actual performance against the planned strategic outcomes.

## 6.1 Purpose and Scope

The purpose of M&E is to conduct performance monitoring by following up on the implementation and reviewing progress of work plans that reflect outputs to be achieved under each outcome. The progress or lack of progress collated is analyzed against the planned targets. The findings from the analysis will inform the Ministry on:

1. Budget decisions;
2. Gaps in the implementation of the Performance Contract; and
3. The need for corrective measures.

The reporting system will require each implementing unit in the Ministry to monitor its activities and prepare performance reports, which will be presented to management. Management will discuss the consolidated performance reports on a quarterly basis, after which an Annual Report will be presented to the Principal Secretary and the Performance Enforcement Department (PED) at OPC as annual progress report based on implementation of its Performance Contract.

# 7.0 FINANCIAL RESOURCES MOBILIZATION

In order for the Ministry to sustain its operations, financial resources must be made available to enable implementation of the Strategic Plan. As a new entity that has to establish its structures, huge initial financial outlay is required.

## 7.1 Rationale for Alternative Sources of Funding

MoCECCD is one of many MDAs that access funding from Treasury. However, this funding may not suffice to provide for all its operations. Therefore, the Ministry should explore other avenues to access and/or generate additional resources. Some plausible options for additional and sustainable sources of funding would require the Ministry to develop sound working relations with various Development Partners with interest in the areas of civic education, culture and community development. A mapping exercise will be undertaken detailing the focus areas of each partner and level of partnership with the Ministry.

# ANNEXES

## Annex 1: List of Members of the Planning Team

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **No.** | **Name** | **Designation** | **Organization** | **Tel/Cell** | **E-mail Address** |
| 1 | ABEL MWAMLIMA | DDHRM | DDRMD | 0999934324 | [wake.abel@gmail.com](mailto:wake.abel@gmail.com) |
| 2 | MPHATSO MSENDERO | PHRO | DHRMD | 0999603772 | [mphabena@gmail.com](mailto:mphabena@gmail.com) |
| 3 | BLESSINGS WALAWALA | CHIEF CURATOR | MoCECCD | 0999274637 | [denvar01@yahoo.com](mailto:denvar01@yahoo.com) |
| 4 | CHARLES MKUNGA | CHIEF DCD | MoCECCD | 0999797882 | [charlesmkunga@yahoo.com](mailto:charlesmkunga@yahoo.com) |
| 5 | CHRIS MBUKWA | PRINCIPAL ECONOMIST | MoCECCD | 0992 782 100 | [chrismbukwa@yahoo.co.uk](mailto:chrismbukwa@yahoo.co.uk) |
| 6 | ASHRAF BANDA | PRINCIPAL ECONOMIST | MoCECCD | 0993 678 644 | [Ashba@gmail.com](mailto:Ashba@gmail.com) |
| 7 | PATIENCE CHAMKAKALA | PAO | MoCECCD | 0888850011 | [petmamba@gmail.com](mailto:petmamba@gmail.com) |
| 8 | GANIZANI NKHWAZI | ECONOMIST | MoCECCD | 0994379439 | [nkhwazi3rd@gmail.com](mailto:nkhwazi3rd@gmail.com) |
| 9 | MADALO WAWANYA | ECONOMIST | MoCECCD | 0998952086 | [wamadalo@yahoo.com](mailto:wamadalo@yahoo.com) |
| 10 | ALICK KAMPEZA | CEO | MoCECCD | 0999323025 | [akampeza@gmail.com](mailto:akampeza@gmail.com) |
| 11 | MTISUNGE KHEMBO | PLANNING OFFICER | MoCECCD | 088473665 | [khembomtisunge@gmail.com](mailto:khembomtisunge@gmail.com) |
| 12 | ALICE KANYANGALA | PLANNING OFFICER | MoCECCD | 0999335705 | [Alicekanyangala@gmail.com](mailto:Alicekanyangala@gmail.com) |
| 13 | FISYANI KALUWA | PLANNING OFFICER | MoCECCD | 0999959409 | [fisyanikaluwa@gmail.com](mailto:fisyanikaluwa@gmail.com) |
| 14 | PEMPHERO JEKETE | PLANNING OFFICER | MoCECCD | 0991284944 | [pjekete@gmail.com](mailto:pjekete@gmail.com) |

## 

## Annex 2: List of Participants who participated in the Strategic Planning

| **No.** | **Name** | **Designation** | **Ministry/Department** | **Tel/Cell Phone** | **E-mail Address** |
| --- | --- | --- | --- | --- | --- |
| **1** | IVY J. LUHANGA | PS | MoCECCD | 0888323509 | [iluhanga@yahoo.com](mailto:iluhanga@yahoo.com) |
| **2** | ESMIE T. KAINJA, PHD | PS | MoGCDSW | 0997044924 | [esmie.kainja@gmail.com](mailto:esmie.kainja@gmail.com) |
| **3** | ABEL MWAMLIMA | DDHRM | DDRMD | 0999934324 | [wake.abel@gmail.com](mailto:wake.abel@gmail.com) |
| **4** | SYMON MALIKO | DS | MoCECCD | 0888552478 | [symonmaliko@gmail.com](mailto:symonmaliko@gmail.com) |
| **5** | ELIZABETH CHINDEBVU GOMANI | DoMM | MoCECCD | 0996195842 | [egomanichindebvu@yahoo.com](mailto:egomanichindebvu@yahoo.com) |
| **6** | COTILDA SAWASAWA | DoCD | MoCECCD | 0995709292 | [cosawasawa5@yahoo.com](mailto:cosawasawa5@yahoo.com) |
| **7** | P. LIHOMA | DDNRAS | MoCECCD | 0997072377 | [plihoma@yahoo.com](mailto:plihoma@yahoo.com) |
| **8** | P. KALIBA | DDMM | MoCECCD |  | [pkaliba@yahoo.com](mailto:pkaliba@yahoo.com) |
| **9** | HUMPHREY MPONDAMINGA | DEPUTY DIRECTOR | MoCECCD | 0881959 902 | [humphrey.mpondaminga@hotmail.com](mailto:humphrey.mpondaminga@hotmail.com) |
| **10** | CHRISSY CHIUMIA | DDMM | MoCECCD | 0995825302 | [cchiumia@gmail.com](mailto:cchiumia@gmail.com) |
| **11** | DALITSO CHIKWEMBANI | CHIEF CIVIC EDUCATION OFFICER | MoCECCD | 0999511534 | [dchikwembani@gmail.com](mailto:dchikwembani@gmail.com) |
| **12** | ROZARIO KAMANGA | PROGRAM MANAGER | COSOMA | 0999314831 | [rkamanaga@cosoma.mw](mailto:rkamanaga@cosoma.mw) |
| **13** | EDWIN MSEWA | PROJECT OFFICER | NICE | 0996292333 | [gkalindekafe@yahoo.com](mailto:gkalindekafe@yahoo.com) |
| **14** | A. NGALAWANGO | CHRMO | MoCECCD | 0999955342 | [ahmedwango@yahoo.com](mailto:ahmedwango@yahoo.com) |
| **15** | RONALD PHIRI | CCDO | MoCECCD | 0999233599 | [ronaldphiri8@gmail.com](mailto:ronaldphiri8@gmail.com) |
| **16** | AUBERT MKWAWIRA | CCDO | MoCECCD | 0995501359 | [admkwawira@gmail.com](mailto:admkwawira@gmail.com) |
| **17** | ADAMSON CHAKANIKA | CCDO | MOCECCD | 0995606830 | [chakanika@agmail.com](mailto:chakanika@agmail.com) |
| **18** | CHARLES MKUNGA | CCDO | MoCECCD | 0999797882 | [charlesmkangala@yahoo.com](mailto:charlesmkangala@yahoo.com) |
| **19** | MR. MATAYATAYA | CCDO | MoCECCD | 0999797882 | [matayavp@gmail.com](mailto:matayavp@gmail.com) |
| **20** | Z. MWANDIRA | CCDO | MoCECCD | 0888355910 | [zmwandira@yahoo.com](mailto:zmwandira@yahoo.com) |
| **21** | ANGANILE NTHAKOMWA | CCSO | MoCECCD | 0999858514 | [anganile2007@gmail.com](mailto:anganile2007@gmail.com) |
| **22** | MC DONALD MALUAWAYA | CHIEF ARTS OFFICER | MoCECCD | 0888878940 | [mjmaluwaya@gmail.com](mailto:mjmaluwaya@gmail.com) |
| **23** | BLESSINGS WALAWALA | CHIEF CURATOR | MoCECCD | 0999274637 | [denvar1@yahoo.co.uk](mailto:denvar1@yahoo.co.uk) |
| **24** | LIONEL NGUMUYA | CHIEF ARCHIVIST | MoCECCD | 0888608142 | [lionelngunazi@gmail.com](mailto:lionelngunazi@gmail.com) |
| **25** | WILLIAM MALIMERO | PCEO | MoCECCD | 0888497172 | [williammalimero@gmail.com](mailto:williammalimero@gmail.com) |
| **26** | PATIENCE CHAMKAKALA | ADMINISTRATOR | MoCECCD | 0888850011 | [petmamba@gmail.com](mailto:petmamba@gmail.com) |
| **27** | MPHATSO MSENDERO | PHRMO | DHMRD | 0999603772 | [mphabena@gmail.com](mailto:mphabena@gmail.com) |
| **28** | CHRIS MBUKWA | PRINCIPAL ECONOMIST | MoCECCD | 0992782100 | [chrismbukwa@yahoo.co.uk](mailto:chrismbukwa@yahoo.co.uk) |
| **29** | ASHRAF BANDA | PRINCIPAL ECONOMIST | MoCECCD | 0888497172 | [ashba2020@gmail.com](mailto:ashba2020@gmail.com) |
| **30** | GANIZANI NKHWAZI | ECONOMIST | MoCECCD | 0994379439 | [Nkhwazi3rd@gmail.com](mailto:Nkhwazi3rd@gmail.com) |
| **31** | MADALO WAWANYA | ECONOMIST | MoCECCD | 0998952086 | [wamadalo@yahoo.com](mailto:wamadalo@yahoo.com) |
| **32** | VICTOR GONDWE | CSO | MoCECCD | 0999385394 | [Gondwe.victor@yahoo.com](mailto:Gondwe.victor@yahoo.com) |
| **33** | CHRSIPIN KALAYA | CIVIC EDUCATION OFFICER | MoCECCD | 0999466741 | [cakalaya@gmail.com](mailto:cakalaya@gmail.com) |
| **34** | ALICK KAMPEZA | CEO | MoCECCD | 0999323025 | [akampeza@gmail.com](mailto:akampeza@gmail.com) |
| **35** | YOHANE NYIRENDA | CHIEF CURATOR | MoCECCD | 0888842755 | [yenyirenda@gmail.com](mailto:yenyirenda@gmail.com) |
| **36** | H.H. SIMFUKWE | SAO | MoCECCD | 0888861014 | [simfukwe.harrison@gmail.com](mailto:simfukwe.harrison@gmail.com) |
| **37** | INNOCENT MANKHWALA | ARCHIVES | MoCECCD | 0888662550 | [ihsmankhwala@gmail.com](mailto:ihsmankhwala@gmail.com) |
| **38** | CLEMENT MWESO | ARCHIVIST | MoCECCD | 0999368898 | [cmweso@gmail.com](mailto:cmweso@gmail.com) |
| **39** | STELLA TSIGA | CDO | MoCECCD |  | [tswazipsiga@gmail.com](mailto:tswazipsiga@gmail.com) |
| **40** | MTISUNGE KHEMBO | PLANNING OFFICER | MoCECCD | 088473665 | [khembomtisunge@gmail.com](mailto:khembomtisunge@gmail.com) |
| **41** | TOPSY KACHERE | DCDO | MoCECCD | 0888614959 | [kacheretopsy@yahoo.com](mailto:kacheretopsy@yahoo.com) |
| **42** | EMMANUEL KASOMPHE | DCDO | MoCECCD | 0999192999 | [kasompheec@gmail.com](mailto:kasompheec@gmail.com) |
| **43** | PHILLIP MPONDA BANDA | DCDO | MoCECCD | 0888314629 | [pgillipmpondabanda@gmaiol.com](mailto:pgillipmpondabanda@gmaiol.com) |
| **44** | ALICE KANYANGALA | PLANNING OFFICER | MoCECCD | 0999335705 | [Alicekanyangala@gmail.com](mailto:Alicekanyangala@gmail.com) |
| **45** | FISYANI KALUWA | PLANNING OFFICER | MoCECCD | 0999959409 | [fisyanikaluwa@gmail.com](mailto:fisyanikaluwa@gmail.com) |
| **46** | PEMPHERO JEKETE | PLANNING OFFICER | MoCECCD | 0991284944 | [pjekete@gmail.com](mailto:pjekete@gmail.com) |

## Annex 3: List of Reference Materials consulted

|  |  |
| --- | --- |
| Item No. | Reference |
| 1 | Government of Malawi, Ministry of Finance, Economic Planning and Development: Malawi Growth and Development Strategy III (MGDS III) |
| 2 | Government of Malawi (2015), AIDS Response Progress Report |
| 3 | Ministry of Gender, Children, Disability and Social Welfare Strategic Plan |
| 4 | Ministry of Information and Communications Technology Strategic Plan |
| 5 | Sustainable Development Goals |
| 6 | National Cultural Policy |
| 7 | National Community Development Policy |
| 8 | Draft Civic Education Policy |
| 9 | Draft Adult Literacy Policy |
| 10 | Draft Record Management Policy |

###### ANNEX 4: Resource requirements summarized and disaggregated at outcome, outcome target and output level

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Key Result Area: Civic Education | | **Strategic Outcome 1: Improved Civic Knowledge, Management And Coordination of Civic Education Programme** | | | | | | | |
| Outcome Target | **Related Outputs** | **Output Indicator** | **Total Targets** | **Estimated Cost ‘000** | | | | | |
|  |  |  |  | **2016/2017** | **2017/2018** | **2018/2019** | **2019/2020** | **2020/2021** | **TEC** |
| 50% Reduction in duplication of civic education activities by 2021 | 1.1.1 National Civic Education Policy developed and implemented by 2020 | Policy developed and implemented | 1 | 1,732,500.00 | 19,057,500.00 | 10,963,250.00 | 23,059,575.00 | 25,365,532.50 | **80,178,357.50** |
| 1.1.2 National civic education forum established by 2021 | National civic education Forum in place | 1 |  |  | 8,851,150.00 | 2,736,265.00 | 10,709,891.50 | **22,297,306.50** |
| 1.1.3 Civic education in government MDAs identified coordinated | Number of civic education activities identified and coordinated |  |  | 10,279,500.00 | 11,307,450.00 | 12,438,195.00 | 13,682,014.00 | **47,707,159.00** |
| 1.1.4 Stakeholders Strategic Plans aligned to Civic Education Policy | Number of Stakeholders Strategic Plans aligned to Civic Education Policy |  |  |  |  | 11,479,875.00 | 12,627,862.00 | **24,107,737.00** |
| 70% of enhanced popular participation in development processes | 1.2.1 Formative research conducted and report produced | Number of formative researches conducted | 2 |  |  | 16,394,850.00 |  | 16,737,768.00 | **33,132,618.00** |
| 1.2.2 Civic education officers oriented on how to conduct Civic Education activities (Trainer of trainers) | Number of regional orientation workshops conducted | 3 |  | 9,000,000.00 | 9,900,000.00 | 10,890,000.00 |  | **29,790,000.00** |
| 1.2.3 People sensitized on various social issues through interactive film shows | Number of people sensitized | 2,040,000 | 5,880,000.00 | 8,468,000.00 | 9,468,000.00 | 10,468,000.00 | 11,608,908.00 | **45,892,908.00** |
|  | 1.2.4 People sensitized on topical issues through community dialogue sessions | Number of community dialogue sessions conducted | 19,440 | 14,680,000.00 | 16,148,000.00 | 17,762,800.00 | 19,539,080.00 | 21,492,988.00 | **89,622,868.00** |
| 1.2.5 DCs and ADCs sensitized on the importance of community participation in development programmes | Number of committee sensitized | 196 |  | 9,633,800.00 | 10,597,180.00 | 11,656,898.00 | 12,822,587.80 | **44,710,465.80** |
| 1.2.6 IEC promotion materials on development processes produced and disseminated | Number of IEC materials produced and disseminated | 81,035 | 19,225,000.00 | 24,147,500.00 | 20,225,000.00 | 20,225,000.00 | 21,147,322.50 | **104,969,822.50** |
| 80% enhanced popular participation in democratic processes by 2021 | 1.3.1 People mobilized for civic education on governance issues through interactive film shows | Number of people sensitized | 2,040,000 | 5,880,000.00 | 8,468,000.00 | 9,468,000.00 | 10,468,000.00 | 11,608,908.00 | **45,892,908.00** |
| 1.3.2 People sensitized on governance issues through community dialogue sessions | Number of people sensitized | 19,440 | 16,300,000.00 | 17,930,000.00 | 19,723,000.00 | 21,695,300.00 | 23,864,830.00 | **99,513,130.00** |
| 1.3.3 28 District Councils and 168 ADCs sensitized on governance issues. | Number of development committees' sensitized | 196 | 8,475,000.00 | 10,322,500.00 | 11,254,750.00 | 11,880,225.00 | 12,408,247.50 | **54,340,722.50** |
| 1.3.4 IEC promotional materials on governance issues produced and disseminated | Number of IEC materials produced and disseminated | 81,035 | 19,225,000.00 | 24,147,500.00 | 20,225,000.00 | 20,225,000.00 | 21,147,322.50 | **104,969,822.50** |
| 1.4 80% transformative and evidence based civic education activities conducted by 2021 | 1.4.1 Appreciative enquiry sessions conducted | Number of enquiry sessions conducted | 9 |  | 2,668,000.00 | 4,534,800.00 | 4,988,280.00 | 6,537,108.00 | **18,728,188.00** |
|  | 1.4.2 Star performers and role models Increased | Number of star performers and models | 17 |  | 2,871,000.00 | 3,158,100.00 | 4,473,910.00 | 5,821,301.00 | **16,324,311.00** |
|  | 1.4.3 Civic education resources centers established | Number of resource centers established | 2 |  |  | 428,086,350.00 |  | 540,984,483.50 | **969,070,833.50** |
| **Sub - Total** |  |  |  | **91,397,500.00** | **163,141,300.00** | **611,919,680.00** | **196,223,603.00** | **768,567,074.80** | **1,831,249,157.80** |
| **Key Result Area 2:** **Cultural Development** | | **Strategic Outcome 2:** **Malawi’s national heritage in all its identifiable forms safeguarded and promoted for national identity, posterity and sustainable socio-economic development** | | | | | | | |
| 2.1 50% of key stakeholder institutions mainstreaming cultural issues in their programmes by 2021 | 2.1.2 Key stakeholder institutions oriented on mainstreaming of culture in their programme | Number of key stakeholder institutions oriented | 195 | 6,100,000.00 | 9,760,000.00 | 10,736,000.00 | 11,809,600.00 | 12,990,560.00 | **51,396,160.00** |
| 2.1.4 Institutions focal persons trained in mainstreaming culture in programmes | Number of institutions focal persons trained | 180 |  | 8,784,000.00 | 9,662,400.00 | 10,628,640.00 | 11,691,504.00 | **40,766,544.00** |
| 2.2 80% of key institutions involved in preserving tangible and intangible cultural heritage provided with technical know-how by 2021 | 2.2.1 Institutions oriented on cultural heritage | Number of institutions oriented on cultural heritage | 100 | 6,450,000.00 | 7,095,000.00 | 7,804,500.00 | 8,584,950.00 | 9,443,445.00 | **39,377,895.00** |
| 2.2.2 Community groups mobilized in cultural heritage preservation | Number of community groups mobilized | 204 | 6,750,000.00 | 7,425,000.00 | 8,167,500.00 | 8,984,250.00 | 9,882,675.00 | **41,209,425.00** |
| 2.2.3 Movable and immovable cultural heritage maintained | Number of cultural heritage sites maintained | 27 | 37,750,000.00 | 41,525,000.00 | 45,677,500.00 | 50,245,250.00 | 55,269,775.00 | **230,467,525.00** |
|  |  |  |  |  |  |  |  |  |
| 2.2.4 Pieces of cultural legislation reviewed | Number of pieces of cultural legislation reviewed | 5 | 13,820,000.00 | 15,202,000.00 | 16,722,200.00 | 18,394,420.00 | 20,233,862.00 | **84,372,482.00** |
| 2.3 50% of information on cultural issues collected, processed and disseminated by 2021 | 2.3.1 Research on various aspects of culture conducted | Number of researches conducted | 10 | 16,250,000.00 | 24,375,000.00 | 34,125,000.00 | 37,537,500.00 | 17,875,000.00 | **130,162,500.00** |
|  | 2.3.2 Databank for Culture developed | Number of databanks developed and populated | 1 |  | 11,110,000.00 | 12,221,000.00 |  | 14,787,410.00 | **38,118,410.00** |
| 2.3.3 Awareness programs on cultural issues conducted | Number of awareness programs conducted and coordinated | 13 | 11,230,000.00 | 15,722,000.00 | 17,294,200.00 | 19,023,620.00 | 20,925,982.00 | **84,195,802.00** |
| 2.4 20% of cultural and heritage industry's capacity strengthened by 2021 | 2.4.1 Stakeholders equipped with cultural and conservation skills | Number of stakeholders equipped with cultural and conservation skills | 450 | 11,100,000.00 | 18,870,000.00 | 20,757,000.00 | 22,832,700.00 | 25,115,970.00 | **98,675,670.00** |
| 2.4.2 Grant schemes for culture practitioners introduced | Number of grant schemes introduced | 2 |  | 20,295,000.00 |  | 24,556,950.00 | 4,911,390.00 | **49,763,340.00** |
| 2.4.3 Cultural industry coordination structure established | National Arts Heritage Council (NAHeC) Bill enacted | 1 |  |  | 8,713,300.00 |  | 26,543,093.00 | **35,256,393.00** |
| 2.4.4 Cultural heritage infrastructure rehabilitated and developed | Number of infrastructure rehabilitated and developed | 32 | 40,000,000.00 | 160,000,000.00 | 80,000,000.00 | 88,000,000.00 | 96,800,000.00 | **464,800,000.00** |
| 2.4.5 Cultural industry and heritage events facilitated promoted | Number of events facilitated and hosted | 125 | 15,450,000.00 | 16,995,000.00 | 18,694,500.00 | 20,563,950.00 | 22,620,345.00 | **94,323,795.00** |
| 2.4.6 Cultural industry and heritage production centers developed | Number of centers developed | 2 |  |  | 50,000,000.00 | 20,000,000.00 | 23,000,000.00 | **93,000,000.00** |
| 2.4.7 Cultural heritage sites developed and marketed | Number of heritage sites marketed | 5 |  | 16,885,000.00 | 18,573,500.00 | 20,430,850.00 | 22,473,935.00 | **78,363,285.00** |
| 2.5 40% improvement in good records management practices by 2021 | 2.5.1 National Records Management Policy developed and implemented | Policy developed and implemented | 1 |  | 18,000,000.00 | 32,000,000.00 | 14,000,000.00 | 12,000,000.00 | **76,000,000.00** |
|  | 2.5.2 Records management registry personnel from the public sector trained in proper records management practices | Number of records management registry personnel from the public sector trained | 1000 | 23,795,700.00 | 36,175,270.00 | 28,792,797.00 | 31,672,076.70 | 34,839,284.37 | **155,275,128.07** |
| 2.5.3 Records retention and disposal schedules for selected MDAs reviewed | Number of records retention and disposal schedules for selected MDAs reviewed | 10 | 26,278,000.00 | 28,905,800.00 | 31,796,380.00 | 34,976,018.00 | 38,473,619.80 | **160,429,817.80** |
| 2.5.4 MDAs mainstreaming proper records management standards and compliance to records management practices | Number of MDAs mainstreaming proper records management standards and compliance to records management practices | 250 | 14,000,000.00 | 15,400,000.00 | 16,940,000.00 | 18,634,000.00 | 20,497,400.00 | **85,471,400.00** |
| 2.5.5 Historical 16mm cinematographic films digitized | Number of historical 16mm cinematographic films digitized | 250 | 530,000.00 | 583,000.00 | 641,300.00 | 705,430.00 | 775,973.00 | **3,235,703.00** |
| 2.6 80% of the country’s literature output collected and preserved by 2021 | 2.6.1 Printed and published works in Malawi collected and preserved in National Archives | Number of printed and published works in Malawi collected and preserved in National Archives | 5000 | 1,350,000.00 | 1,485,000.00 | 1,633,500.00 | 1,796,850.00 | 1,976,535.00 | **8,241,885.00** |
| 2.8 Malawi’s cultural heritage and public morals protected, preserved and promoted by 2021 | 2.7.1 Film distributors, producers and entertainment facilities regulated | Number of Film distributors, producers and entertainment facilities regulated | 2511 | 11,160,000.00 | 12,276,000.00 | 13,503,600.00 | 14,853,960.00 | 16,339,356.00 | **68,132,916.00** |
| 2.7.2 Film industry and publications regulated | Number of film industry and publications regulated | 43,560 | 21,380,000.00 | 23,518,000.00 | 25,869,800.00 | 28,456,780.00 | 31,302,458.00 | **130,527,038.00** |
| **Sub - Total** |  |  |  | **263,393,700.00** | **510,386,070.00** | **510,325,977.00** | **506,687,794.70** | **550,769,572.17** | **2,341,563,113.87** |
| Strategic Outcome 3: Improved resource mobilization for cultural development | | | | | | | | | |
| 50% of financial resources in the cultural and heritage industry mobilized | 3.1.1 Cultural industry resource mobilization strategy developed | Number of Cultural industry resource mobilization strategy developed | 1 |  | 5,775,000 | 6,352,500 | 6,987,750 | 7,686,525 | **26,801,775.00** |
| 3.1.2 Stakeholders in the cultural industry trained in financial resources mobilization and management skills | Number of stakeholders trained in financial resources mobilization and management skills | 550 |  | 5,775,000 | 6,352,500 | 6,987,750 | 7,686,525 | **26,801,775.00** |
| Outcome Target 3.2: 50% of natural resource users in the cultural and heritage industry sensitized on natural resource management by 2021 | 3.2.1 Natural resources management challenges within the cultural industry documented | Documentation of natural resources management challenges | 1 |  | 3,190,000 |  |  |  | **3,190,000.00** |
| **Sub - Total** |  |  |  | **-** | **14,740,000.00** | **12,705,000.00** | **13,975,500.00** | **15,373,050.00** | **56,793,550.00** |
| **Key Result Area: Community Development** | | | | | | | | | |
| Strategic Outcome 4: Increased community participation in development projects and community based population education | | | | | | | | | |
| 50% of men and women, boys and girls actively participating in community based development projects by 2021 | Community Development Policy developed | Policy developed | 1 |  | 11,000,000.00 | 16,500,000.00 | 12,000,000.00 | 6,000,000.00 | **45,500,000.00** |
| Community development leaders skills enhanced | Number of community development leaders trained | 7520 | 14,200,000.00 | 25,560,000.00 | 28,116,000.00 | 30,927,600.00 | 27,834,840.00 | **126,638,440.00** |
| Delivery of Community mobilization and capacity building services enhanced | Community mobilization and capacity building services offered |  |  | 18,200,000.00 | 20,020,000.00 | 22,022,000.00 | 24,224,200.00 | **84,466,200.00** |
| Awareness of Community development programmes enhanced | Number of commemoration events facilitated | 3 | 20,450,000.00 | 22,495,000.00 | 24,744,500.00 | 27,218,950.00 | 29,940,845.00 | **124,849,295.00** |
|  | Networking and coordination of community development programmes enhanced | Number of community development technical working groups meetings conducted and international conferences patronized | 21 | 12,000,000.00 | 18,500,000.00 | 20,165,000.00 | 21,979,850.00 | 23,958,036.50 | **96,602,886.50** |
| Capacity of Community development staff enhanced | Number of staff trained in community and social protection | 240 |  | 48,000,000.00 | 52,800,000.00 | 58,080,000.00 | 63,888,000.00 | **222,768,000.00** |
| Capacity of community development institutions improved | Number of community development institutions rehabilitated | 6 |  | 130,000,000.00 | 250,000,000.00 | 150,000,000.00 | 120,000,000.00 | **650,000,000.00** |
| Community leaders and members mobilized to contribute and actively participate in the implementation of self-help and donor funded projects | Number of community leaders and members mobilized | 9749 |  | 14,000,000.00 | 9,340,000.00 | 10,340,000.00 |  | **33,680,000.00** |
| 60% of untrained community leaders and village development committee members equipped with leadership and management skills | Community leaders’ skills in leadership and management enhanced | Number of community leaders with leadership skills enhanced | 6660 | 6,435,000.00 | 8,365,500.00 | 10,875,150.00 | 14,137,695.00 | 18,379,003.50 | **58,192,348.50** |
| **Sub - Total** |  |  |  | **53,085,000.00** | **296,120,500.00** | **432,560,650.00** | **346,706,095.00** | **314,224,925.00** | **1,442,697,170.00** |
| **Strategic Outcome 4: Increased community participation in development projects and community based population education** | | | | | | | | | |
| 4.3 Literacy levels for adults and youth increased by 16 % by 2021 | National Adult Literacy Policy Developed and implemented | Policy developed and implemented | 1 |  | 8,000,000.00 | 22,000,000.00 | 12,000,000.00 | 8,000,000.00 | **50,000,000.00** |
| Delivery of adult literacy program improved | Number of ABL volunteer instructors trained | 16000 | - | 48,500,000.00 | 50,078,500.00 | 52,785,000.00 | 58,500,000.00 | **209,863,500.00** |
| Number FLINT manual reviewed | 1 | 13,168,750.00 | - | - | - | - | **13,168,750.00** |
| Number of manuals printed | 500 | 6,250,000.00 | - | - | - | - | **6,250,000.00** |
|  |  | Number of district officers oriented | 400 | - | - | 92,750,000.00 | - | - | **92,750,000.00** |
| Number of supervisory visits conducted | 20 | 10,000,000.00 | 10,000,000.00 | 10,000,000.00 | 10,000,000.00 | 10,000,000.00 | **50,000,000.00** |
| Number of push bikes and motor vehicles procured | 12102 | 7,500,000.00 | 420,000,000.00 | 300,000,000.00 | 300,000,000.00 | 31,500,000.00 | **1,059,000,000.00** |
| Number of assorted equipment procured and maintained | 8 | 42,720,000.00 | 42,720,000.00 | 42,720,000.00 | 42,720,000.00 | 42,720,000.00 | **213,600,000.00** |
| Number of TV and radio programs produced and aired | 3 | 81,080,000.00 | 81,080,000.00 | 81,080,000.00 | 81,080,000.00 | 81,080,000.00 | **405,400,000.00** |
| Number of equipment procured and maintained | 15 | 12,000,000.00 | 12,000,000.00 | 12,000,000.00 | 500,000.00 | 500,000.00 | **37,000,000.00** |
| Number of assorted ABL instructional materials procured and distributed | 540,000 | 30,325,000.00 | 42,325,000.00 | 44,325,000.00 | 48,325,000.00 | 50,325,000.00 | **215,625,000.00** |
| Number of volunteer male and female oriented | 2,400 | 82,000,000.00 | 41,000,000.00 | 41,000,000.00 | 41,000,000.00 | 41,000,000.00 | **246,000,000.00** |
| Number of coordination meetings | 20 | 4,920,000.00 | 4,920,000.00 | 4,920,000.00 | 4,920,000.00 | 4,920,000.00 | **24,600,000.00** |
| Number of CDAs oriented in English curriculum | 520 | 58,800,000.00 | 36,750,000.00 | - | - | - | **95,550,000.00** |
| Number of male and female instructors trained in adult literacy curriculum | 4,900 | 61,751,020.40 | 82,334,693.88 | 82,334,693.88 | 123,502,040.81 | 154,377,551.02 | **504,299,999.99** |
| Number of adult literacy centers opened | 4,900 | 28,744,897.95 | 38,326,530.61 | 38,326,530.61 | 57,489,795.92 | 71,862,244.90 | **234,749,999.99** |
| Number of male and female ABL graduates linked to vocational and entrepreneurial skills | 800,000 | 975,000.00 | 1,462,500.00 | 1,950,000.00 | 2,437,500.00 | 2,925,000.00 | **9,750,000.00** |
| Number writers workshops conducted | 2 | 9,388,750.00 | - | - | - | - | **9,388,750.00** |
|  |  | Number of easy to read materials printed and distributed | 112,500 | 14,450,000.00 | 14,450,000.00 | 14,450,000.00 | 14,450,000.00 | 14,450,000.00 | **72,250,000.00** |
| Number of rural information centers established | 4,000 |  |  | 32,000,000.00 | 48,000,000.00 | 64,000,000.00 | **144,000,000.00** |
| Number or instructional materials for English Literacy Instructors procured | 230,000 | 31,065,000.00 | 32,065,000.00 | 36,065,000.00 | 37,065,000.00 | 38,065,000.00 | **174,325,000.00** |
| Number consultants identified to formulate M and E | 1 | 11,430,000.00 | - | - | - | - | **11,430,000.00** |
| Number of computer sets procured for M and E | 40 | 32,000,000.00 | - | - | - | - | **32,000,000.00** |
| Number of adult literacy officers oriented on M and E system | 60 | 10,455,000.00 | - | - | - | - | **10,455,000.00** |
| **Sub - Total** |  |  |  | **549,023,418.35** | **915,933,724.49** | **905,999,724.49** | **876,274,336.73** | **674,224,795.92** | **3,921,455,999.98** |
| **Key Result Area: Community Development** | | **Strategic Outcome 4: Increased community participation in development projects and community based population education** | | | | | | | |
| 4.5.1 80% of the target population mobilized in Community Based Population Education Program by 2021 | Strategy and guidelines for implementation of Community Population Education Programme developed, printed and disseminated | Number of strategy and guidelines developed | 1 |  | 32,585,000.00 |  |  |  | **32,585,000.00** |
|  | Number of strategy and guidelines printed and disseminated | 1000 |  | 48,440,000.00 |  |  |  | **48,440,000.00** |
| Community based Population Education (Sex and Sexuality education) Manual reviewed, printed and disseminated | Number of Community based Population Education (Sex and Sexuality education) Manuals reviewed printed and disseminated | 4000 |  | 33,812,500.00 | 33,812,500.00 |  |  | **67,625,000.00** |
|  | Trainers trained on delivery of sexuality education | Number of Trainers trained on delivery of sexuality education | 400 |  | 34,500,000.00 | 36,500,000.00 |  |  | **215,000,000.00** |
| Assorted Training equipment procured/ produced | Number of Assorted Training equipment procured/ produced | Assorted |  | 15,733,333.00 |  | 17,866,667.00 |  | **33,600,000.00** |
| Community based Population Education (Sex and Sexuality education) radio programmes and films reviewed, 200 produced and disseminated | Number of Community based Population Education (Sex and Sexuality education) radio programmes and films produced and disseminate | 200 |  | 30,547,500.00 |  | 30,547,500.00 |  | **61,095,000.00** |
| Community leaders sensitized on Community Population Education Programme | Number of Community leaders sensitized on Community Population Education Programme | 2000 |  | 10,125,400.00 | 10,125,400.00 | 10,125,400.00 | 10,125,400.00 | **40,500,000.00** |
| Monitoring of Community based Population Education Programme enhanced | Number of Monitoring frameworks for Community based Population Education Programme developed and number of visits done monitoring frameworks for Community based Population Education Programme developed and number of visits done |  |  | 61,380,000.00 | 29,101,667.00 | 29,101,667.00 | 29,101,667.00 | **148,685,000.00** |
| 5.2 80% of the target population sensitized on enhanced HIV AIDS education by 2021 | Girls, boys, men and women sensitized on sexuality education | Number of Girls, boys, men and women sensitized on sexuality education | 2,000,000 |  | 20,250,000.00 | 20,250,000.00 | 20,250,000.00 | 20,250,000.00 | **105,000,000.00** |
| **Sub - Total** |  |  |  | - | **287,373,733.00** | **129,789,567.00** | **107,891,234.00** | **59,477,067.00** | **752,530,000.00** |
| **Strategic Outcome 5: Improved capacity of households to manage their livelihoods and nutrition wellbeing** | | | | | | | | | |
| 5.1 60% of households targeted with home management and nutrition interventions | Community resilience, Nutrition and Home Management Manual and Demonstration Guides finalized printed and distributed | Number of Manual and Demonstration guides finalized |  | 13,920,000 |  |  |  |  | **13,920,000.00** |
|  | Number of Manual and Demonstration guides printed and distributed | 2000 | 9,660,000 |  |  |  |  | **9,660,000.00** |
| Frontline workers (CDAs) oriented in revised Community Nutrition and Home Management manuals and guidelines | Number of frontline workers (CDAs) oriented in revised Community Nutrition and Home Management manuals and guidelines | 400 | 37,750,000 | 37,750,000.00 |  |  |  | **75,500,000.00** |
| Community leaders trained in Community Nutrition and Home Management | Number of community leaders trained in Community Nutrition and Home Management | 2,000 |  | 10,125,000 | 10,125,000 | 10,125,000 | 10,125,000 | **40,500,000.00** |
| Mothers and care group members’ skills of early malnutrition case detection and referral enhanced | Number of mothers and care group members’ skills of early malnutrition case detection and referral enhanced | 500,000 | 1,500,000 | 1,500,000 | 1,500,000 | 1,500,000 | 1,500,000 | **7,500,000.00** |
| Households practicing good hygiene and sanitation | Number of households practicing good hygiene and sanitation | 200,000 | 864,000 | 864,000 | 864,000 | 864,000 | 864,000 | **4,270,000.00** |
| Households reached with information promoting good nutrition practices, hygiene and sanitation | Number of households reached with information promoting good nutrition practices, hygiene and sanitation | 600,000 | 89,440,000 | 89,440,000 | 89,440,000 | 89,440,000 | 89,440,000 | **447,200,000.00** |
|  | Monitoring of Home management and Nutrition activities enhanced | Number of Monitoring of Home management and Nutrition activities conducted |  |  | 8,585,000 | 10,896,667 | 11,896,667 | 13,896,667 | **14,275,000.00** |
| Networking with Nutrition service providers strengthened | Number of coordination meetings conducted | 1396 |  | 11,140,173.00 | 12,140,173.00 | 13,140,173.00 | 14,140,173.00 | **15,140,173.00** |
| Crosscutting issues mainstreamed in Nutrition initiatives | Number of trainings and sensitizations in mainstreaming of Crosscutting issues mainstreamed in Nutrition initiatives |  |  | 42,675,000 | 14,400,000 | 14,400,000 | 14,400,000 | **85,875,000.00** |
| 5.2 80% of the target population sensitized on enhanced HIV AIDS education by 2021 | Men and boys reached campaigns rolled out in communities as part of He for She campaign to increase uptake of HCT, Treatment, VMMC, Condom use and promote gender equality and reduce GBV | Number of men and boys reached campaigns rolled out in communities as part of He for She campaign to increase uptake of HCT, Treatment, VMMC, Condom use and promote gender equality and reduce GBV | 600,000 | 52,480,000 | 52,480,000 | 52,480,000 | 52,480,000 | 52,480,000 | **262,400,000.00** |
| Strategy developed and implemented to sensitize the public on the 90:90:90 approach | Strategy developed and implemented to sensitize the public on the 90:90:90 approach | 1 |  | 35,585,000 | 16,146,666.67 | 16,146,666.67 | 16,146,666.67 | **87,305,000.00** |
| 5.3 50 % of rural and urban Village and Savings Loan groups equipped with business and value addition skills by 2021 | Economic Empowerment (Umodzi ndi Phindu) and VSL Training Manuals reviewed printed and distributed | Number of Economic Empowerment (Umodzi ndi Phindu) and VSL Training Manuals reviewed and copies of each printed and distributed | 2000 |  | 67,625,000 | 108,095,000 |  |  | **175,720,000.00** |
|  | Frontline workers (CDAs) trained in the VSL manual | Number of frontline workers (CDAs) trained in the VSL manual | 400 |  |  | 107,500,000 | 107,500,000 |  | **215,000,000.00** |
| Capacity of rural and urban business groups strengthened | Number of Capacity of rural and urban business groups strengthened | 5000 |  | 30,000,000 | 30,000,000 | 30,000,000 | 30,000,000 | **120,000,000.00** |
| VSL groups formed and Trained in group dynamics and management | Number of VSL groups formed and Trained in group dynamics and management | 1700 |  | 15,000,000 | 12,000,000 | 9,000,000 | 9,000,000 | **450,000,000.00** |
| VSL and business groups capacitated in cooperative management capacitated | Number of VSL and business groups /cooperative management capacitated | 40 |  | 300,000 | 300,000 | 300,000 | 300,000 | **1,200,000.00** |
| Business groups supported to access appropriate technology for value addition | Number of business groups supported to access appropriate technology for value addition | 300 |  | 232,000,000 | 232,000,000 |  |  | **464,000,000.00** |
| Business groups’ products marketed and promoted in local trade fairs | Number of business groups’ products marketed and promoted in local trade fairs | 60 |  | 27,625,000 | 27,625,000 | 27,625,000 | 27,625,000 | **110,500,000.00** |
| Manufacturing business groups linked to Malawi Bureau of Standards for certification of products | Number of manufacturing business groups linked to Malawi Bureau of Standards for certification of products | 100 |  |  | 11,125,000 | 11,125,000 |  | **22,250,000.00** |
| Trading houses established for small entrepreneurs | Number of trading houses established for small entrepreneurs | 4 |  |  | 15,380,000 |  | 15,380,000 | **30,760,000.00** |
| Coordination meetings conducted at all levels | Number of coordination meetings conducted at all levels | 4 |  | 77,860,000 | 77,860,000 | 77,860,000 | 77,860,000 | **311,440,000.00** |
|  | Monitoring framework for Community economic empowerment activities s developed and implemented | Number of Monitoring framework for Community economic empowerment activities s developed and implemented | 1 |  | 35,585,000 | 17,000,000 | 17,000,000 | 17,000,000 | **86,585,000.00** |
| 50% Capacity of Magomero Community Development College strengthened by 2021 | Certificate curriculum reviewed | Number of curricula reviewed and developed, | 1 | 7,450,000.00 | 0 | 0 | 0 | 0 | **7,450,000.00** |
| Diploma curriculum in Community Development developed | Number of curricula developed, | 1 | 11,445,000 | 0 | 0 | 0 | 0 | **11,445,000.00** |
| Stakeholder meeting conducted | Number of stakeholders meetings conducted | 1 | 18,780,000 | 0 | 0 | 0 | 0 | **18,780,000.00** |
| Approval meetings on development of diploma curriculum conducted | Number of meetings held | 1 | 2,605,000 | 0 | 0 | 0 | 0 | **2,605,000.00** |
| Writers’ workshop on the developing diploma curriculum in home management and nutrition conducted | Number of writers' workshops conducted | 1 | 0 | 10,195,000 | 0 | 0 | 0 | **10,195,000.00** |
| Stakeholder consultative and validation meeting in the development of diploma in Home Management and Nutrition conducted | Number of meetings conducted | 2 | 0 | 18,500,000 | 0 | 0 | 0 | **18,500,000.00** |
| Approval meetings on development of diploma curriculum in home management and nutrition conducted | Number of meetings held | 1 | 0 | 3,132,500 | 0 | 0 | 0 | **3,132,500.00** |
|  | Diploma curriculum in Home Management and Nutrition developed | Number of curricula developed, | 1 | 0 | 31,827,500.00 | 0 | 0 | 0 | **31,827,500.00** |
| Writers’ workshop on the developing degree curriculum in community development conducted | Number of writers' workshops conducted | 1 | 0 | 0 | 16,200,000 | 0 | 0 | **16,200,000.00** |
| Stakeholder consultative meeting on the development of degree curriculum in community development | Number of meetings conducted | 1 | 0 | 0 | 23,600,000 | 0 | 0 | **23,600,000.00** |
| Approval meetings on development of degree curriculum in community development conducted | Number of meetings held | 1 | 0 | 0 | 3,132,500 | 0 | 0 | **3,132,500.00** |
| Community Development Certificate/Diploma programme in community development conducted | Number of Community Development Certificate/Diploma programme in community development conducted | 5 | 20,000,000 | 30,765,000 | 32,765,000 | 36,765,000 | 38,765,000 | **159,060,000.00** |
| Community Development Diploma programme in home management conducted | Number of Community Development Diploma in home management and nutrition programme conducted | 3 | 0 | 0 | 15,456,667 | 18,456,667 | 20,456,667 | **54,370,000.00** |
| Certificate course in agro-food processing conducted | Number of course conducted | 4 | 0 | 42,785,000 | 42,785,000 | 42,785,000 | 42,785,000 | **171,140,000.00** |
| Community Development Degree programme conducted | Number of Community Development degree courses conducted | 2 | 0 | 0 | 0 | 14,400,000 | 24,400,000 | **38,800,000.00** |
|  | Community Development professional courses for continuous development developed | Number of Community Development professional courses for continuous development developed | 3 | 16,230,000 | 16,230,000 | 16,230,000 | 0 | 0 | **48,690,000.00** |
| Continuous professional training courses for serving community development officers conducted | Number of courses conducted | 12 | 27,350,000 | 30,350,000 | 34,350,000 | 37,350,000 | 0 | **129,400,000.00** |
| Tailor made courses developed | Number of Tailor made courses developed | 4 | 0 | 12,716,250 | 12,716,250 | 12,716,250 | 12,716,250 | **50,865,000.00** |
| Tailor-made training courses for individuals and organizations conducted | Number of courses conducted | 4 | 0 | 67,200,000 | 67,200,000 | 67,200,000 | 67,200,000 | **268,800,000.00** |
| E- Learning infrastructure developed | E- Learning infrastructure developed | 1 | 0 | 0 | 91,100,000 | 0 | 0 | **91,100,000.00** |
| Writers' workshop on the development of E-Learning programme materials conducted | Number of workshop conducted | 2 | 0 | 0 | 10745000 | 10745000 | 0 | **21,490,000.00** |
| Tailor made courses under ODL conducted | Number of courses under ODL developed | 2 | 0 | 0 | 0 | 9,730,000 | 9,730,000 | **19,460,000.00** |
| Appropriate technology Centre improved and operationalized | Number of AT centers improved and operationalized | 4 | 14,500,000 | 2,780,000 | 7,800,000 | - | - | **25,080,000.00** |
| College farm operationalized | College farm operationalized | 1 | - | 8,020,000 | 8,020,000 | 8,020,000 | 8,020,000 | **32,080,000.00** |
| Magomero College infrastructure improved | Number of infrastructure improved | 11 | 60,000,000 | 60,000,000 | 60,000,000 | 60,000,000 | 60,000,000 | **300,000,000.00** |
| Existing structures rehabilitated and furnished | Number of structures rehabilitated and furnished | 5 | 26,460,000 | 26,460,000 | 26,460,000 | 26,460,000 | 26,460,000 | **132,300,000.00** |
|  | Academic and administrative capacity enhanced | Academic and administrative capacity enhanced | 8 | 1,030,000 | 20,500,000 | 20,500,000 | 37,200,000 | 37,200,000 | **116,430,000.00** |
| Academic and administrative capacity enhanced | Number of vehicles procured | 3 | - | 270,000,000 | 6,500,000 | 6,500,000 | 6,500,000 | **289,500,000.00** |
| In service trainings conducted | Number of trainings conducted | 15 | - | 10,625,000 | 10,625,000 | 10,625,000 | 10,625,000 | **42,500,000.00** |
| Academic research for professional development conducted | Number of academic research conducted | 10 | - | 100,300,000 | 100,300,000 | 100,300,000 | 100,300,000 | **401,200,000.00** |
| Magomero College registered and accredited by TEVETA and NCHE | Number of institutions registered and accredited | 1 | 33,977,500 | 33,977,500 | 0 | 0 | 0 | **67,955,000.00** |
| Magomero College programmes registered and accredited by TEVETA and NCHE | Number of programmes registered and accredited | 3 | 3,132,500.00 | 2,420,000 | 3,132,500 | 0 | 0 | **8,685,000.00** |
| **Sub - Total** | **Sub -Total** |  |  | **448,574,000.00** | **1,574,922,923.00** | **1,456,495,423.34** | **989,655,423.34** | **855,315,423.34** | **5,666,772,673.00** |
| **Key Result Area: Administration and Management** | | **Strategic Outcome1: Improved Institutional Capacity and Organizational Management** | | | | | | | |
| **90% of the programs implemented efficiently and effectively by 2021** | Strategic plan developed | Strategic plan developed | 1 |  | 28,000,000 | 16,000,000 |  |  | **44,000,000.00** |
| Strategic Plan launched and disseminated | Strategic Plan launched and disseminated | 1 |  | 5,170,000 |  |  |  | **5,170,000.00** |
| Annual Work plan developed and implemented | Annual Work plan develop and implemented | 1 | 5,590,000 | 5,600,000 | 5,650,000 | 5,700,000 | 5,750,000 | **28,290,000.00** |
| Budget formulated and implemented | Budget formulated and implemented | 1 | 14,190,000 | 14,190,000 | 14,250,000 | 14,500,000 | 14,650,000 | **71,780,000.00** |
| Performance contract developed and implemented | Performance contract developed and implemented | 1 | 4,820,000 | 4,880,000 | 4,920,000 | 5,200,000 | 5,420,000 | **25,240,000.00** |
| Service charter developed | Service charter developed | 1 | 5,540,000 |  |  |  |  | **5,540,000.00** |
| Service charter launched and disseminated | Service charter launched and disseminated | 1 |  |  | 12,000,000 |  |  | **12,000,000.00** |
|  | Meeting to validate Programme of Action for Community Development and Culture Policy conducted | Number of meetings conducted | 1 |  | 3,690,000 |  |  |  | **3,690,000.00** |
|  | Consultant to develop Management Information System identified | Number of consultants identified | 1 |  | 500,000 |  |  |  | **500,000.00** |
| Improved ICT infrastructure in place and operational by 2021 | Train staff on website management | Number of staff trained | 6 |  | 3,020,000 |  |  |  | **3,020,000.00** |
| IT staff and infrastructure established and recruited | IT staff and infrastructure established and recruited | 2 |  | 6,500,000 |  |  |  |  |
| Vacancy rate reduced from 54% to 10% by 2021 | 303 employees recruited | Number of employees recruited | 303 | 1,956,000 | 1,956,000 | 1,956,000 | 1,956,000 | 1,956,000 | **9,780,000.00** |
| Institutional Performance improved by 80% by 2021 | Training plan developed and implemented | Training plan developed and implemented | 1 | 121,910,000 | 121,910,000 | 121,910,000 | 121,910,000 | 121,910,000 | **609,550,000.00** |
| HIV/AIDS , gender and disability issues mainstreamed in all programs by 2021 | HIV/AIDS workplace program developed and mainstreamed | HIV/AIDS workplace program developed and mainstreamed | 1 | 3,770,000 | 3,770,000 | 3,770,000 | 3,770,000 | 3,770,000 | **18,850,000.00** |
| 90% of administrative service provision | Administrative services provided | Administrative services provided | 5 | 60,000,000 | 70,800,000 | 77,880,000 | 85,668,000 | 94,234,800 | **388,582,800.00** |
| Office services and supplies provided | Administrative services provided | 5 | 48,800,000 | 53,680,000 | 59,048,000 | 64,952,800 | 71,448,080 | **297,928,880.00** |
| Annual procurement Plan developed and Implemented | Annual procurement plan developed | 5 | 3,800,000 | 4,180,000 | 4,598,000 | 5,057,800 | 5,563,580 | **23,199,380.00** |
| 100% Cost Centers audited by 2021 | Annual Risk Based Internal Audit Plan developed | Annual Risk Based Internal Audit Plan developed | 5 | 4,662,000 | 5,000,000 | 6,000,000 | 7,000,000 | 8,000 | **22,670,000.00** |
|  | Carry out Internal Audit Exercises | Cost centers audited | 5 | 4,368,000 | 5,000,000 | 6,000,000 | 7,000,000 | 8,000,000 | **30,368,000.00** |
|  | Attend Audit Committee meetings | Meetings conducted | 5 | 444,000 | 600,000 | 700,000 | 800,000 | 900,000 | **3,444,000.00** |
| Annual/Quarter Reports produced | Reports produced | 5 | 128,000 | 300,000 | 400,000 | 500,000 | 600,000 | **1,928,000.00** |
| **Sub -Total** |  |  |  | **279,978,000.00** | **338,746,000.00** | **335,082,000.00** | **324,014,600.00** | **334,210,460.00** | **1,605,531,060.00** |
|  |  |  |  |  |  |  |  |  |  |
| **GRAND TOTAL** |  |  |  | **1,685,451,618.35** | **3,799,250,517.49** | **4,252,383,454.83** | **3,239,561,852.77** | **3,497,312,251.23** | **16,809,269,174.65** |