## Sheet1
Evalauation Recommendations for Future Similar Projects
Evaluation | Recommendations | Management Response
UNDP-GEF Terminal Evaluation of Sustainable Land Management | Gender leadership building training should be conducted to develop women leadership in sustainable land management and decision related to these. | Partially accept - This project is financially closed and can’t embark on new activities. This recommendation could only be carried over for implementation for new projects.
| The vegetable cultivation program for each household was very small. It could not even meet the household needs. So, it is recommended to provision vegetable program including most demanded species and in a size that will meet household need and also could sell for income. For economic benefit, include high value species so that they could earn more and that will help to reduce vulnerability of households. | Partially accept - The purpose of household gardens was to demonstrate the possibility of vegetable gardens towards household food security, not to ensure each household will receive enough seed to make it economically viable for them.
| PMU of the future projects should be housed in the implementing agency’s building or nearby so that close communication will be maintained. It is important that consensus is achieved between the PMU and the implementing Partner on roles and responsibilities to ensure a clear distinction between day-to-day management and strategic guidance and oversight functions. That will help to avoid communication and coordination gaps that was observed in this project. | Fully accept - For future projects these considerations will be taken into account. These arrangements depend on the implementation modality that is agreed with the Implementing Partner at design phase and capacity of IPs to provide accommodation for PMU.
| The gender equity and gender issues were not discussed or considered in the project development of this project. The EWT conducted gender survey and made strategy but other didn’t. It is recommended to discuss gender issues in project design and planning work plans in the future projects. | Partially accept - It is important to consider that GEF5 projects did not have gender specific indicators and/or activities as part of their design. In that sense, the project did not consider any gender disaggregated indicators. Nevertheless, the Project promoted a gender approach to its activities. Two working teams for rehabilitation, one in Karoo and one in Olifants, consist mainly of women to empower them as well. The team composition of the different Responsible Parties were also well balanced with regard to gender with a 50/50 split of men and women working on the project. That include students as well.
| It is recommended that in the future projects, involve the service providers who have long experience in relevant programme implementation in rural areas and also has office base (active and permanent presence in the landscape) on the pilot sites or nearby areas. With similar intension, MTR also suggested to involve local NGO | Fully accept - This will only be relevant for future projects. The emphasis must be on experience and skills for successful implementation and avoiding high transaction and project costs for implementing project activities from a distance.
| Land degradation problem is very big so there is need of big effort to address it. Hence, it is recommended to develop mega project to address land degradation in SA using lessons from this project and similar other projects. The key findings and recommendations from the SLM Finance Strategy should guide the financing of such a mega project or projects. | Fully accept
| It is recommended to make provision in projects, pre-training assessment and post training assessment. In this project no information was available how baseline scores were developed. | Fully Agree - During the design and implementation of future projects, training activities will be planned, conducted, and assessed accordingly through a range of evaluation techniques.
End of Project Evaluation on Automotive Training and ReSkilling in the Post-COVID Economic Recovery for Vulnerable Youth and Women in South Africa | That UNDP staff capacity be increased if the scope of the project is increased. Rationale: The current UNDP staff complement was insufficient for the size and scope of the workload. While the current team was competent and accomplished most targets, this may not be replicated should the scope of future phases increase; additional staff will be essential.