## Sheet1
Action Area | Activity | [8 empty] | Milestone | Indicative Amount | Comment- Grant
|  | 2022 |  |  |  | 2023
|  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Public Awareness and Communications | Public awareness campaign activities in all ORASECOM Member States (e.g. community mobilization, media) | 2022 Q1: Communications firm engaged; 2022 Q3: Concept idea developed; 2022 Q4: Full strategy approved by ORASECOM; 2023 Q4: Campaign implementation | 1.Communications firm engaged 2. Concept idea developed and presented 3.Draft Strategy presented 4. Full strategy approved by ORASECOM, 5. Campaign implemented (08-10/23) | 200,00 | Grounded Media (Service Contract)
| Update of ORASECOM knowledge management platforms (e.g. website, outreach material, best practices) | 2023 Q1: Needs assessment from ORASECOM | 1.Needs Assessment from ORASECOM 2. Agree on the modalities 3. Develop TOR 4. Contracting
Inter-basin dialogue and regional learning | Advertising WaterNet courses in basin and region | [8 empty] | A broucher with calendar showing planned courses, venue and dates | 200000 | WaterNet Grant
| Showcasing at WaterNet Symposium | [8 empty] | 1. Presentation on the capacity building program within ReNOKA 2. Flyer showing courses and details
Faciltating participation in the courses from the basin to the region based on the WaterNet concept note
Protection of critical ecosystems | Development of transboundary integrated catchment management development plans (ICMDP) Upper Mohokare and Makhaleng | [8 empty] | 1. Selection of the firm 2.Inception report 3. ICMP of Upper Mohokare | 600000 | Service Contract (tbc)
Update of ORASECOM strategic frameworks | Advancing lessons learnt on climate resilience in strategic frameworks of ORASECOM (e.g. analyses, guidelines, manual) | [8 empty] | 1. Meeting held between GIDRM and ORASECOM to share the concept and present available opportunities in the programme 2. Agreement on way forward 3. Action plan drawn | 100000 | GIDRM
| Extending the Land Cover Atlas into the Orange Senqu River Basin | [8 empty] | 1. Concept shared with ORASECOM. 2. Discussions about modalities held and a way forward mapped out |  | Firm TBC