## Project Evaluation Plan
UNDP SOMALIA: CO EVALUATION PLAN 2011 - 2017
Country Office |  |  |  | Somalia
Overall Responsibility: |  |  |  | Country Director
Version: |  |  |  | v1.1 06.2017
Status: |  |  |  | Draft
Effective Date: |  |  |  | 01.01.2011 (Retroactive) - 12.12.2017
Next Review Date: |  |  |  | 31.12.2017
Informed By: |  |  |  | CPD, Prodocs, Master Work Plan, D.1 Project Evaluation Plans, E.1 Program Evalation Plans
Region | Program | Project | Evaluation Type | Evaluation Title | Methodology | Process Indicators | Non-CPD Outcome Indicators | CPD Attribution | Start / End Date | Status | Key Evaluation Stakeholders | Internal Responsibility | External Responsibility | Partners (Joint Evaluation) | Evaluation Funding Source | Mandatory Evaluation | Budget
ALL | HIV / AIDS | HIV / AIDS | Outcome / Process | HIV / AIDS: End of project cycle | Mixed method | TBC | TBC | Outcome 3 and 4 | 10.2015 - 12.2015 | For 2015 | Donors, UN agencies, civil society, public sector actors, private sector actors, beneficiaries | HIV / AIDS | Outsourcing: TBC | TBC | Global Fund | Yes | TBC
ALL | GROL | SIDP | Process | EC SIDP evaluation | NA | NA | NA | NA | 10.2011 - 02.2012 | Completed | EC, Government partners | SIDP | EC | In partnership with other donors | EC | Yes | NA
ALL | PREP | LED | Outcome / Process | LED evaluation | RCT (TBC) | TBC | TBC | Outcome 3 and 4 | 09.2012 - 12.2012 | Completed | Donors, UN agencies, civil society, public sector actors, private sector actors, beneficiaries | PREP | Outsourcing: TBC | TBC | Program (via interested donors) | Yes | 188599
All | GROL | Comm. Security | Process | Youth at Risk pilot project Tracer study | Tracer study | TBC | NA | Outcomes 1-4 | 10-2012 - 12-2012 | Completed | Donors, UN agencies, civil society, public sector actors, private sector actors, beneficiaries | Community Security | Outsourcing to NRC -International Consultant | ILO, UNICEF | GOJ | NO | 55000
ALL | ALL | ALL | Outcome | CO outcome evaluation: Mid term review (including Outcome reports for each CPD outcome) | Mixed method | NA | NA | 24 CPD outcome indicators | 2014-06-01 | Completed through ADR | Donors, UN agencies, civil society, public sector actors, private sector actors, beneficiaries | CO PPU M&E | Outsourcing: TBC | NA | TRAC | Yes | TBC
ALL | ROLS | ALL | Process | UNDP Somalia rule of law and security evaluation | NA | NA | NA | NA | 09.2011 - 12.2011 | Completed | Donors, UN agencies, civil society, public sector actors | ROLS Program | BCPR + Consultant | NA | ROLS Projects | Yes | 50000
ALL | GROL | SIDP | Outcome / Process | SIDP evaluation: End of project cycle | Mixed method | TBC | TBC | Outcome 2 | 10.2014 - 12.2014 | Completed | Donors, UN agencies, civil society, public sector actors, private sector actors, beneficiaries | SIDP | Outsourcing: TBC | TBC | Project | Yes | 50000
ALL | ROL | A2J/CSP/CPP | Outcome / Process | ROL/B&I end of project evaluation | Mixed method | TBC | TBC | Outcome 3 and 4 | 1.2015 - 3.2015 | Completed | Donors, UN agencies, civil society, public sector actors, private sector actors, beneficiaries | ROL | BCPR Roster to be consulted | TBC | Global Fund | Yes | 59658
ALL | HIV / AIDS | HIV / AIDS | Outcome / Process | HIV / AIDS: Mid term review | Mixed method | TBC | TBC | Outcome 3 and 4 | 10.2013 - 12.2013 | Completed | Donors, UN agencies, civil society, public sector actors, private sector actors, beneficiaries | HIV / AIDS | Outsourcing: TBC | TBC | Global Fund | Yes | TBC
ALL | GROL | Parliament | Project | Parliament Mid term review | Mixed method | TBC | TBC | Outcome 2 | 2017-06-01 | In Process | Donors, public sector actors, beneficiaries | Parliament | Outsourcing: TBC | NA | Project | No | 89092
ALL | GROL | ROL | Project | MPTF ROL | Mixed Method | TBC | TBC | Outcome 2 and 4 | April 2017 - Sep 2017 | Initiated | Donors, UN agencies, civil society, public sector actors, private sector actors, beneficiaries | GROL | Outsourcing: TBC | TBC | Project | Yes | 80000
ALL | CCU | GEWE | Project | Gender Equality and Women's Empowerment | Mixed Method | TBC | TBC | Outcome 4 | July 2017 - Dec 2017 | Not initiated | Donors, UN agencies, civil society, public sector actors, private sector actors, beneficiaries | CCU | Outsourcing: TBC | TBC | Project | Yes | 80000
ALL | CDU | SIP | Project | Project evaluation | Mixed Method | TBC | TBC | Outcome 2 | 2017-08-01 | Initiated | Donors, UN agencies, civil society, public sector actors, private sector actors, beneficiaries | CDU | Outsourcing: TBC | TBC | Project | Yes | 80000
ALL | PREP | JPLG | Project | End of Project Evaluation | Mixed Method | TBC | TBC | Outcome 2 | 2017-07-01 | Not initiated | Donors, UN agencies, civil society, public sector actors, private sector actors, beneficiaries | GROL | Outsourcing: TBC | TBC | Project | Yes | 80000
ALL | PREP | CCR | Project | End of Project Evaluation | Mixed Method | TBC | TBC | Outcome 3 | 2017-07-01 | Initiated | Donors, UN agencies, civil society, public sector actors, private sector actors, beneficiaries | PREP | Outsourcing: TBC | TBC | Project | Yes | 80000