**UNDP Bahrain**

**2012-2016 Country Programme Monitoring & Evaluation Plan**

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **CPD Outcome** | **Strategic Plan Results Area** | **Evaluation Title** | **Partners (joint evaluation)** | **Evaluation commissioned by (if not UNDP)** | **Type of evaluation** | **Planned Evaluation Completion Date** | **Estimated Cost** | **Provisional Source of Funding** |
| **Improved Governance:**  Strengthened capacity to formulate plans and policies more efficiently, fairly and transparently | SP Outcome 2: Voice, development, RoL and accountability are met by stronger democratic governance | Terminal evaluation of the Capacity Development Facility | **Bahrain Institute for Public Administration**  Civil Service Bureau  e-Government Authority  Tamkeen | UNDP | Decentralised project-level evaluation | March 2015 | US$ 10,000 | Project budget |
| Terminal evaluation of UNDP support to the Universal Periodic Review (UPR) | **Ministry of Foreign Affairs**  **Ministry of Human Rights**  Ministry of Human Rights & Social Development,  Bahrain HR Society,  Transparency NGO,  Supreme Council for Women,  Bahraini Women Union,  General Federation of Trade Unions, NIHR, MOI, MOF | UNDP | Decentralised project-level evaluation | March 2012 | US$ 20,000 | Project budget |
| **CPD Outcome** | **Strategic Plan Results Area** | **Evaluation Title** | **Partners (joint evaluation)** | **Evaluation commissioned by (if not UNDP)** | **Type of evaluation** | **Planned Evaluation Completion Date** | **Estimated Cost** | **Provisional Source of Funding** |
| **Inclusive Sustainable Development:**  More women empowered, youth unemployment reduced and national environmental protection actively pursued | SP Outcome1: Growth and Development are inclusive & sustainable;  SP Outcome 4: Progress in reducing gender inequality & promoting women empowerment | Evaluate the effectiveness of UNDP programmes in addressing  social policies and strategies benefiting  women, children, disabled persons and youth | Ministry of Social Development  Supreme Council for Women  General Organization for Youth  Bahraini Women Union  Ministry of Culture  Central Informatics Organization | UNDP | Outcome level evaluation | Jan-March 2015 | US$ 50,000 | Relevant Projects’ Budgets |
| Terminal evaluation of the national strategies on childhood and persons with disabilities | **Ministry of Social Development**  National Committee on Childhood,  National Committee on Disability,  National Union for Disabilities,  Bahrain Association for Lawyers,  Supreme Council for Women,  UNICEF | UNDP | Decentralised project-level evaluation | April 2014 | US$ 7,000 | Project budget |
| **CPD Outcome** | **Strategic Plan Results Area** | **Evaluation Title** | **Partners (joint evaluation)** | **Evaluation commissioned by (if not UNDP)** | **Type of evaluation** | **Planned Evaluation Completion Date** | **Estimated Cost** | **Provisional Source of Funding** |
| **Economic Development:**  Knowledge-based and private-sector growth for sustainable pro-poor and pro-women development | SP Outcome 7:  Development debates prioritizing poverty, inequalities and exclusion, consistent with our engagement policies.  SP Outcome 4: Progress in reducing gender inequality & promoting women empowerment | Terminal evaluation of the Institutional Capacity for Global Economic Environment & Globalization Programme | **Ministry of Industry and Commerce**  Economic Development Board  e-Government Authority | UNDP | Decentralised project-level evaluation | March 2015 | US$20,000 | Project budget |
| Terminal evaluation of the Gender and Economic Policy Management Initiative (GEPMI) | **University of Bahrain**  Supreme Council for Women  Arabian Gulf University  Bahrain Institute for Public Administration  Central Informatics Organization | UNDP | Decentralised project-level evaluation | Dec 2016 –  Jan 2017 | US$20,000 | Project budget |
| **CPD Outcome** | **Strategic Plan Results Area** | **Evaluation Title** | **Partners (joint evaluation)** | **Evaluation commissioned by (if not UNDP)** | **Type of evaluation** | **Planned Evaluation Completion Date** | **Estimated Cost** | **Provisional Source of Funding** |
| **Mid-Term CPD Evaluation** | All | Mid-Term Evaluation of the Country Programme | **Ministry of Foreign Affairs**  **Ministry of Finance**  Economic Development Board  CP Counterparts | UNDP | Decentralized Outcome level Evaluation | April – May 2015 | US$ 45,000 | DAS |
| **Final CPD Evaluation** | All | Final Evaluation of the Country Programme 2012-2016 | **Ministry of Foreign Affairs**  **Ministry of Finance**  Economic Development Board  CP Counterparts | UNDP | Decentralized Outcome level Evaluation | Dec 2016 –  Jan 2017 | US$ 45,000 | DAS |
| **Monitoring activities** | All | Project monitoring is incorporated in UNDP and PSC staff visits to the Implementing Partners and their facilities. Project Board (or Project Steering Committee) meetings are also means for monitoring.  As projects are within Manama and there are no sub-offices or activities outside Manama there are no monitoring visits planned. | | | | | All monitoring activities are financed directly from the Project budgets | |

\*Due to delays experienced in finalizing the 2012-2016 CPAP document with the Government of Bahrain, the Monitoring and Evaluation Plan is based on the CPD Evaluation Plan approved by the EB in September 2010.

\*\*The CPD Monitoring and Evaluation Plan was updated in March/April 2014 due to delays in signing the CPAP and to align with the new SP.

\*\*\*Version as of 30 April 2014.