## ERC 2019 final
SN | Title | Type | Partners (Joint Evaluations) | Planned End Date | Key Stake holders | Resource & Fund Source | Comments for RBAS
1 | Évaluation finale - Appui au processus de justice transitionnelle (Phase II) | Project |  | 2019-09-01 | -- | $25 000 | Mandatory evaluation
2 | Évaluation à mi-parcours - Appui à la préparation, prévention et gestion des crises (PPRC) | Project |  | 2019-05-01 | -- | $25 000 | Evaluation in review process
3 | Évaluation à mi-parcours - Appui au NAMA PST | Project |  | 2019-07-01 | -- | $15 000 | Avaluation done, reviewed - waiting for COPIL validation letter to be able to upload
4 | Évaluation finale - Appui au NAMA PST | Project |  | 2019-11-01 | -- | $20 000 | Mandatory - recommandation to launch the evaluation process given
5 | Evaluation Finale - Résilience côtière | Project |  | 2019-12-01 | -- | $20 000 | Mandatory - (to be noted that the mid-term evaluation, due to 2017, isn't done yet, as the the initiated one was refused - process re-lauched in march)
6 | Évaluation à mi-parcours - Renforcement de l'engagement citoyen | Project |  | 2019-06-01 | -- | $20 000 | Evaluation on process
7 | Evaluation finale - Renforcement de la redevabilité publique | Project |  | 2019-09-01 |  | $ 15000 | Mandatory - negociations on process with donor (KOICA) to cancel it as the mid-term evaluation hasn't been validated yet
8 | Évaluation finale - Assistance électorale | Project |  | 2020-05-01 | -- | $15 000 | Evaluation planed for december 2019 after the Tunisian elactions to be done - Mandatory - only evaluation planed for 2020
Formulas:
Planned End Date = [1]Gouvernance!P3
Planned End Date = [1]CERC!O4