**UNDP CO INDONESIA EVALUATION PLAN *(PROGRAMME PERIOD 2016-2020)***

| **UNPDF/CPD Outcome** | **UNDP SP Outcome (2018-2021)** | **UNDP SP Output (2018-2021)** | **Award ID** | **Project Name** | **Midterm Evaluation Title** | **Planned Midterm Evaluation  Completion Date** | **Actual Midterm Evaluation  Completion Date** | **Final Evaluation Title** | **Planned Final Evaluation  Completion Date** | **Actual Final Evaluation  Completion Date** | **Partners (Joint Evaluation)** | **Evaluation commissioned by  (if not UNDP)** | **Type of evaluation** | **Estimated Cost (USD)** | **Provisional Source of Funding** |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| CPD Outcome 1-4 | SP Outcome 1-3 | SP Outputs | - | CPD Midterm Evaluation | Midterm Evaluation | Dec-19 |  | N.A. | N.A. | N.A. | BAPPENAS | - | CPD Evaluation | 50,000 | Development Effectiveness |
| CPD Outcome 3 | SP Outcome 2 | SP Output 2.3.1 | 51288 | Disaster Risk Reduction based Rehab.& Reconst. (DR4) | Midterm Evaluation | Aug-14 | Oct-14 | Not required | N.A. | N.A. | BNPB | - | Project Evaluation | 35,000 | Project budget |
| CPD Outcome 3 | SP Outcome 1 | SP Output 1.4.1 | 56845 | GEF - Strengthening Community Based Forest and Watershed | GEF Midterm Evaluation | Jul-12 | Sep-12 | GEF Terminal Evaluation | Oct-15 | Oct-15 | KLHK | - | Project Evaluation | 30,000 | Project budget |
| CPD Outcome 3 | SP Outcome 1 | SP Output 1.5.1 | 60776 | GEF - Wind Hybrid Power Generation (WHyPGen) Market Development | GEF Midterm Evaluation | Dec-14 | Sep-14 | GEF Terminal Evaluation | Jun-17 | Jul-17 | KLHK | - | Project Evaluation | 15,000 | Project budget |
| CPD Outcome 4 | SP Outcome 2 | SP Output 2.2.3 | 61763 | Strengthening Access to Justice in Indonesia (SAJI) | Midterm Evaluation | Oct-14 | Oct-14 | Not required | N.A. | N.A. | BAPPENAS | - | Project Evaluation | 25,000 | Project budget |
| CPD Outcome 3 | SP Outcome 1 | SP Output 1.5.1 | 68398 | GEF - Strategic Planning and Action to Climate Resilience (SPARC) | GEF Midterm Evaluation | Sep-16 | Sep-16 | GEF Terminal Evaluation | Oct-18 |  | KLHK | - | Project Evaluation | 35,000 | Project budget |
| CPD Outcome 3 | SP Outcome 2 | SP Output 2.3.1 | 71676 | Safer Communities through Disaster Risk Reduction (SCDRR) | Midterm Evaluation | Sep-16 | Sep-16 | Project Evaluation | Jul-18 |  | BNPB | - | Project Evaluation | 20,000 | Project budget |
| CPD Outcome 3 | SP Outcome 2 | SP Output 2.1.1 | 75619 | REDD+ Interim Phase | Not required | N.A. | N.A. | Project Evaluation | Jun-17 | Mar-17 | KLHK | - | Project Evaluation | 30,000 | Project budget |
| CPD Outcome 3 | SP Outcome 2 | SP Output 2.3.1 | 75809 | GEF - Third National Communication to The UNFCCC - Full Size (TNC) | GEF Midterm Evaluation | Dec-16 | Dec-16 | GEF Terminal Evaluation | Dec-17 | Dec-17 | KLHK | - | Project Evaluation | 25,000 | Project budget |
| CPD Outcome 3 | SP Outcome 1 | SP Output 1.4.1 | 77733 | GEF - Enhancing Protected Area in Sulawesi (E-PASS) | GEF Midterm Evaluation | Aug-18 |  | GEF Terminal Evaluation | Oct-20 |  | KLHK | - | Project Evaluation | 35,000 | Project budget |
| CPD Outcome 4 | SP Outcome 2 | SP Output 2.2.3 | 82733 | Support to the Justice Sector Reform in Indonesia (SUSTAIN) | Managed by EU | N.A. | N.A. | Project Evaluation | May-19 |  | MA | - | Project Evaluation | 62,683 | Project budget |
| CPD Outcome 1 | SP Outcome 1 | SP Output 1.4.1 | 82941 | Sustainable Palm Oil | Not required | N.A. | N.A. | Project Evaluation | Nov-18 |  | KEMENTAN | - | Project Evaluation | 10,000 | Project budget |
| CPD Outcome 3 | SP Outcome 1 | SP Output 1.4.1 | 83160 | GEF - FSP Reducing PBDE and UPOPs | GEF Midterm Evaluation | Dec-18 |  | GEF Terminal Evaluation | Dec-19 |  | KEMENPERIN | - | Project Evaluation | 35,000 | Project budget |
| CPD Outcome 3 | SP Outcome 1 | SP Output 1.4.1 | 83791 | GEF - Global Marine Commodities | GEF Midterm Evaluation | Apr-20 |  | GEF Terminal Evaluation | Jan-22 |  | BAPPENAS | - | Project Evaluation | 14,000 | Project budget |
| CPD Outcome 3 | SP Outcome 1 | SP Output 1.4.1 | 85001 | GEF - Biodiversity Conservation in Sumatra | GEF Midterm Evaluation | Jul-19 |  | GEF Terminal Evaluation | Jul-20 |  | KLHK | - | Project Evaluation | 80,000 | Project budget |
| CPD Outcome 3 | SP Outcome 2 | SP Output 2.4.1 | 85815 | GEF - Kalimantan Forest | GEF Midterm Evaluation | Jun-21 |  | GEF Terminal Evaluation | Nov-24 |  | KLHK | - | Project Evaluation | 160,000 | Project budget |
| CPD Outcome 3 | SP Outcome 2 | SP Output 2.5.1 | 86173 | GEF - Market Transformation | GEF Midterm Evaluation | Jul-19 |  | GEF Terminal Evaluation | Mar-22 |  | ESDM | - | Project Evaluation | 70,000 | Project budget |
| CPD Outcome 3 | SP Outcome 1 | SP Output 1.4.1 | 90780 | GEF - MSP - Cross Cutting Capacity (CCC) | GEF Midterm Evaluation | Aug-18 |  | GEF Terminal Evaluation | Feb-20 |  | KKP | - | Project Evaluation | 35,000 | Project budget |
| CPD Outcome 3 | SP Outcome 1 | SP Output 1.4.1 | 94636 | GEF - Illegal Wildlife Trade (IWT) | GEF Midterm Evaluation | Apr-19 |  | GEF Terminal Evaluation | Apr-22 |  | KLHK | - | Project Evaluation | 35,000 | Project budget |
| CPD Outcome 3 | SP Outcome 2 | SP Output 2.1.1 | 96630 | Support Facility for the Peat Restoration Agency Setup | Not required | N.A. | N.A. | Project Evaluation | Jul-18 |  | BRG | - | Project Evaluation | 30,000 | Project budget |
| CPD Outcome 3 | SP Outcome 2 | SP Output 2.5.1 | 97002 | Partnership Market Readiness (PMR) | Not required | N.A. | N.A. | Project Evaluation | Jun-19 |  | KEMENKO EKONOMI | - | Project Evaluation | 35,000 | Project budget |
| CPD Outcome 3 | SP Outcome 2 | SP Output 2.4.1 | 98670 | Support to Institutionalizing the Multi-Door Approach | Not required | N.A. | N.A. | Project Evaluation | Dec-18 |  | KLHK | - | Project Evaluation | 35,000 | Project budget |
| CPD Outcome 4 | SP Outcome 3 | SP Output 3.2.1 | 101963 | Enhancing the Role of Religious Education in CVE | Not required | N.A. | N.A. | Project Evaluation | Mar-19 |  | UIN | - | Project Evaluation | 15,000 | Project budget |
| CPD Outcome 3 | SP Outcome 1 | SP Output 1.4.1 | 104290 | GEF - Sixth OP of the GEF SGP in Indonesia | GEF Midterm Evaluation | Jun-19 |  | GEF Terminal Evaluation | Mar-21 |  | KLHK | - | Project Evaluation | 45,000 | Project budget |